## Q1_20_21 all data
DfT Group | Project Name | Risk Number | Brief Risk Description | BRD Risk Category | BRD Primary Risk to | BRD Internal Control | BRD Mitigation - Actions taken (brief description) | BRD Residual Impact | BRD Residual Likelihood | Severity Score Risk Category | BRD Has this Risk turned into an Issue?
AMIS | Mars | 1 | What you see if all there is | Economic | Costs | Treat - Prevent |  | High | Medium | Medium | No
AMIS | Mars | 2 | hammer | Economic | Schedule | Treat - Prevent |  | High | Medium | Medium | No
AMIS | Mars | 3 | plastic | Technological | Schedule | Treat - Prevent |  | Medium | Medium | Medium | No
AMIS | Mars | 4 | Green lumber fallacy | Political | Benefits | Treat - Prevent |  | Medium | Medium | Medium | No
AMIS | Mars | 5 | Memento mori and amor fati | Political | Schedule | Treat - Prevent |  | Medium | Medium | Medium | No
AMIS | Mars | 6 | Memento mori and amor fati | Technological | Schedule | Treat - Prevent |  | Medium | Medium | Medium | No
RPE | SoT | 1 | What you see if all there is | Political | Costs | Treat - Prevent |  | Low | Low | Low | No
RPE | SoT | 2 | Green lumber fallacy | Economic | Schedule | Treat - Prevent |  | Low | Low | Low | No
RPE | SoT | 3 | hammer | Political | Schedule | Treat - Prevent |  | Medium | Low | Low | No
RPE | SoT | 4 | screw driver | Social | Costs | Treat - Directive |  | Medium | Low | Low | No
RPE | SoT | 5 | The mind is not a vessel to be filled but a fire to be lighted | Social | Benefits | Treat - Prevent |  | Low | Low | Low | No
RPE | SoT | 6 | Memento mori and amor fati
RSS | A13 | 1 | What you see if all there is | Technological | Benefits | Treat - Prevent |  | High | High | High
RSS | A13 | 2 | The sea gets deeper the further you go into it | Economic | Benefits | Treat - Prevent |  | Medium | Medium | Medium
RSS | A13 | 3 | Don't you know an apparition is just a cheap date. What have you been drinking these days | Economic | Costs | Treat - Prevent |  | Low | Medium | Low
RSS | A13 | 4 | What you see if all there is | Economic | Benefits | Treat - Corrective |  | Medium | Low | Low
RSS | A13 | 5 | nail | Economic | Benefits | Tolerate |  | Low | High | Low
RSS | A13 | 6 | Memento mori and amor fati | Technological | Benefits | Treat - Corrective |  | High | Low | Low
RPE | F9 | 1 | The sea gets deeper the further you go into it | Environmental | Costs | Treat - Corrective |  | High | Medium | Medium | No
RPE | F9 | 2 | hammer | Political | Benefits | Tolerate |  | Very High | Low | Low | No
RPE | F9 | 3 | The mind is not a vessel to be filled but a fire to be lighted | Economic | Costs | Treat - Prevent |  | High | Medium | Medium | No
RPE | F9 | 4 | screw driver | Environmental | Costs | Treat - Corrective |  | Medium | Medium | Medium | No
RPE | F9 | 5 | The sea gets deeper the further you go into it | Social | Schedule | Treat - Corrective |  | Medium | Medium | Medium | No
RPE | F9 | 6 | Memento mori and amor fati | Legal | Schedule | Treat - Prevent |  | High | Medium | Medium | No
RIG | Columbia | 1 | wood | Legal | Schedule | Treat - Corrective |  | Very Low | Low | Low | No
RIG | Columbia | 2 | Green lumber fallacy | Legal | Schedule | [5 empty] | Yes
RIG | Columbia | 3 | screw driver
RIG | Columbia | 4 | Don't you know an apparition is just a cheap date. What have you been drinking these days
RIG | Columbia | 5 | The mind is not a vessel to be filled but a fire to be lighted
RIG | Columbia | 6 | Memento mori and amor fati

## Q1_20_21 Count
BRD Risk Category | Low | Medium | High | Total
Economic | 5 | 6 | 0 | 11
Technological | 1 | 2 | 1 | 4
Political | 3 | 2 | 0 | 5
Legal | 1 | 3 | 0 | 4
Social | 2 | 1 | 0 | 3
Environmental | 0 | 2 | 0 | 2
BRD Primary Risk to | Low | Medium | High | Total
Costs | 3 | 6 | 0 | 9
Schedule | 3 | 6 | 0 | 9
Benefits | 6 | 4 | 1 | 11
BRD Internal Control | Low | Medium | High | Total
Treat - Prevent | 5 | 13 | 1 | 19
Treat - Directive | 1 | 0 | 0 | 1
Treat - Corrective | 3 | 3 | 0 | 6
Tolerate | 3 | 0 | 0 | 3
BRD Residual Impact | Low | Medium | High | Total
High | 1 | 5 | 1 | 7
Medium | 3 | 11 | 0 | 14
Low | 6 | 0 | 0 | 6
Very High | 1 | 0 | 0 | 1
Very Low | 1 | 0 | 0 | 1
BRD Residual Likelihood | Low | Medium | High | Total
Medium | 1 | 16 | 0 | 17
Low | 10 | 0 | 0 | 10
High | 1 | 0 | 1 | 2
Severity Score Risk Category | Low | Medium | High | Total
Medium | 0 | 16 | 0 | 16
Low | 12 | 0 | 0 | 12
High | 0 | 0 | 1 | 1
BRD Has this Risk turned into an Issue? | Low | Medium | High | Total
No | 7 | 15 | 0 | 22
None | 5 | 1 | 1 | 7

## Q4_19_20 all data
DfT Group | Project Name | Risk Number | Brief Risk Description | BRD Risk Category | BRD Primary Risk to | BRD Internal Control | BRD Mitigation - Actions taken (brief description) | BRD Residual Impact | BRD Residual Likelihood | Severity Score Risk Category | BRD Has this Risk turned into an Issue?

## Q4_19_20 Count
BRD Risk Category | Low | Medium | High | Total
Economic | 2 | 0 | 0 | 2
Political | 1 | 0 | 0 | 1
Social | 1 | 2 | 0 | 3
Technological | 1 | 3 | 1 | 5
Environmental | 0 | 1 | 0 | 1
BRD Primary Risk to | Low | Medium | High | Total
Costs | 1 | 2 | 0 | 3
Schedule | 4 | 2 | 2 | 8
Benefits | 2 | 2 | 1 | 5
BRD Internal Control | Low | Medium | High | Total
Treat - Prevent | 4 | 2 | 1 | 7
Treat - Directive | 0 | 1 | 0 | 1
Treat - Corrective | 3 | 2 | 1 | 6
Tolerate | 0 | 1 | 1 | 2
BRD Residual Impact | Low | Medium | High | Total
Low | 3 | 0 | 0 | 3
Medium | 3 | 5 | 0 | 8
High | 0 | 1 | 2 | 3
Very High | 0 | 0 | 1 | 1
Very Low | 1 | 0 | 0 | 1
BRD Residual Likelihood | Low | Medium | High | Total
Low | 7 | 0 | 0 | 7
Medium | 0 | 5 | 0 | 5
High | 0 | 1 | 2 | 3
Very High | 0 | 0 | 1 | 1
Severity Score Risk Category | Low | Medium | High | Total
Low | 7 | 0 | 0 | 7
Medium | 0 | 6 | 0 | 6
High | 0 | 0 | 3 | 3
BRD Has this Risk turned into an Issue? | Low | Medium | High | Total