## Constructed BICC Data Master
Project/Programme Name | Sea of Tranquility | Apollo 11 | Apollo 13 | Falcon 9 | Columbia
SRO Sign-Off | 2017-04-04 | 2017-04-06 | 2017-04-18 | 2017-04-04 | 2017-04-07
Reporting period (GMPP - Snapshot Date) | Q4 Jan - Mar 2017 | Q4 Jan - Mar 2017 | Q4 Jan - Mar 2017 | Q4 Jan - Mar 2017 | Q4 Jan - Mar 2017
Quarter Joined | 1314 - Q3 |  | 1314 - Q3 | Q3 1415 | 1617 - Q1
GMPP (GMPP - formally joined GMPP) | 1314-Q2 | 1617-Q1 | 1112-Q1 | 1415-Q4 | 1617-Q1
IUK top 40 |  |  |  | Yes
Top 37 |  |  |  | Yes
DfT Business Plan |  |  |  | Yes
GMPP - IPA ID Number | DFT_0020_1314-Q2 | DFT_0025_1617-Q1 | DFT_0005_1112-Q1 | DfT_0022_1415-Q4 | DFT_0029_1617-Q1
DFT ID Number | 2 | 13 | 19 | 20 | 32
Working Contact Name | Abbe Faria | Benedetto | Albert de morcef | Lord Wilmore | Eugenie Danglers
Working Contact Telephone | 07740 537 555 | 020 7944 999 | 020 7944 9999 | 07712 542999 | 792041499
Working Contact Email | abbe.faria@highengland.co.uk | benedetto@dft.gsi.gov.uk | al.demorcerf@dft.gsi.gov.uk | Lord.Wilmore@highengland.co.uk | Eugenie.Danglers@dft.gsi.gov.uk
DfT Group | Roads Devolution & Motoring | Rail Group | Rail Group | Roads Devolution & Motoring | Rail Group
DfT Division | Strategic Roads | Network Services | Major Projects | Strategic Roads | Network Rail
Agency or delivery partner (GMPP - Delivery Organisation primary) | DfT - Highways England | DfT - DfTc | DfT - DfTc | DfT - Highways England
Strategic Alignment/Government Policy (GMPP - Key drivers) | CMC is clearly aligned with the Departments strategic business objectives. It is expected that the scheme will tackle congestion on the roads and improve journey time reliability improve road safety by reducing incident related delays and encourage sustainable local travel by promoting the ethos of the right traffic on the right road | Caderousse programme supports the achievement of key objectives for DfT DCLG and BIS. The Department for Transport's key objectives are: ¦ - Support a transport system that is an engine for economic growth but one that is also greener and safer and improves quality of life in our communities. ¦ - Improve the links that help to move goods and people around. ¦ - Secure the sustainability of the railway and create capacity for improvement of services. | Increase Connectivity and tackle congestion - Mercedes will deliver more trains with more seats and faster journeys to improving connectivity from London and other cities. Support regional economic developments through the creation of – Mercedes creates 730+ new skilled jobs | Following a DfT-led public consultation in 2013 the need for a new Edmond Dante was included in the National Infrastructure Plan in 2014. In addition to addressing the problems caused by congestion and unreliable journeys improvements in road crossing capacity are also required to support economic growth and improve the environment. | If data is shown in a comparable way these are the most overcrowded train services in Great Britain and are forecast to have continuing high levels of growth. ¦ ¦ The proposal addresses historic under-provision of capacity to meet current demand as well as forecast demand in CP5. This is a key concern for Danglers
Project Scope | The identity Dantès assumes when he emerges from prison and inherits his vast fortune. As a result, the Count of Monte Cristo is usually associated with a coldness and bitterness that comes from an existence based solely on vengeance. | A lazy, drunk, and greedy man. Caderousse is present when the plot to frame Dantès is hatched, but he does not take an active part in the crime. Unlike Danglars and Mondego, Caderousse never finds his fortune, instead making his living through petty crime and the occasional murder. | Dantès’s beautiful and good fiancée. Though Mercédès marries another man, Fernand Mondego, while Dantès is in prison, she never stops loving Dantès. Mercédès is one of the few whom Dantès both punishes (for her disloyalty) and rewards (for her enduring love and underlying goodness). | The protagonist of the novel. Dantès is an intelligent, honest, and loving man who turns bitter and vengeful after he is framed for a crime he does not commit. When Dantès finds himself free and enormously wealthy, he takes it upon himself to act as the agent of Providence, rewarding those who have helped him in his plight and punishing those responsible for his years of agony. | A greedy, envious cohort of Mondego. Danglars hatches the plot to frame Dantès for treason. Like Mondego, he becomes wealthy and powerful, but loses everything when Monte Cristo takes his revenge. Danglars’s obsession with the accumulation of wealth makes him an easy target for Monte Cristo, who has seemingly limitless wealth on hand to exact his revenge.
Brief project description (GMPP - brief descripton) | revenge | Greedy | Goodness | Protagonist | Rat
Delivery Structure | Programme | Programme | Programme | Project | Programme
Description if 'Other'
Change Delivery Methodology | Hybrid | Waterfall | Waterfall | Waterfall | Waterfall
Primary Category | Infrastructure | Infrastructure | Infrastructure | Infrastructure | Procurement
If other Primary Category please describe
Secondary Category |  |  | Procurement |  | Infrastructure
If other Secondary Category please describe
Tertiary Category |  |  |  |  | Other
If other Tertiary Category please describe |  |  |  |  | Rolling Stock
Has Project Scope Changed? | No | No | No | No | No
Scope Change Commentary (if applicable)
List Strategic Outcomes (GMPP - Intended Outcome 1) | Don't you know an apparition is just a cheap date. What have you been drinking these days | The mind is not a vessel to be filled but a fire to be lighted | screw | The mind is not a vessel to be filled but a fire to be lighted | Don't you know an apparition is just a cheap date. What have you been drinking these days | nail
IO1 - Monetised? | Monetised Benefit | Monetised | Monetised Benefit | Monetised Benefit | Non-monetised
List Strategic Outcomes (GMPP - Intended Outcome 2) | The sea gets deeper the further you go into it | The sea gets deeper the further you go into it | plastic | nail | nail | Don't you know an apparition is just a cheap date. What have you been drinking these days
IO2 - Monetised? | Non-Monetised Benefit | Monetised | Monetised Benefit | Monetised Benefit | Monetised
List Strategic Outcomes (GMPP - Intended Outcome 3) | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy | plastic | plastic | screw | The mind is not a vessel to be filled but a fire to be lighted
IO3 - Monetised? | Non-Monetised Benefit | Monetised | Monetised Benefit | Non-Monetised Benefit | Non-monetised
List Strategic Outcomes (GMPP - Intended Outcome 4) | screw driver | wood | Memento mori and amor fati | plastic | Memento mori and amor fati | nail
IO4 - Monetised? | Monetised Benefit | Monetised | Monetised Benefit | Monetised Benefit | Non-monetised
List Strategic Outcomes (GMPP - Intended Outcome 5) | Memento mori and amor fati | screw | plastic | Memento mori and amor fati | The sea gets deeper the further you go into it | The sea gets deeper the further you go into it
IO5 - Monetised? | Non-Monetised Benefit | non-montised benefit | Monetised Benefit | Non-Monetised Benefit
List Strategic Outcomes (GMPP - Intended Outcome 6) | nail | plastic | screw | Green lumber fallacy | What you see if all there is | What you see if all there is
IO6 - Monetised? |  | non-montised benefit | Monetised Benefit
List Strategic Outcomes (GMPP - Intended Outcome 7) | Memento mori and amor fati | nail | The sea gets deeper the further you go into it | plastic | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy
IO7 - Monetised? |  |  | Monetised Benefit
List Strategic Outcomes (GMPP - Intended Outcome 8) | The sea gets deeper the further you go into it | Memento mori and amor fati | screw driver | screw driver | screw | plastic
IO8 - Monetised? |  |  | Monetised Benefit
List Strategic Outcomes (GMPP - Intended Outcome 9)
IO9 - Monetised?
Intended Outcome 10
IO10 - Monetised?
Single Departmental Plan 1 | Boosting Economic Growth and Opportunity | Boosting Economic Growth and Opportunity | Boosting Economic Growth and Opportunity | Boosting Economic Growth and Opportunity | Boosting Economic Growth and Opportunity
Single Departmental Plan 2 | Improving Journeys | Improving Journeys | Building a One Nation Britain | A Safe Secure and Sustainable transport system | Improving Journeys
Single Departmental Plan 3 | A Safe Secure and Sustainable transport system | A Safe Secure and Sustainable transport system | Improving Journeys | Improving Journeys | A Safe Secure and Sustainable transport system
Single Departmental Plan 4 |  |  |  | Building a One Nation Britain
Risk Level (RPA) | Banana | Apples | Pears | Banana | Pears
Risk Level (RPA) Date | 2015-12-01 | 2016-01-06 | 2016-10-01 | 2016-06-06 | 2016-04-22
Departmental DCA | Amber/Green | Amber | Amber/Red | Red | Amber/Green
Departmental DCA Narrative | Stoicism is a school of Hellenistic philosophy founded by Zeno of Citium in Athens in the early 3rd century BC. It is a philosophy of personal ethics informed by its system of logic and its views on the natural world. According to its teachings, as social beings, the path to eudaimonia (happiness, or blessedness) is found in accepting the moment as it presents itself, by not allowing oneself to be controlled by the desire for pleasure or fear of pain, by using one's mind to understand the world and to do one's part in nature's plan, and by working together and treating others fairly and justly. | Richard David James (born 18 August 1971), best known by the stage name Aphex Twin, is a British musician.[1] He is best known for his idiosyncratic work in electronic styles such as techno and ambient music in the 1990s, and has also been associated with the electronic subgenre known as intelligent dance music.[2][3] In 2001, Guardian journalist Paul Lester called James "the most inventive and influential figure in contemporary electronic music".[4] Raised in Cornwall, James began performing as a rave DJ at local clubs and free parties in the late 1980s.[5] In 1991 his debut EP Analogue Bubblebath was released on Mighty Force, a local independent label, winning him acclaim and a cult following.[6][7] James co-founded the independent label Rephlex Records the same year. He attracted wider praise for his 1992 debut album Selected Ambient Works 85–92, released by Belgian label Apollo. He signed to the UK label Warp in 1993, and his music became increasingly well known with the charting albums Selected Ambient Works Volume II (1994) and ...I Care Because You Do (1995), and singles "On" (1993), "Come to Daddy" (1997), and "Windowlicker" (1999). The latter two singles, accompanied by music videos directed by Chris Cunningham, brought James attention in the US market. | Bitcoin is a cryptocurrency invented in 2008 by an unknown person or group of people using the name Satoshi Nakamoto[15] and started in 2009[16] when its implementation was released as open-source software.[7]:ch. 1 It is a decentralized digital currency without a central bank or single administrator that can be sent from user to user on the peer-to-peer bitcoin network without the need for intermediaries.[8] Transactions are verified by network nodes through cryptography and recorded in a public distributed ledger called a blockchain. Bitcoins are created as a reward for a process known as mining. They can be exchanged for other currencies, products, and services.[17] Research produced by University of Cambridge estimates that in 2017, there were 2.9 to 5.8 million unique users using a cryptocurrency wallet, most of them using bitcoin.[18] | The Bretton Woods system of monetary management established the rules for commercial and financial relations among the United States, Canada, Western European countries, Australia, and Japan after the 1944 Bretton Woods Agreement. The Bretton Woods system was the first example of a fully negotiated monetary order intended to govern monetary relations among independent states. The chief features of the Bretton Woods system were an obligation for each country to adopt a monetary policy that maintained its external exchange rates within 1 percent by tying its currency to gold and the ability of the IMF to bridge temporary imbalances of payments. Also, there was a need to address the lack of cooperation among other countries and to prevent competitive devaluation of the currencies as well. | Cricket is a bat-and-ball game played between two teams of eleven players on a field at the centre of which is a 22-yard (20-metre) pitch with a wicket at each end, each comprising two bails balanced on three stumps. The batting side scores runs by striking the ball bowled at the wicket with the bat (and running between the wickets), while the bowling and fielding side tries to prevent this (by getting the ball to either wicket) and dismiss each batter (so they are "out"). Means of dismissal include being bowled, when the ball hits the stumps and dislodges the bails, and by the fielding side catching the ball after it is hit by the bat, but before it hits the ground. When ten batters have been dismissed, the innings ends and the teams swap roles. The game is adjudicated by two umpires, aided by a third umpire and match referee in international matches. They communicate with two off-field scorers who record the match's statistical information.
SRO Full Name | Elon Musk | Elon Musk | Jeff Bezos | John Lennon | Paul Mccarthney
SRO Email | Elon@highengland.co.uk | Elon@highengland.co.uk | jeff@dft.gsi.gov.uk | john.l@highwaysengland.co.uk | paul.Mccartney@dft.gsi.gov.uk
SRO Phone No. | 07795 120989 | 020 7999 4959 | 020 7944 6999 | 01306 999999 | 020 7944 8988
Percentage of time spent on SRO Role | 0.3 | 0.15 | 0.3 | 0.25 | 0.1
SRO Tenure Start Date | 2014-08-19 | 2016-01-01 | 2015-12-07 | 2014-10-09 | 2016-01-01
SRO Tenure End Date | 2021-09-30 | 2018-01-01 | 2019-12-31 | 2025-12-31 | 2018-01-01
SRO MPLA Status | Cohort 14 | Not Eligible - Master Builder | Cohort 13 | Cohort 14 | Masterbuilder
SRO MPLA - If 'other' please describe | MPLA completed and passed |  |  | Completed and passed MPLA
SRO PLP Status
SRO PLP - If 'other' please describe
Date If Current SRO Letter Issued | 2015-03-26 | 2017-01-03 | 2016-06-24 | 2014-10-09 | 2017-01-03
Has the SRO changed? |  | No | No | No | Yes
If new SRO reason for change
PD Full Name | Graham Greene | Vladimir Nabokov | Homer | P G Wodehouse | Tom Wolfe
PD Email | Graham.Green@highwaysengland.co.uk | vladimir@dft.gsi.gov.uk | homer@dft.gsi.gov.uk | wodehouse@uk.pwc.com | tom.wolfe@dft.gsi.gov.uk
PD Phone No. | 07388 123456 | 020 7944 1234 | 020 7944 9876 | 07711 771 246 | 020 7987 4161
Secondary PDs please name?
PD MPLA Status | Eligible - awaiting cohort | Cohort 7 | Cohort 15 | Not Eligible - Contractor | Cohort 5
PD MPLA - If 'other' please describe
PD PLP Status | Eligible - awaiting cohort |  |  | Not Eligible - Contractor
PD PLP - If 'other' please describe
Has PD changed? |  | No
If new PD reason for change
New PD - If 'other' please specify
Percentage of time spent on PD Role | 1 | 0.2 | 1 | 1 | 0.3
PD Tenure Start Date | 2017-01-30 | 2016-03-01 | 2014-04-01 | 2014-03-01 | 2015-01-01
PD Tenure End Date | 2021-09-30 | 2024-03-31 | 2020-02-06 | 2017-12-31 | 2019-12-31
Date if PD letter issued
Project stage | Execute (Delivery) | Execute (Delivery) | Execute | Definition phase | Execute
Project stage if Other
Approval MM1 | Standard B | Standard B | Standard B | Standard B | Standard B
Approval MM1 Original Baseline | 2013-10-24 | 2012-07-01 | 2006-11-01 | 2016-05-30
Approval MM1 Latest Approved Baseline |  |  |  | 2016-01-18
Approval MM1 Forecast / Actual | 2013-10-24 | 2012-07-01 | 2006-11-01 | 2016-01-18
Approval MM1 Milestone Type | Project | Project | Project | Project | Project
Approval MM1 Notes | The sea gets deeper the further you go into it | Green lumber fallacy | Green lumber fallacy | What you see if all there is | Memento mori and amor fati
Approval MM2 | Team Liftoff | Space Roving | Gemini Armstrong | Team Liftoff | Mercury Liftoff
Approval MM2 Original Baseline | 2013-09-17 | 2012-07-01 | 2006-08-31 | 2016-06-30 | 2012-06-27
Approval MM2 Latest Approved Baseline |  |  |  | 2016-05-30
Approval MM2 Forecast / Actual | 2013-11-13 | 2012-07-01 | 2006-08-31 | 2016-01-18 | 2012-06-27
Approval MM2 Milestone Type | Approval - HMT SOBC | Approval - HMT SOBC | Approval - HMT SOBC | Approval - HMT SOBC | Approval - HMT SOBC
Approval MM2 Notes | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy | The sea gets deeper the further you go into it | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days
Approval MM3 | Standard C | Standard C | Standard C | Standard C | Standard C
Approval MM3 Original Baseline | 2013-09-17 | 2015-02-01 | 2006-08-31 | 2016-09-26 | 2013-07-04
Approval MM3 Latest Approved Baseline |  |  |  | 2016-10-24
Approval MM3 Forecast / Actual | 2013-09-20 | 2015-02-01 | 2006-08-31 | 2018-06-30 | 2013-07-04
Approval MM3 Milestone Type | Project | Project | Project | Project | Project
Approval MM3 Notes | What you see if all there is | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | What you see if all there is | The sea gets deeper the further you go into it
Approval MM4 | Sputnik Radiation | Craters Hypatia | Oxygen Module | Sputnik Radiation | Craters Module
Approval MM4 Original Baseline | 2013-09-17 |  | 2007-02-28 | 2016-12-19
Approval MM4 Latest Approved Baseline |  |  |  | 2017-03-30
Approval MM4 Forecast / Actual | 2013-09-20 | 2017-08-01 | 2007-02-28 | 2018-07-31
Approval MM4 Milestone Type | Sputnik Radiation | Craters Hypatia | Oxygen Module | Sputnik Radiation | Craters Module
Approval MM4 Notes | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | The mind is not a vessel to be filled but a fire to be lighted | Don't you know an apparition is just a cheap date. What have you been drinking these days | The sea gets deeper the further you go into it
Approval MM5 | Moon Cosmonauts | Tranquility Aldridge | Mercury Shuttle | Moon Cosmonauts | Spaceship Aldridge
Approval MM5 Original Baseline | 2016-02-16 |  |  | 2019-09-30
Approval MM5 Latest Approved Baseline
Approval MM5 Forecast / Actual | 2016-05-11 | 2018-12-01 |  | 2019-09-30
Approval MM5 Milestone Type | Project | Project | Project | Project | Project
Approval MM5 Notes | The mind is not a vessel to be filled but a fire to be lighted | What you see if all there is | What you see if all there is | The mind is not a vessel to be filled but a fire to be lighted | The sea gets deeper the further you go into it
Approval MM6 | Spaceship Checklist | Spaceship Cosmonauts | Earth Aldridge | Spaceship Checklist | Man Landing
Approval MM6 Original Baseline | 2015-03-31 |  |  | 2017-12-31 | 2013-09-25
Approval MM6 Latest Approved Baseline
Approval MM6 Forecast / Actual | 2015-03-31 |  |  | 2017-12-31 | 2013-09-25
Approval MM6 Milestone Type | Procurement | Procurement | Procurement | Procurement | Procurement
Approval MM6 Notes | The sea gets deeper the further you go into it | The sea gets deeper the further you go into it | Memento mori and amor fati | The sea gets deeper the further you go into it | The mind is not a vessel to be filled but a fire to be lighted
Approval MM7 | Gravity Roving | Mercury Shuttle | Craters Magnetic | Gravity Roving | Soyuz Landing
Approval MM7 Original Baseline |  |  | 2007-06-01 | 2017-12-31 | 2013-10-28
Approval MM7 Latest Approved Baseline
Approval MM7 Forecast / Actual |  |  | 2007-06-01 | 2017-12-31 | 2013-10-28
Approval MM7 Milestone Type | Procurement | Procurement | Procurement | Procurement | Procurement
Approval MM7 Notes | Memento mori and amor fati | What you see if all there is | The sea gets deeper the further you go into it | What you see if all there is | What you see if all there is
Approval MM8 | Oxygen Armstrong | Craters Armstrong | Tranquility Shuttle | Oxygen Armstrong | Apollo Cosmonauts
Approval MM8 Original Baseline |  |  | 2009-11-01 | 2018-12-31 | 2014-04-01
Approval MM8 Latest Approved Baseline
Approval MM8 Forecast / Actual |  |  | 2009-11-01 | 2018-12-31 | 2014-04-01
Approval MM8 Milestone Type | Procurement | Procurement | Procurement | Procurement | Procurement
Approval MM8 Notes | Memento mori and amor fati | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days | The sea gets deeper the further you go into it | The sea gets deeper the further you go into it
Approval MM9 | Earth Lade | Meteorite Landing | Astronauts Cosmonauts | Earth Lade | Soyuz Collins
Approval MM9 Original Baseline |  |  | 2011-10-01 | 2019-03-31 | 2014-04-01
Approval MM9 Latest Approved Baseline
Approval MM9 Forecast / Actual |  |  | 2011-10-01 | 2019-03-31 | 2014-04-01
Approval MM9 Milestone Type | Procurement | Procurement | Procurement | Procurement | Procurement
Approval MM9 Notes | The mind is not a vessel to be filled but a fire to be lighted | Memento mori and amor fati | The sea gets deeper the further you go into it | Memento mori and amor fati | Memento mori and amor fati
Approval MM10 | Standard D | Standard D | Standard D | Standard D | Standard D
Approval MM10 Original Baseline | 2016-03-15 |  | 2012-06-26 | 2021-01-01 | 2014-06-30
Approval MM10 Latest Approved Baseline | 2016-04-25
Approval MM10 Forecast / Actual | 2016-05-23 |  | 2012-06-26 | 2020-09-30 | 2014-08-04
Approval MM10 Milestone Type | Project | Project | Project | Project | Project
Approval MM10 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | The mind is not a vessel to be filled but a fire to be lighted | The sea gets deeper the further you go into it | What you see if all there is | The sea gets deeper the further you go into it
Approval MM11 | Gemini Cosmonauts | Challenger Eleven | Apollo Lade | Gemini Cosmonauts | Serenity Cosmonauts
Approval MM11 Original Baseline | 2016-04-15 |  | 2012-07-18 | 2020-09-30 | 2014-06-30
Approval MM11 Latest Approved Baseline | 2016-06-24 |  |  |  | 2014-07-28
Approval MM11 Forecast / Actual | 2016-06-30 |  | 2011-11-28 | 2020-09-30 | 2014-08-01
Approval MM11 Milestone Type | Gemini Cosmonauts | Challenger Eleven | Apollo Lade | Gemini Cosmonauts | Serenity Cosmonauts
Approval MM11 Notes | Green lumber fallacy | Green lumber fallacy | The mind is not a vessel to be filled but a fire to be lighted | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy
Approval MM12 | Mercury Aldridge |  | Serenity Aldridge | Gemini Landing | Gravity Cosmic
Approval MM12 Original Baseline | 2016-05-13
Approval MM12 Latest Approved Baseline
Approval MM12 Forecast / Actual | 2016-05-11
Approval MM12 Milestone Type | Project
Approval MM12 Notes | Memento mori and amor fati | Green lumber fallacy | Memento mori and amor fati | Memento mori and amor fati | The sea gets deeper the further you go into it
Approval MM13 | Spaceship Walk |  | Serenity Aldridge | Gemini Landing | Gravity Cosmic
Approval MM13 Original Baseline
Approval MM13 Latest Approved Baseline
Approval MM13 Forecast - Actual
Approval MM13 Type
Approval MM13 Notes | Green lumber fallacy | Don't you know an apparition is just a cheap date. What have you been drinking these days | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days | The mind is not a vessel to be filled but a fire to be lighted
Approval MM14 | Spaceship Walk |  | Serenity Aldridge | Gemini Landing | Gravity Cosmic
Approval MM14 Original Baseline
Approval MM14 Latest Approved Baseline
Approval MM14 Forecast - Actual
Approval MM14 Type
Approval MM14 Notes | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | Memento mori and amor fati | Green lumber fallacy | Green lumber fallacy
Approval MM15 | Spaceship Walk |  | Serenity Aldridge | Gemini Landing | Gravity Cosmic
Approval MM15 Original Baseline
Approval MM15 Latest Approved Baseline
Approval MM15 Forecast - Actual
Approval MM15 Type
Approval MM15 Notes | Memento mori and amor fati | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy
Approval MM16 | Spaceship Walk |  | Serenity Aldridge | Gemini Landing | Gravity Cosmic
Approval MM16 Original Baseline
Approval MM16 Latest Approved Baseline
Approval MM16 Forecast - Actual
Approval MM16 Type
Project MM16 Notes | Memento mori and amor fati | Memento mori and amor fati | Memento mori and amor fati | The mind is not a vessel to be filled but a fire to be lighted | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM18 | Standard A | Standard A | Standard A | Standard A | Standard A
Project MM18 Original Baseline | 2012-09-01 | 2011-11-30 | 2005-06-01 | 2014-05-30 | 2012-07-16
Project MM18 Latest Approved Baseline
Project MM18 Forecast - Actual | 2012-09-01 | 2011-11-30 | 2005-06-01 | 2014-05-30 | 2012-07-16
Project MM18 Type | Project Start Date | Project Start Date | Project Start Date | Project Start Date | Project Start Date
Project MM18 Notes | The mind is not a vessel to be filled but a fire to be lighted | What you see if all there is | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy | Memento mori and amor fati
Project MM19 | Standard E | Standard E | Standard E | Standard E | Standard E
Project MM19 Original Baseline | 2016-12-31 | 2012-10-31 | 2012-08-23 | 2021-03-31 | 2015-12-31
Project MM19 Latest Approved Baseline |  |  |  | 2021-12-31 | 2016-04-01
Project MM19 Forecast - Actual | 2016-10-10 | 2012-10-31 | 2012-08-23 | 2021-01-15 | 2016-04-01
Project MM19 Type | Project | Project | Project | Project | Project
Project MM19 Notes | The mind is not a vessel to be filled but a fire to be lighted | The sea gets deeper the further you go into it | Green lumber fallacy | Green lumber fallacy | The mind is not a vessel to be filled but a fire to be lighted
Project MM20 | Standard F | Gravity Magma | Standard F | Standard F | Standard F
Project MM20 Original Baseline | 2020-12-31 | 2016-03-01 | 2017-06-25 | 2025-11-30 | 2017-12-31
Project MM20 Latest Approved Baseline |  |  |  |  | 2018-01-31
Project MM20 Forecast - Actual | 2020-12-31 | 2015-10-01 | 2017-10-16 | 2026-12-31 | 2018-01-31
Project MM20 Type | Project | Project | Project | Project | Project
Project MM20 Notes | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | Memento mori and amor fati
Project MM21 | Standard H | Craters Cosmonauts | Standard H | Standard H | Standard H
Project MM21 Original Baseline | 2021-09-30 | 2016-03-01 | 2020-02-06 | 2026-12-31 | 2019-12-31
Project MM21 Latest Approved Baseline |  | 2016-12-31 |  |  | 2018-12-31
Project MM21 Forecast - Actual | 2021-09-30 | 2016-12-31 | 2020-02-06 | 2026-12-31 | 2019-12-31
Project MM21 Type | Standard H | Project | Standard H | Standard H | Standard H
Project MM21 Notes | What you see if all there is | Don't you know an apparition is just a cheap date. What have you been drinking these days | What you see if all there is | Memento mori and amor fati | What you see if all there is
Project MM22 | Lunar Radiation | Challenger Hypatia | Tranquility Cosmic | Lunar Radiation | Space Sea
Project MM22 Original Baseline | 2023-03-31 | 2016-12-31 | 2049-03-31 | 2084-12-31 | 2047-07-28
Project MM22 Latest Approved Baseline
Project MM22 Forecast - Actual | 2023-03-31 | 2016-12-31 | 2049-03-31 | 2084-12-31 | 2047-07-28
Project MM22 Type | Lunar Radiation | Project | Tranquility Cosmic | Lunar Radiation | Space Sea
Project MM22 Notes | The sea gets deeper the further you go into it | The sea gets deeper the further you go into it | Green lumber fallacy | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy
Project MM23 | Man Checklist | Tranquility Hypatia | Sputnik Magnetic | Astronauts Walk | Inverted Checklist
Project MM23 Original Baseline | 2016-02-13 | 2017-07-31 | 2015-09-01 | 2015-01-07 | 2014-09-01
Project MM23 Latest Approved Baseline |  |  | 2015-10-15
Project MM23 Forecast - Actual | 2016-12-13 | 2017-07-31 | 2015-10-15 | 2016-01-26 | 2014-09-01
Project MM23 Type | Project | Project | Project | project | Procurement
Project MM23 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | What you see if all there is | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM24 | Oxygen Landing | Astronauts Sea | Craters Kestrel | Columbia Hypatia | Astronauts Module
Project MM24 Original Baseline | 2017-01-23 | 2017-03-01 | 2015-09-30 | 2015-06-30 | 2017-07-31
Project MM24 Latest Approved Baseline |  | 2017-11-01 | 2016-09-30
Project MM24 Forecast - Actual | 2017-01-23 | 2017-11-01 | 2016-07-31 | 2017-03-02 | 2017-07-31
Project MM24 Type | Project | Project | Project | Project | Other
Project MM24 Notes | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM25 | Mercury Checklist | Meteorite Module | Oxygen Magma | Moon Cosmic | Moon Shuttle
Project MM25 Original Baseline | 2018-03-26 | 2018-09-01 | 2016-05-01 |  | 2017-12-31
Project MM25 Latest Approved Baseline
Project MM25 Forecast - Actual | 2018-03-26 | 2018-09-01 | 2016-03-01 |  | 2017-12-31
Project MM25 Type | Project | Project | Project |  | Other
Project MM25 Notes | Green lumber fallacy | Memento mori and amor fati | Memento mori and amor fati | What you see if all there is | Memento mori and amor fati
Project MM26 | Spaceship Cosmic | Lunar Magma | Oxygen Armstrong | Moon Cosmic | Serenity Command
Project MM26 Original Baseline | 2018-09-10 | 2022-10-01 | 2016-12-01 |  | 2018-05-31
Project MM26 Latest Approved Baseline
Project MM26 Forecast - Actual | 2018-09-10 | 2022-10-01 | 2016-12-01 |  | 2018-12-01
Project MM26 Type | Project | Project | Project |  | Other
Project MM26 Notes | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | The mind is not a vessel to be filled but a fire to be lighted
Project MM27 | Orbital Ocean | Lunar Liftoff | Inverted Hypatia | Moon Cosmic | Tranquility Aldridge
Project MM27 Original Baseline | 2018-02-22 | 2024-03-31 | 2016-12-01 |  | 2017-08-28
Project MM27 Latest Approved Baseline
Project MM27 Forecast - Actual | 2018-05-29 | 2024-03-31 | 2016-12-01 |  | 2017-08-28
Project MM27 Type | Project | Project | Project |  | Other
Project MM27 Notes | The sea gets deeper the further you go into it | The mind is not a vessel to be filled but a fire to be lighted | What you see if all there is | The mind is not a vessel to be filled but a fire to be lighted | What you see if all there is
Project MM28 | Tranquility Kestrel | Standard H | Man Kestrel | Moon Cosmic | Oxygen Sea
Project MM28 Original Baseline | 2019-12-23 | 2024-03-31 | 2017-06-25
Project MM28 Latest Approved Baseline
Project MM28 Forecast - Actual | 2019-12-23 | 2024-03-31 | 2017-10-16
Project MM28 Type | Project | Standard H | Project
Project MM28 Notes | What you see if all there is | Memento mori and amor fati | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy | The sea gets deeper the further you go into it
Project MM29 | Team Hypatia | Soyuz Roving | Man Kestrel | Moon Cosmic | Oxygen Sea
Project MM29 Original Baseline |  | 2079-12-31 | 2018-08-23
Project MM29 Latest Approved Baseline
Project MM29 Forecast - Actual |  | 2079-12-31 | 2018-08-23
Project MM29 Type |  | Soyuz Roving | Project
Project MM29 Notes | The sea gets deeper the further you go into it | Green lumber fallacy | Green lumber fallacy | Green lumber fallacy | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM30 | Team Hypatia |  | Team Walk | Moon Cosmic | Oxygen Sea
Project MM30 Original Baseline |  |  | 2020-02-06
Project MM30 Latest Approved Baseline
Project MM30 Forecast - Actual |  |  | 2020-02-06
Project MM30 Type |  |  | Project
Project MM30 Notes | What you see if all there is | The sea gets deeper the further you go into it | The sea gets deeper the further you go into it | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM31 | Team Hypatia |  | Gravity Module | Moon Cosmic | Oxygen Sea
Project MM31 Original Baseline |  |  | 2015-02-28
Project MM31 Latest Approved Baseline
Project MM31 Forecast - Actual |  |  | 2015-02-28
Project MM31 Type |  |  | Project
Project MM31 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | What you see if all there is | The mind is not a vessel to be filled but a fire to be lighted | The mind is not a vessel to be filled but a fire to be lighted | The sea gets deeper the further you go into it
Project MM32 | Team Hypatia | Orbital Landing | Sputnik Walk | Moon Cosmic | Oxygen Sea
Project MM32 Original Baseline |  |  | 2015-03-05
Project MM32 Latest Approved Baseline
Project MM32 Forecast - Actual |  |  | 2015-03-05
Project MM32 Type |  |  | Project
Project MM32 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | The mind is not a vessel to be filled but a fire to be lighted | The mind is not a vessel to be filled but a fire to be lighted | The mind is not a vessel to be filled but a fire to be lighted | The sea gets deeper the further you go into it
Milestone Commentary | The 2015 Ashes (named Investec Ashes Series for sponsorship reasons) was a series of Test cricket matches played between England and Australia for The Ashes. The venues were Sophia Gardens (Cardiff), Lord's (London), Edgbaston (Birmingham), Trent Bridge (Nottingham), and The Oval (London).[2] Australia were the defending holders of the Ashes going into the series, having won in 2013–14. England won the series 3–2, regaining the Ashes after taking an unassailable lead with victory in the fourth Test. | The 2017–18 Ashes series (named Magellan Ashes Series for sponsorship reasons)[3] was a series of Test cricket matches contested between England and Australia for The Ashes. The series was played at five venues across Australia between 23 November 2017 and 8 January 2018. England were the defending holders of the Ashes going into the series, having won in 2015. Australia won the series 4–0, regaining The Ashes after taking an unassailable lead with an innings victory in the third Test. | The 2019 Ashes series (officially the Specsavers Ashes Series for sponsorship reasons[1]) was a series of Test cricket matches played between England and Australia for The Ashes in August and September 2019. The venues were Edgbaston, Lord's, Headingley, Old Trafford and The Oval.[2] Australia were the defending holders of the Ashes going into the series, having won in 2017–18. It was the first Test series of the inaugural 2019–21 ICC World Test Championship.[3][4] During the second Test match a concussion substitute was used for the first time in international cricket. Australia retained the Ashes after winning the fourth Test,[5] with England levelling the series 2–2 in the final test, resulting in the first drawn Ashes series since 1972.[6] | The 2010–11 Ashes series (known as the Vodafone Ashes Series for sponsorship reasons) was the 66th series of Test cricket matches played to contest The Ashes. The series was played in Australia as part of the England cricket team's tour of the country during the 2010–11 season. Five Tests were played from 25 November 2010 to 7 January 2011.[1] England won the series 3–1 and retained the Ashes, having won the previous series in 2009 by two Tests to one. As of 2019, it remains the most recent occasion that a visiting team has won an Ashes series. | The 2013 Ashes series was a series of Test cricket matches contested between England and Australia for the Ashes.[2] It formed part of the 2013 Australian tour of England, which also included the 2013 ICC Champions Trophy, five One Day Internationals and two Twenty20 Internationals.[2] The 2013 series was the first of two back-to-back Ashes series. With the intent of breaking the cycle of Ashes series being held directly before Cricket World Cups, the Ashes were brought forward in the schedule by one year, starting with the 2013–14 series in Australia.[3][4]
Project Lifecycle Stage | Execute (Delivery) | Execute (Delivery) | Execute | Definition phase | Execute
Project Stage if Other
Significant Steel Requirement | YES | No | No | yes | Yes
SRO Finance confidence | Green | Amber | Amber | Amber | Amber
IPDC approval point | Full Business Case | Strategic Outline Case | Full Business Case | Strategic Outline Case | Full Business Case
Latest Treasury Approval Point (TAP) or equivalent | Full Business Case | Outline Business Case | Full Business Case | Strategic Outline Case | Full Business Case
Business Case used to source figures (GMPP TAP used to source figures) | Full Business Case | Outline Business Case | Full Business Case | Outline Business Case | Other
Date of TAP used to source figures |  |  |  | 2016-01-18
Name of source in not Business Case (GMPP -If not TAP please specify equivalent document used) |  | Network Rail |  | n/a | C-DEL/non-govt costs - Enhancements reporting
If not TAP please specify date of equivalent document | 2015-03-12 | 2015-02-01 | 2012 - 2014 | 2017-02-14 | 2014-07-28
Version Number Of Document used to Source Figures (GMPP - TAP version Number) | Q4 2015 | v2.0 | 1Q 2012 | 1.6 | Q2 2014
Real or Nominal - Baseline | Nominal | Real | Nominal | Nominal | Real
Real or Nominal - Actual/Forecast | Nominal | Real | Nominal | Nominal | Real
Index Year |  | 2012 |  |  | 2012
Deflator |  | 0.035
Source of Finance | public finance | Public Finance | Private Finance | public finance | public finance
Other Finance type Description |  |  |  | Financing route is to be confirmed. Working assumption is that the construction will be separated into packages with one being partially privately financed and the other publicly financed
NPV for all projects and NPV for programmes if available | 2393 | 2034 | 1985 | 2815
Project cost to closure | 1435.3 | 963.2 | 6310 | 4395 | 678.06
RDEL Total Budget/BL | 0 | 0 | 236.95 | 0 | 132.7
CDEL Total Budget/BL | 1435.3 | 0 | 0 | 199.1 | 0
Non-Gov Total Budget/BL | 0 | 1654.6 | 6276 | 0 | 601.2
Total Budget/BL | 1435.3 | 1654.6 | 6512.95 | 199.1 | 733.9
RDEL Total Forecast | 0 | 0 | 263.44 | 0 | 132.66
CDEL Total Forecast | 1402.9 | 0 | 46.25 | 4395.01 | 0
Non-Gov Total Forecast | 0 | 1378.6 | 6276 | 0 | 612.7
Total Forecast | 1402.9 | 1378.6 | 6585.69 | 4395.01 | 745.36
RDEL Total Variance | 0 | 0 | 26.49 | 0 | -0.04
CDEL Total Variance | -32.4 | 0 | 46.25 | 4195.91 | 0
Non-Gov Total Variance | 0 | -276 | 0 | 0 | 11.5
Total Variance | -32.4 | -276 | 72.74 | 4195.91 | 11.46
RDEL Total Budget/BL SR (20/21) | 0 | 0 | 122.05 | 0 | 132.7
CDEL Total Budget/BL SR (20/21) | 1435.3 | 0 | 0 | 199.1 | 0
Non-Gov Total Budget/BL SR (20/21) | 0 | 774.2 | 576 | 0 | 542.8
Total Budget SR (20/21) | 1435.3 | 774.2 | 698.05 | 199.1 | 675.5
RDEL Total Forecast SR (20/21) | 0 | 0 | 132.19 | 0 | 132.66
CDEL Total Forecast SR (20/21) | 1402.9 | 0 | 46.25 | 432.54 | 0
Non-Gov Total Forecast SR (20/21) | 0 | 735.6 | 576 | 0 | 554.3
Total Forecast SR (20/21) | 1402.9 | 735.6 | 754.44 | 432.54 | 686.96
Project Costs Narrative RDEL | There are no RDEL cost for this project. | Figures in 12/13 prices and includes phase 1 & 2. ¦ ¦ These represent current best estimates and are subject to change as project develops. The forecast reflects the removal of the line electrification. ¦ Grip2 costs were presented to DfT in Dec 2016: AFC were accepted at Programme Board but the budget was not increased. AFC will be considered by Programme board before being formally reflected in cost estimates. ¦ Depots & Stabling as well as Consortium's £45m contribution are not included. ¦ Following recent advice we have included Chiltern's contribution in the budget figures. This change as well as the removal of the line electrification do not fully explain the new figures. There is currently a £246m difference between the total baseline and the total forecast and we are investigating exhaustively with Network Rail the reasons explaining this gap. Similarly we are investigating the different reasons explaining the baseline increase since last report from £1 525.01m to £1 624.60m and the total forecast decrease from £1488.98m to £1 378.60m. | The Project Cost to Closure isn’t calculated up to 2020. ¦ This figure is calculated by adding the £5.7bn total value of to the £480m CP5 works being delivered by Network Rail and an additional £130m to represent the bi-mode variation. ¦ However the final cost of the Bi-mode variation has not been fully agreed yet so this is an estimate. Similarly the £480m for Network Rail costs is their CP5 allocation only. ¦ Finally the £5.7bn for is calculated in the Business case and is the standard quoted value of over the 27 ½ years. ¦ Its not possible to dis aggregate costs for sections within the contract period ¦ ¦ ¦ Non-Gov costs reflect funding provided to Network Rail for works in CP5 (480m equally distributed across CP5). The remaining unprofiled spend of 5.7bn shows the value of the contract this is in terms of the costs of the and fleets over 27.5years via the Set Availability Payments for the fleet. This figure is unchanged from the Business Case (FBC). Over the course of the Programme there have been additional costs as a result of mitigating delays in the provision of infrastructure including contract variations to modify the fleet. These costs are reflect in the RDEL one off costs. ¦ ¦ RDEL one off costs include costs of external advisers costs of bimode variation signed 2016 (transaction charges and assumed funding package over life of fleet - this will be subject to confirmation) and test delay mitigation payments for DfT obligations under the contract. The expected OPEX increase for increased maintenance costs as a result of bi-mode operations is included in FY 2017/18 - 2021/22. (Pre 2015/16 RDEL Budget and Forecast figures calculated using figures from Q4 2014/15 GMPP report.) | The current cost estimates were developed by Highways England to support appraisal of the shortlisted options and selection of the Preferred Route. Highways England's use its own cost database and have also sought specialist advice for tunnelling costs. Estimates have been developed using three-point estimating techniques and Monte Carlo simulation to produce a range of estimated costs (P10 most likely i.e. mode and P90). ¦ ¦ Estimates have been produced using the Division estimating rate libraries for standard highways and structural works. These libraries are audited and updated annually using data from the Division’s Cost Capture database of actual and tendered rates captured from previous works. Specialist input has been sought for the tunnelling and other complex works to supplement this historical data including market enquiries for key items such as tunnel boring machine supply and assembly. ¦ ¦ Base estimates have been produced at Q1 2014 prices (the price base of the Division’s current rate libraries). After incorporation of allowances for risk and uncertainty estimates are converted to outturn prices in nominal terms using the Division’s current forecast profile of inflation for the major projects portfolio. | R-DEL costs reflect costs historically reported in the previous Rolling Stock BICC report which were included in DfT LTF (current and previous versions) and paid via franchise agreement. The costs for rolling stock are contracted (with all new rolling stock in operation in 2018) and therefore not expected to change significantly. The cost figures for Non-Gov costs are in 12/13 prices and reflect the Network Rail enhancement forecasts for the Capacity programme. The projects in scope for these costs include ; Traction Power Supply Upgrade and Reading Ascot to London train lengthening. The baseline reflects a change controls agreed in April 2016 to cover some validated cost escalation on the programme. As a result the change controlled base line increased by £29m (12/13 prices) in Control Period 5 (2014-2019) and by £20m (12/13 prices) to the Control Period 6 (2019-2024) forecast. There is a £12m variance (period 11 Jan 17 forecasts) reported against the change controlled baseline which is currently being reviewed and validated. Costs for the South London HV grid and CP4 rollover schemes including Route 3 Power sign off Package 7 10 Car Suburban Railway ASDO have been removed from the cost table as these do not immediately relate to programme outputs. The combined value of these schemes (all 12/13 prices) is £20.3m (pre 16/17) £0.5m (17/18) £4m (17/18) £9.1m (18/19) £4.1m (19/20) £9.5m (20/21) £9.2m (21/22) and £8.7 post 21/22. All of these are reported in Network Rail's CP5 Enhancement Delivery Plan. The figures do not include funding for Depots & Stabling (AFC is £44m 12/13) or any contributions from other funding sources including any EU funding renewals expenditure third party funding or from other funding sources.
Project Costs Narrative CDEL | The latest range estimate for the scheme is £1.193bn to £1.662bn with a most likely value of £1.435bn. Spending Round SR13 confirmed a budget of £1.5 billion for the scheme. A contribution of £100m has been committed by Local Authorities and the LEP and Heads of terms have been agreed with all parties. ¦ The project started construction in October 2016 and remains on track to meet the public commitment of opening the new route to traffic by December 2020. ¦ The forecast profile is based on the latest approved Highways England estimate of £1.435bn which was developed in April 16. |  | The total costs of £5.7bn are financed via PFI payments over 27.5 years. DfT guarantees use of the trains in the Great Western and East Coast franchises. ¦ ¦ Network Rail funded in CP5 to deliver £480m of enabling works prior to entry into service (classified as C-AME not CDEL which is why it is included in non government costs). ¦ ¦ 46.25 is the Capex element of the depot costs included in the bimode variation signed in 2016. | The cost estimates were developed by Highways England's Commercial Services Division (CS) to support appraisal of the shortlisted options and selection of the Preferred Route. A probabilistic range estimating process was used including three-point estimating techniques and Monte Carlo simulation. A probability distribution has been produced providing estimated outturn costs at P10 Most Likely (mode) and P90 points within the range. ¦ ¦ Estimates have been produced using Highways England's estimating rate libraries for standard highways and structural works. These libraries are audited and updated annually using data from the Division’s Cost Capture database of actual and tendered rates captured from previous works. Specialist input has been sought for the tunnelling and other complex works to supplement this historical data including market enquiries for key items such as tunnel boring machine supply and assembly. ¦ ¦ Base estimates have been produced at Q1 2014 prices (the price base of the Division’s current rate libraries). After incorporation of allowances for risk and uncertainty estimates are converted to outturn prices in nominal terms using the Division’s current forecast profile of inflation for the major projects portfolio. ¦ ¦ ¦ The forecast for the RIS1 period includes the Development Phase costs which are being developed following the appointment of the Technical Partner in May 2016. The baseline for FY16/17 consists of the 16/17 element of the Options Phase budget and £29.7m approved for FY16/17 for Development Phase activity. The forecast for FY16/17 has been reduced because the PRA has been delayed and the Development Phase activities have therefore slowed. The budget shown in RIS1 (2015-2020) is based on the Highways England approved capital baseline (v1.1); against this budget the current forecast shows minimal variance. The total project costs shown have been updated following submission of the OBC in February and are for the recommended route with private finance and associated timing. ¦ A more detailed estimate of costs for the remainder of RIS1 and extending into RIS2 is be presented in the summer before seeking HE DfT and HMT approval in due course to the remainder of the Development Phase funding following the Preferred Route Announcement.
Pre 16-17 RDEL Baseline - One off new costs - investment in change |  | 0 | 62.35 | 0 | 4.98
Pre 16-17 RDEL Baseline - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
Pre 16-17 RDEL Baseline - Recurring old costs |  | 0 | 0 | 0 | 0
Pre 16-17 RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 62.35 | 0 | 4.98
Pre-profile RDEL Forecast one off new costs |  | 0 | 45.98 | 0 | 4.94
Pre 16-17 RDEL Actual - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
Pre 16-17 RDEL Actual - Recurring old costs |  | 0 | 0 | 0 | 0
Pre 16-17 RDEL Actual - Whole Life Cost breakdown | 0 | 0 | 45.98 | 0 | 4.94
2016/2017 RDEL Spend on profile? - One off new costs - investment in change |  |  | No |  | Yes
2016/2017 RDEL Spend on profile? - Recurring new costs - investment in change
2016/2017 RDEL Spend on profile? - recurring old costs
2016/2017 RDEL Spend on profile? - Whole Life Cost breakdown |  |  | No |  | Yes
16-17 RDEL Baseline - One off new costs - investment in change |  | 0 | 2 | 0 | 11.36
16-17 RDEL Baseline - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
16-17 RDEL Baseline - Recurring old costs |  | 0 | 0 | 0 | 0
16-17 RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 2 | 0 | 11.36
16-17 RDEL Forecast - One off new costs - investment in change |  | 0 | 4.09 | 0 | 11.36
16-17 RDEL Forecast - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
16-17 RDEL Forecast - Recurring old costs |  | 0 | 0 | 0 | 0
16-17 RDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 4.09 | 0 | 11.36
17-18 RDEL Baseline - One off new costs - investment in change |  | 0 | 8.9 | 0 | 46.72
17-18 RDEL Baseline - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
17-18 RDEL Baseline - Recurring old costs |  | 0 | 0 | 0 | 0
17-18 RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 8.9 | 0 | 46.72
17-18 RDEL Forecast - One off new costs - investment in change |  | 0 | 9.75 | 0 | 46.72
17-18 RDEL Forecast - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
17-18 RDEL Forecast - Recurring old costs |  | 0 | 0 | 0 | 0
17-18 RDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 9.75 | 0 | 46.72
18-19 RDEL Baseline - One off new costs - investment in change |  | 0 | 24.1 | 0 | 36.22
18-19 RDEL Baseline - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
18-19 RDEL Baseline - Recurring old costs |  | 0 | 0 | 0 | 0
18-19 RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 24.1 | 0 | 36.22
18-19 RDEL Forecast - One off new costs - investment in change |  | 0 | 37.88 | 0 | 36.22
18-19 RDEL Forecast - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
18-19 RDEL Forecast - Recurring old costs |  | 0 | 0 | 0 | 0
18-19 RDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 37.88 | 0 | 36.22
19-20 RDEL Baseline - One off new costs - investment in change |  | 0 | 24.7 | 0 | 33.42
19-20 RDEL Baseline - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
19-20 RDEL Baseline - Recurring old costs |  | 0 | 0 | 0 | 0
19-20 RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 24.7 | 0 | 33.42
19-20 RDEL Forecast - One off new costs - investment in change |  | 0 | 34.49 | 0 | 33.42
19-20 RDEL Forecast - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
19-20 RDEL Forecast - Recurring old costs |  | 0 | 0 | 0 | 0
19-20 RDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 34.49 | 0 | 33.42
20-21 RDEL Baseline - One off new costs - investment in change |  | 0 | 25.3 | 0 | 0
20-21 RDEL Baseline - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
20-21 RDEL Baseline - Recurring old costs |  | 0 | 0 | 0 | 0
20-21 RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 25.3 | 0 | 0
20-21 RDEL Forecast - One off new costs - investment in change |  | 0 | 23.81 | 0 | 0
20-21 RDEL Forecast - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
20-21 RDEL Forecast - Recurring old costs |  | 0 | 0 | 0 | 0
20-21 RDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 23.81 | 0 | 0
21-22 RDEL Baseline - One off new costs - investment in change |  | 0 | 6.4 | 0 | 0
21-22 RDEL Baseline - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
21-22 RDEL Baseline - Recurring old costs |  | 0 | 0 | 0 | 0
21-22 RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 6.4 | 0 | 0
21-22 RDEL Forecast - One off new costs - investment in change |  | 0 | 12.41 |  | 0
21-22 RDEL Forecast - Recurring new costs - investment in change |  | 0 | 0 |  | 0
21-22 RDEL Forecast - Recurring old costs |  | 0 | 0 |  | 0
21-22 RDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 12.41 | 0 | 0
Unprofiled Remainder RDEL Baseline - One off new costs - investment in change (GMPP - Remaining Spend) |  | 0 | 83.2 | 0 | 0
Unprofiled Remainder RDEL Baseline - Recurring new costs - investment in change (GMPP - Remaining Spend) |  | 0 | 0 | 0 | 0
Unprofiled Remainder RDEL Baseline - Recurring old costs (GMPP - Remaining Spend) |  | 0 | 0 | 0 | 0
Unprofiled Remainder RDEL Baseline - Whole Life Cost breakdown (GMPP - Remaining Spend) | 0 | 0 | 83.2 | 0 | 0
Unprofiled Remainder RDEL Forecast - One off new costs - investment in change (GMPP – Remaining Spend) |  | 0 | 95.03 | 0 | 0
Unprofiled Remainder RDEL Forecast - Recurring new costs - investment in change |  | 0 | 0 | 0 | 0
Unprofiled Remainder RDEL Forecast - Recurring old costs (GMPP - Remaining Spend) |  | 0 | 0 | 0 | 0
Unprofiled RDEL Forecast Total | 0 | 0 | 95.03 | 0 | 0
Total RDEL Baseline - One off new costs - investment in change | 0 | 0 | 236.95 | 0 | 132.7
Total RDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
Total RDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
Total RDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 236.95 | 0 | 132.7
Total RDEL Forecast - One off new costs - investment in change | 0 | 0 | 263.44 | 0 | 132.66
Total RDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
Total RDEL Forecast - Recurring old costs | 0 | 0 | 0 | 0 | 0
Total RDEL Forecast Total | 0 | 0 | 263.44 | 0 | 132.66
Annual Steady State for RDEL recurring new costs
Year RDEL spend stops | No Spend | 2022/23 |  | No Spend | 2019/2020
Pre 16-17 CDEL Baseline - One off new costs - investment in change | 68.9 | 0 | 0 | 28.5 | 0
Pre 16-17 CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
Pre 16-17 CDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
Pre 16-17 CDEL Baseline - Whole Life Cost breakdown | 68.9 | 0 | 0 | 28.5 | 0
Pre-profile CDEL Forecast one off new costs | 68.8 | 0 | 0 | 26.01 | 0
Pre 16-17 CDEL Actual - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
Pre 16-17 CDEL Actual - Recurring old costs | 0 | 0 | 0 | 0 | 0
Pre 16-17 CDEL Actual - Whole Life Cost breakdown | 68.8 | 0 | 0 | 26.01 | 0
2016/2017 CDEL Spend on profile? - One off new costs - investment in change | Yes |  | No | Yes
2016/2017 CDEL Spend on profile? - Recurring new costs - investment in change
2016/2017 CDEL Spend on profile? - Recurring old costs
2016/2017 CDEL Spend on profile? - Whole Life Cost breakdown | Yes |  | No | Yes
16-17 CDEL Baseline - One off new costs - investment in change | 123.6 | 0 | 0 | 35.6 | 0
16-17 CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 |  | 0
16-17 CDEL Baseline - Recurring old costs | 0 | 0 | 0 |  | 0
16-17 CDEL Baseline - Whole Life Cost breakdown | 123.6 | 0 | 0 | 35.6 | 0
16-17 CDEL Forecast - One off new costs - investment in change | 142.3 | 0 | 46.25 | 27.77 | 0
16-17 CDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
16-17 CDEL Forecast - Recurring old costs | 0 | 0 | 0 | 0 | 0
16-17 CDEL Forecast - Whole Life Cost breakdown | 142.3 | 0 | 46.25 | 27.8 | 0
17-18 CDEL Baseline - One off new costs - investment in change | 414.9 | 0 | 0 | 45 | 0
17-18 CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
17-18 CDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
17-18 CDEL Baseline - Whole Life Cost breakdown | 414.9 | 0 | 0 | 45 | 0
17-18 CDEL Forecast - One off new costs - investment in change | 371.6 | 0 | 0 | 47.09 | 0
17-18 CDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
17-18 CDEL Forecast - Recurring old costs | 0 | 0 | 0 | 0 | 0
17-18 CDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 0 | 0 | 0
18-19 CDEL Baseline - One off new costs - investment in change | 407.3 | 0 | 0 | 45 | 0
18-19 CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
18-19 CDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
18-19 CDEL Baseline - Whole Life Cost breakdown | 407.3 | 0 | 0 | 45 | 0
18-19 CDEL Forecast - One off new costs - investment in change | 485.8 | 0 | 0 | 45 | 0
18-19 CDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
18-19 CDEL Forecast - Recurring old costs | 0 | 0 | 0 | 0 | 0
18-19 CDEL Forecast - Whole Life Cost breakdown | 485.8 | 0 | 0 | 45 | 0
19-20 CDEL Baseline - One off new costs - investment in change | 401 | 0 | 0 | 45 | 0
19-20 CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
19-20 CDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
19-20 CDEL Baseline - Whole Life Cost breakdown | 401 | 0 | 0 | 45 | 0
19-20 CDEL Forecast - One off new costs - investment in change | 278.3 | 0 | 0 | 45.05 | 0
19-20 CDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
19-20 CDEL Forecast - Recurring old costs | 0 | 0 | 0 | 0 | 0
19-20 CDEL Forecast - Whole Life Cost breakdown | 278.3 | 0 | 0 | 45.05 | 0
20-21 CDEL Baseline - One off new costs - investment in change | 19.6 | 0 | 0 | 0 | 0
20-21 CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
20-21 CDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
20-21 CDEL Baseline - Whole Life Cost breakdown | 19.6 | 0 | 0 | 0 | 0
20-21 CDEL Forecast - One off new costs - investment in change | 56.1 | 0 | 0 | 241.58 | 0
20-21 CDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
20-21 CDEL Forecast - Recurring old costs | 0 | 0 | 0 | 0 | 0
20-21 CDEL Forecast - Whole Life Cost breakdown | 56.1 | 0 | 0 | 241.58 | 0
21-22 CDEL Baseline - One off new costs - investment in change | 0 | 0 | 0 | 0 | 0
21-22 CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
21-22 CDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
21-22 CDEL Baseline - Whole Life Cost breakdown | 0 | 0 | 0 | 0 | 0
21-22 CDEL Forecast - One off new costs - investment in change | 0 | 0 | 0 | 549.31 | 0
21-22 CDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 |  | 0
21-22 CDEL Forecast - Recurring old costs | 0 | 0 | 0 |  | 0
21-22 CDEL Forecast - Whole Life Cost breakdown | 0 | 0 | 0 | 549.31 | 0
Unprofiled Remainder CDEL Baseline - One off new costs - investment in change (GMPP - Remaining Spend) | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder CDEL Baseline - Recurring new costs - investment in change (GMPP - Remaining Spend) | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder CDEL Baseline - Recurring old costs (GMPP - Remaining Spend) | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder CDEL Baseline - Whole Life Cost breakdown (GMPP - Remaining Spend) | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder CDEL Forecast - One off new costs - investment in change (GMPP - Remaining Spend) | 0 | 0 | 0 | 3413.2 | 0
Unprofiled Remainder CDEL Forecast - Recurring new costs - investment in change (GMPP - Remaining Spend) | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder CDEL Forecast - Recurring old costs (GMPP - Remaining Spend) | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder CDEL Forecast - Whole Life Cost breakdown (GMPP - Remaining Spend) | 0 | 0 | 0 | 3413.2 | 0
Total CDEL Baseline - One off new costs - investment in change | 1435.3 | 0 | 0 | 199.1 | 0
Total CDEL Baseline - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
Total CDEL Baseline - Recurring old costs | 0 | 0 | 0 | 0 | 0
Total CDEL Baseline - Whole Life Cost breakdown | 1435.3 | 0 | 0 | 199.1 | 0
Total CDEL Forecast - One off new costs - investment in change | 1402.9 | 0 | 46.25 | 4395.01 | 0
Total CDEL Forecast - Recurring new costs - investment in change | 0 | 0 | 0 | 0 | 0
Total CDEL Forecast - Recurring old costs | 0 | 0 | 0 | 0 | 0
Total CDEL Forecast Total WLC (old) | 1402.9 | 0 | 46.25 | 4395.01 | 0
Annual Steady State for CDEL recurring new costs
Year CDEL spend stops | 2021 |  | 2046/2047 | 2026/2027 | No Spend
Unprofiled Remainder RDEL Baseline - Non-Gov both Revenue and Capital (GMPP - Remaining Spend) |  | 231.3 | 5700 | 0 | 0
Unprofiled Remainder RDEL Forecast - Non-Gov both Revenue and Capital (GMPP - Remaining Spend) |  | 299.4 | 5700 | 0 | 0
Total Baseline - Non-Gov both Revenue and Capital | 0 | 774.2 | 576 | 0 | 542.8
Total Forecast - Non-Gov both Revenue and Capital | 0 | 774.2 | 576 | 0 | 542.8
Pre 16-17 Baseline - Non-Gov both Revenue and Capital |  | 341.7 | 192 | 0 | 68
Pre-profile Forecast Non-Gov |  | 337.8 | 192 | 0 | 68
2016/2017 Non-Gov (£m) Revenue & Capital Spend on profile? |  | Yes | Yes |  | Yes
16-17 Baseline - Non-Gov both Revenue and Capital |  | 69.1 | 96 | 0 | 167.5
16-17 Forecast - Non-Gov both Revenue and Capital |  | 77.7 | 96 | 0 | 158.4
17-18 Baseline - Non-Gov both Revenue and Capital |  | 18.2 | 96 | 0 | 173.7
17-18 Forecast - Non-Gov both Revenue and Capital |  | 62.9 | 96 | 0 | 171.1
18-19 Baseline - Non-Gov both Revenue and Capital |  | 21.9 | 96 | 0 | 66.7
18-19 Forecast - Non-Gov both Revenue and Capital |  | 64.3 | 96 | 0 | 82.1
19-20 Baseline - Non-Gov both Revenue and Capital |  | 323.3 | 96 | 0 | 66.9
19-20 Forecast - Non-Gov both Revenue and Capital |  | 192.9 | 96 | 0 | 74.7
20-21 Baseline - Non-Gov both Revenue and Capital |  | 309.4 | 0 | 0 | 58.4
20-21 Forecast - Non-Gov both Revenue and Capital |  | 187.7 | 0 | 0 | 58.4
21-22 Baseline - Non-Gov both Revenue and Capital |  | 339.7 | 0 | 0 | 0
21-22 Forecast - Non-Gov both Revenue and Capital |  | 155.9 | 0 | 0 | 0
Pre 16-17 Baseline - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
Pre 16-17 Forecast - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
2016/2017Income (£m) Revenue & Capital Spend on Profile?
16-17 Baseline - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
16-17 Forecast - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
17-18 Baseline - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
17-18 Forecast - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
18-19 Baseline - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
18-19 Forecast - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
19-20 Baseline - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
19-20 Forecast - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
20-21 Baseline - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
20-21 Forecast - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
21-22 Baseline - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
21-22 Forecast - Income (£m) both Revenue and Capital |  | 0 | 0 | 0 | 0
Unprofiled Remainder Baseline - Non Gov both Revenue and Capital (GMPP - Remaining Spend) |  | 0 | 0 | 0 | 0
Unprofiled Remainder Forecast - Non Gov both Revenue and Capital (GMPP - Remaining Spend) |  | 0 | 0 | 0 | 0
Total Baseline - Income (£m) both Revenue and Capital | 0 | 0 | 0 | 0 | 0
Total Forecast - Income (£m) both Revenue and Capital | 0 | 0 | 0 | 0 | 0
Pre 16-17 BEN Baseline - Gov. Cashable |  |  |  | 0
Pre 16-17 BEN Baseline - Gov. Non-Cashable |  |  |  | 0
Pre 16-17 BEN Baseline - Economic (inc Economic (inc Private Partner) |  |  |  | 0
Pre 16-17 BEN Baseline - Disbenefit Disbenefit UK Economic |  |  |  | 0
Pre 16-17 BEN Baseline - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
Pre 16-17 BEN Actual - Gov. Cashable |  |  |  | 0
Pre 16-17 BEN Actual - Gov. Non-Cashable |  |  |  | 0
Pre 16-17 BEN Actual - Economic (inc Private Partner) |  |  |  | 0
Pre 16-17 BEN Actual - Disbenefit UK Economic |  |  |  | 0
Pre-profile BEN Total | 0 | 0 | 0 | 0 | 0
16-17 BEN Baseline - Gov. Cashable |  |  |  | 0
16-17 BEN Baseline - Gov. Non-Cashable |  |  |  | 0
16-17 BEN Baseline - Economic (inc Private Partner) |  |  |  | 0
16-17 BEN Baseline - Disbenefit UK Economic |  |  |  | 0
16-17 BEN Baseline - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
16-17 BEN Forecast - Gov. Cashable |  |  |  | 0
16-17 BEN Forecast - Gov. Non-Cashable |  |  |  | 0
16-17 BEN Forecast - Economic (inc Private Partner) |  |  |  | 0
16-17 BEN Forecast - Disbenefit UK Economic |  |  |  | 0
16-17 BEN Forecast - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
17-18 BEN Baseline - Gov. Cashable |  |  |  | 0
17-18 BEN Baseline - Gov. Non-Cashable |  |  |  | 0
17-18 BEN Baseline - Economic (inc Private Partner) |  |  |  | 0
17-18 BEN Baseline - Disbenefit UK Economic |  |  |  | 0
17-18 BEN Baseline - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
17-18 BEN Forecast - Gov. Cashable |  |  |  | 0
17-18 BEN Forecast - Gov. Non-Cashable |  |  |  | 0
17-18 BEN Forecast - Economic (inc Private Partner) |  |  |  | 0
17-18 BEN Forecast - Disbenefit UK Economic |  |  |  | 0
17-18 BEN Forecast - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
18-19 BEN Baseline - Gov. Cashable |  |  |  | 0
18-19 BEN Baseline - Gov. Non-Cashable |  |  |  | 0
18-19 BEN Baseline - Economic (inc Private Partner) |  |  |  | 0
18-19 BEN Baseline - Disbenefit UK Economic |  |  |  | 0
18-19 BEN Baseline - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
18-19 BEN Forecast - Gov. Cashable |  |  |  | 0
18-19 BEN Forecast - Gov. Non-Cashable |  |  |  | 0
18-19 BEN Forecast - Economic (inc Private Partner) |  |  |  | 0
18-19 BEN Forecast - Disbenefit UK Economic |  |  |  | 0
18-19 BEN Forecast - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
19-20 BEN Baseline - Gov. Cashable |  |  |  | 0
19-20 BEN Baseline - Gov. Non-Cashable |  |  |  | 0
19-20 BEN Baseline - Economic (inc Private Partner) |  |  |  | 0
19-20 BEN Baseline - Disbenefit UK Economic |  |  |  | 0
19-20 BEN Baseline - Total Monetised Benefits |  |  |  | 0
19-20 BEN Forecast - Gov. Cashable |  |  |  | 0
19-20 BEN Forecast - Gov. Non-Cashable |  |  |  | 0
19-20 BEN Forecast - Economic (inc Private Partner) |  |  |  | 0
19-20 BEN Forecast - Disbenefit UK Economic |  |  |  | 0
19-20 BEN Forecast - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
20-21 BEN Baseline - Gov. Cashable |  |  |  | 0
20-21 BEN Baseline - Gov. Non-Cashable |  |  |  | 0
20-21 BEN Baseline - Economic (inc Private Partner) |  |  |  | 0
20-21 BEN Baseline - Disbenefit UK Economic |  |  |  | 0
20-21 BEN Baseline - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
20-21 BEN Forecast - Gov. Cashable |  |  |  | 0
20-21 BEN Forecast - Gov. Non-Cashable |  |  |  | 0
20-21 BEN Forecast - Economic (inc Private Partner) |  |  |  | 0
20-21 BEN Forecast - Disbenefit UK Economic |  |  |  | 0
20-21 BEN Forecast - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
21-22 BEN Baseline - Gov. Cashable |  |  |  | 0
21-22 BEN Baseline - Gov. Non-Cashable |  |  |  | 0
21-22 BEN Baseline - Economic (inc Private Partner) |  |  |  | 0
21-22 BEN Baseline - Disbenefit UK Economic |  |  |  | 0
21-22 BEN Baseline - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
21-22 BEN Forecast - Gov. Cashable |  |  |  | 0
21-22 BEN Forecast - Gov. Non-Cashable |  |  |  | 0
21-22 BEN Forecast - Economic (inc Private Partner) |  |  |  | 0
21-22 BEN Forecast - Disbenefit UK Economic |  |  |  | 0
21-22 BEN Forecast - Total Monetised Benefits | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder BEN Baseline - Gov. Cashable |  |  |  | 0
Unprofiled Remainder BEN Baseline - Gov. Non-Cashable |  | 1351 | 0 | 0
Unprofiled Remainder BEN Baseline - Economic (inc Private Partner) |  |  | 3919 | 4796
Unprofiled Remainder BEN Baseline - Disbenefit UK Economic |  |  | -425 | 0
Unprofiled Remainder BEN Baseline - Total Monetised Benefits | 0 | 1351 | 3494 | 4796 | 0
Unprofiled Remainder BEN Forecast - Gov. Cashable |  |  |  | 0
Unprofiled Remainder BEN Forecast - Gov. Non-Cashable |  | 1351 | 0 | 0
Unprofiled Remainder BEN Forecast - Economic (inc Private Partner) | 2398 |  | 3919 | 4796
Unprofiled Remainder BEN Forecast - Disbenefit UK Economic |  |  | -425 | 0
Unprofiled Remainder BEN Forecast - Total Monetised Benefits | 2398 | 1351 | 3494 | 4796 | 0
Total BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
Total BEN Baseline - Gov. Non-Cashable | 0 | 1351 | 0 | 0 | 0
Total BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 3919 | 4796 | 0
Total BEN Baseline - Disbenefit UK Economic | 0 | 0 | -425 | 0 | 0
Total BEN Baseline - Total Monetised Benefits | 0 | 1351 | 3494 | 4796 | 0
Total BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
Total BEN Forecast - Gov. Non-Cashable | 0 | 1351 | 0 | 0 | 0
Total BEN Forecast - Economic (inc Private Partner) | 2398 | 0 | 3919 | 4796 | 0
Total BEN Forecast - Disbenefit UK Economic | 0 | 0 | -425 | 0 | 0
Total BEN Forecast - Total Monetised Benefits | 2398 | 1351 | 3494 | 4796 | 0
Year BEN spend stops | 2079/2081 | 2079/2081 | 2043/2045 | 2082/2084 | 2023/24
Benefits Narrative | Python is an interpreted, high-level, general-purpose programming language. Created by Guido van Rossum and first released in 1991, Python's design philosophy emphasizes code readability with its notable use of significant whitespace. Its language constructs and object-oriented approach aim to help programmers write clear, logical code for small and large-scale projects.[28] | Matplotlib is a plotting library for the Python programming language and its numerical mathematics extension NumPy. It provides an object-oriented API for embedding plots into applications using general-purpose GUI toolkits like Tkinter, wxPython, Qt, or GTK+. There is also a procedural "pylab" interface based on a state machine (like OpenGL), designed to closely resemble that of MATLAB, though its use is discouraged.[3] SciPy makes use of Matplotlib. | PyCharm is an integrated development environment (IDE) used in computer programming, specifically for the Python language. It is developed by the Czech company JetBrains.[6] It provides code analysis, a graphical debugger, an integrated unit tester, integration with version control systems (VCSes), and supports web development with Django as well as Data Science with Anaconda.[7] | Datamaps allows for data to be collected from multiple users using pre-defined forms, built out of Excel spreadsheets. The form can be as complex or as simple as you like - Datamaps does the hard work of collecting the data into one place for onward processing or analysis, whilst ensuring that the data is valid according to expectations. Datamaps acknowledges that in the office environment, we use Excel for everything, but using it to collect data requires help - which is where Datamaps excels. | GitHub, Inc. is an American multinational corporation that provides hosting for software development and version control using Git. It offers the distributed version control and source code management (SCM) functionality of Git, plus its own features. It provides access control and several collaboration features such as bug tracking, feature requests, task management, and wikis for every project.[3] Headquartered in California, it has been a subsidiary of Microsoft since 2018.[4]
Benefits Map | Yes | Yes | Yes | No | Yes
Benefits Analysed | Yes | No | Yes | No | Yes
Benefits Realisation Plan | Yes | No | No | No | No
Initial Benefits Cost Ratio (BCR) | 1.4 | 3.9 | 2.3.1 | 1.21 | 0.63
Adjusted Benefits Cost Ratio (BCR) | 2.6 |  |  | 2.01
VfM Category single entry | High | High | Very High | High | Poor
Present Value Cost (PVC) | £928.5m | 347 | 3725 | 1.9
Present Value Benefit (PVB) | £2 398m | 1351 | 3494 | 2.3
Assurance MM1 | Inverted Landing | Oxygen Magnetic | Man Collins | Inverted Landing | Columbia Hypatia
Assurance MM1 Original Baseline |  |  |  | 2014-10-30
Assurance MM1 Latest Approved Baseline
Assurance MM1 Forecast - Actual |  |  |  | 2014-10-30
Assurance MM1 DCA |  |  |  | Amber
Assurance MM1 Notes | Green lumber fallacy | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy | What you see if all there is | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM2 | Inverted Cosmonauts | Apollo Module | Space Command | Inverted Cosmonauts | Team Magma
Assurance MM2 Original Baseline |  |  | 2006-12-30 |  | 2015-10-31
Assurance MM2 Latest Approved Baseline
Assurance MM2 Forecast - Actual |  |  | 2006-12-30
Assurance MM2 DCA |  |  | Amber
Assurance MM2 Notes | Memento mori and amor fati | Green lumber fallacy | The mind is not a vessel to be filled but a fire to be lighted | What you see if all there is | The sea gets deeper the further you go into it
Assurance MM3 | Inverted Lade | Lunar Radiation | Astronauts Roving | Inverted Lade | Tranquility Cosmonauts
Assurance MM3 Original Baseline | 2013-09-20
Assurance MM3 Latest Approved Baseline
Assurance MM3 Forecast - Actual | 2013-09-20
Assurance MM3 DCA
Assurance MM3 Notes | Green lumber fallacy | What you see if all there is | Green lumber fallacy | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy
Assurance MM4 | Space Liftoff | Moon Magma | Gemini Hypatia | Space Liftoff | Apollo Landing
Assurance MM4 Original Baseline | 2015-02-26 | 2017-06-01 | 2007-09-28 | 2016-06-30
Assurance MM4 Latest Approved Baseline |  |  |  | 2016-09-15
Assurance MM4 Forecast - Actual | 2015-02-26 | 2017-06-01 | 2007-09-28 | 2016-09-15
Assurance MM4 DCA |  |  | Amber | Amber/Red
Assurance MM4 Notes | What you see if all there is | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy | Memento mori and amor fati
Assurance MM5 | Space Cosmic | Columbia Sea | Moon Shuttle | Space Cosmic | Team Cosmonauts
Assurance MM5 Original Baseline | 2016-01-18 |  | 2010-01-14 | 2019-03-31 | 2014-03-27
Assurance MM5 Latest Approved Baseline |  |  |  | 2020-09-30
Assurance MM5 Forecast - Actual | 2016-02-22 |  | 2010-01-14 | 2020-09-30 | 2014-03-23
Assurance MM5 DCA |  |  | Amber/Green
Assurance MM5 Notes | What you see if all there is | The mind is not a vessel to be filled but a fire to be lighted | Memento mori and amor fati | Green lumber fallacy | Memento mori and amor fati
Assurance MM6 | Challenger Walk | Soyuz Lade | Challenger Magnetic | Challenger Walk | Tranquility Roving
Assurance MM6 Original Baseline | 2020-09-13 |  | 2017-04-01 | 2025-12-31
Assurance MM6 Latest Approved Baseline
Assurance MM6 Forecast - Actual | 2020-09-13 |  | 2017-04-01 | 2025-12-31
Assurance MM6 DCA
Assurance MM6 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | Memento mori and amor fati | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | Memento mori and amor fati
Assurance MM7 | Apollo Command | Oxygen Cosmic | Space Roving | Apollo Command | Gravity Radiation
Assurance MM7 Original Baseline | 2021-06-20 |  | 2020-06-30 | 2026-06-30
Assurance MM7 Latest Approved Baseline
Assurance MM7 Forecast - Actual | 2021-06-20 |  | 2020-06-30 | 2026-06-30
Assurance MM7 DCA
Assurance MM7 Notes | The mind is not a vessel to be filled but a fire to be lighted | Don't you know an apparition is just a cheap date. What have you been drinking these days | The sea gets deeper the further you go into it | Green lumber fallacy | The sea gets deeper the further you go into it
Assurance MM8 | Tranquility Command | Lunar Eleven | Space Module | Tranquility Command | Craters Hypatia
Assurance MM8 Original Baseline
Assurance MM8 Latest Approved Baseline
Assurance MM8 Forecast - Actual
Assurance MM8 DCA
Assurance MM8 Notes | What you see if all there is | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | The mind is not a vessel to be filled but a fire to be lighted | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM9 | Tranquility Collins | Oxygen Cosmonauts | Challenger Radiation | Moon Liftoff | Man Magnetic
Assurance MM9 Original Baseline | 2016-02-01 |  | 2015-09-30 | 2015-10-20 | 2015-10-31
Assurance MM9 Latest Approved Baseline |  |  |  | 2015-11-23
Assurance MM9 Forecast - Actual | 2015-12-09 |  | 2015-09-30 | 2015-11-23 | 2016-09-28
Assurance MM9 DCA | Green |  | Amber | Amber | Amber/Red
Assurance MM9 Notes | What you see if all there is | The sea gets deeper the further you go into it | Green lumber fallacy | Memento mori and amor fati | Memento mori and amor fati
Assurance MM10 | Oxygen Module | Mercury Cosmic | Challenger Radiation | Space Walk | Tranquility Collins
Assurance MM10 Original Baseline | 2016-06-30 |  | 2014-04-01 | 2016-06-06 | 2017-01-18
Assurance MM10 Latest Approved Baseline |  |  | 2015-09-15 | 2016-08-17
Assurance MM10 Forecast - Actual | 2016-06-28 |  | 2015-09-15 | 2017-04-05 | 2017-01-18
Assurance MM10 DCA | Green |  |  | N/A | Amber/Green
Assurance MM10 Notes | What you see if all there is | What you see if all there is | Green lumber fallacy | Memento mori and amor fati | What you see if all there is
Assurance MM11 | Serenity Lade | Astronauts Eleven | Challenger Radiation | Lunar Liftoff | Soyuz Magnetic
Assurance MM11 Original Baseline | 2017-10-31 |  |  | 2017-01-31 | 2018-01-31
Assurance MM11 Latest Approved Baseline
Assurance MM11 Forecast - Actual | 2017-10-31 |  |  | 2017-01-31 | 2018-01-31
Assurance MM11 DCA
Assurance MM11 Notes | The mind is not a vessel to be filled but a fire to be lighted | The mind is not a vessel to be filled but a fire to be lighted | Memento mori and amor fati | What you see if all there is | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM12 | Oxygen Cosmonauts | Challenger Liftoff | Serenity Armstrong | Craters Cosmonauts | Astronauts Cosmic
Assurance MM12 Original Baseline | 2021-03-30 |  | 2016-11-30 | 2017-02-28
Assurance MM12 Latest Approved Baseline
Assurance MM12 Forecast - Actual | 2021-03-30 |  | 2016-11-30 | 2017-02-28
Assurance MM12 DCA
Assurance MM12 Notes | The mind is not a vessel to be filled but a fire to be lighted | Don't you know an apparition is just a cheap date. What have you been drinking these days | Memento mori and amor fati | Green lumber fallacy | What you see if all there is
Assurance MM13 | Columbia Checklist | Soyuz Ocean | Challenger Radiation | Columbia Checklist | Space Roving
Assurance MM13 Original Baseline |  |  | 2011-01-24 | 2017-01-10
Assurance MM13 Latest Approved Baseline |  |  |  | 2017-01-10
Assurance MM13 Forecast - Actual |  |  | 2011-01-24 | 2017-01-10
Assurance MM13 DCA |  |  | Amber | Amber/Red
Assurance MM13 Notes | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy | Memento mori and amor fati | The mind is not a vessel to be filled but a fire to be lighted | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM14 | Spaceship Collins | Gravity Cosmic | Soyuz Magma | Spaceship Collins | Apollo Hypatia
Assurance MM14 Original Baseline |  |  | 2012-02-24
Assurance MM14 Latest Approved Baseline
Assurance MM14 Forecast - Actual |  |  | 2012-02-24
Assurance MM14 DCA |  |  | Amber/Green
Assurance MM14 Notes | What you see if all there is | What you see if all there is | Memento mori and amor fati | Memento mori and amor fati | What you see if all there is
Assurance MM15 | Man Kestrel | Tranquility Magnetic | Space Liftoff | Man Kestrel | Lunar Kestrel
Assurance MM15 Original Baseline |  |  | 2014-07-01
Assurance MM15 Latest Approved Baseline
Assurance MM15 Forecast - Actual |  |  | 2014-07-01
Assurance MM15 DCA
Assurance MM15 Notes | Green lumber fallacy | The sea gets deeper the further you go into it | Green lumber fallacy | What you see if all there is | The sea gets deeper the further you go into it
Assurance MM16 | Orbital Lade | Apollo Ocean | Man Aldridge | Orbital Lade | Serenity Landing
Assurance MM16 Original Baseline |  |  | 2014-11-01
Assurance MM16 Latest Approved Baseline
Assurance MM16 Forecast - Actual |  |  | 2014-11-01
Assurance MM16 DCA
Assurance MM16 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | Green lumber fallacy | What you see if all there is | The sea gets deeper the further you go into it
Assurance MM17 | 9 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 9 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 11 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 9 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 9 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc)
Assurance MM17 Original Baseline
Assurance MM17 Latest Approved Baseline
Assurance MM17 Forecast - Actual
Assurance MM17 DCA
Assurance MM17 Notes | Green lumber fallacy | The sea gets deeper the further you go into it | Memento mori and amor fati | Don't you know an apparition is just a cheap date. What have you been drinking these days | The sea gets deeper the further you go into it
Assurance MM18 | 10 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 10 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 12 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 10 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc) | 10 (Repeat assurance point Assurance Action Plan (AAP) NAO PAC SGAR etc)
Assurance MM18 Original Baseline
Assurance MM18 Latest Approved Baseline
Assurance MM18 Forecast - Actual
Assurance MM18 DCA
Assurance MM18 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | The sea gets deeper the further you go into it | What you see if all there is | Green lumber fallacy | Green lumber fallacy
IAAP created | 2013-09-11 | 2017-03-31 | 2013-06-01 | 2015-02-10 | 2014-03-01
IAAP date revised | 2015-09-30 |  | 2016-11-01 | 2016-06-10 | 2014-04-14
IAPP version |  | v1 0 | 9 | 5
SRO assurance confidence RAG internal | Green | Amber/Green | Amber/Green | Amber | Amber
SRO assurance confidence RAG external | Amber/Green | Amber/Green | Amber/Green | Amber | Amber
SRO assurance confidence commentary
SRO assurance scope RAG internal | Green | Amber/Green | Amber/Green | Amber | Amber/Green
SRO assurance scope RAG external | Amber/Green | Amber/Green | Amber/Green | Amber | Amber
SRO assurance scope RAG commentary
SRO Benefits RAG | Green | Amber | Amber | Amber | Amber
Total Number of public sector employees working on the project | 18 | 1.95 | 5.86 | 9 | 1.95
Total Number of external contractors working on the project | 8 | 2 | 3.25 | 5 | 0
Total Number or vacancies on the project | 3 | 0 | 1 | 9 | 1.3
Resources commentary | What you see if all there is | The mind is not a vessel to be filled but a fire to be lighted | What you see if all there is | hammer | nail | The mind is not a vessel to be filled but a fire to be lighted
Total number of employees funded to work on project | 29 | 3.95 | 10.11 | 23 | 3.35
Overall Resource DCA - Now | Green | Amber | Green | Green | Amber
Overall Resource DCA - Future | Green | Green | Green | Amber | Amber
Digital - Now | N/A | N/A | N/A | N/A | N/A
Digital - Future | N/A | N/A | N/A | N/A | N/A
Information Technology - Now | Green | N/A | N/A | N/A | N/A
Information Technology - Future | Green | N/A | N/A | N/A | N/A
Legal Commercial Contract Management - Now | Green | N/A | Red | N/A | Green
Legal Commercial Contract Management - Future | Green | N/A | Amber | N/A | Green
Project Delivery - Now | Green | Amber | Green | Green | Green
Project Delivery - Future | Green | Green | Green | Green | Green
Change Implementation - Now | Green | N/A | Green | N/A | N/A
Change Implementation - Future | Green | N/A | Green | N/A | N/A
Technical - Now | Green | N/A | Green | Green
Technical - Future | Green | N/A | Green | Green
Industry Knowledge - Now | Green | N/A | Green | N/A | N/A
Industry Knowledge - Future | Green | N/A | Green | N/A | N/A
Finance - Now | Green | N/A | Green | N/A | N/A
Finance - Future | Green | N/A | Green | N/A | N/A
Analysis Now | Green | N/A |  | N/A
Analysis - future | Green |  |  | N/A
Communications & Stakeholder Engagement - Now |  |  |  | N/A
Communications & Stakeholder Engagement - Future |  |  |  | N/A
Other Capability 3 | Lands |  | other (please specify) | Other (please specify) | other (please specify)
Other Capability 3 - Now |  |  | Green |  | Amber
Other Capability 3 - Future |  |  | Green |  | Green
Other Capability 4 | other (please specify) |  | other (please specify) | Other (please specify) | other (please specify)
Other Capability 4 - Now
Other Capability 4 - Future
Cap Commentary
SCS PB3 No public sector
SCS PB3 No externals
SCS PB3 No vacancies
SCS PB3 Total | 0 | 0 | 0 | 0 | 0
SCS PB2 No public sector |  | 0.15 |  |  | 0.1
SCS PB2 No externals
SCS PB2 No vacancies
SCS PB2 Total | 0 | 0.15 | 0 | 0 | 0.1
SCS PB1 No public sector | 2 | 0.2 | 1 | 0 | 0.3
SCS PB1 No externals | 1 |  |  | 2
SCS PB1 No vacancies | 1 |  |  | 3
SCS PB1 Total | 4 | 0.2 | 1 | 5 | 0.3
G6 No public sector | 2 | 0.6 |  | 2 | 0.5
G6 No externals | 4 | 1 |  | 1
G6 No vacancies |  |  | 1 | 3
G6 Total | 6 | 1.6 | 1 | 6 | 0.5
G7 No public sector | 3 | 1 | 3.2 | 1 | 1.15
G7 No externals | 2 | 1 | 3.25 | 2
G7 No vacancies |  |  |  | 2 | 0.3
G7 Total | 5 | 2 | 6.45 | 5 | 1.45
FS No public sector | 1 |  | 0.33
FS No externals
FS No vacancies
FS Total | 1 | 0 | 0.33 | 0 | 0
SEO No public sector | 4 |  | 1 | 2
SEO No externals | 1 |  |  | 0
SEO No vacancies
SEO Total | 7 | 0 | 1 | 2 | 0
HEO No public sector | 1 |  |  | 0
HEO No externals
HEO No vacancies |  |  |  | 1 | 1
HEO Total | 1 | 0 | 0 | 1 | 1
EO No public sector | 3 |  | 0.33 | 2
EO No externals
EO No vacancies |  |  |  | 0
EO Total | 3 | 0 | 0.33 | 2 | 0
AO No public sector | 1 |  |  | 1
AO No externals
AO No vacancies
AO Total | 1 | 0 | 0 | 1 | 0
AA No public sector | 1 |  |  | 1
AA No externals
AA No vacancies
AA Total | 1 | 0 | 0 | 1 | 0
Digital No public sector
Digital No externals
Digital No vacancies |  |  | 0
IT No public sector | 1
IT No externals
IT No vacancies |  |  | 0
Legal Commercial No public sector | 1 |  | 0.33 |  | 0.15
Legal Commercial No externals | 1 |  | 1 | 1
Legal Commercial No vacancies |  |  | 0
PD No public sector | 10 | 1.95 | 2.2 | 8 | 1.8
PD No externals | 3 | 2 |  | 4
PD No vacancies | 3 |  | 0 | 9
Technical No public sector | 1 |  | 0.5 | 1
Technical No externals |  |  | 2
Technical No vacancies |  |  | 0
Change Implementation No public sector |  |  | 0.5
Change Implementation No externals | 1
Change Implementation No vacancies
Industry Knowledge No public sector |  |  | 0.5
Industry Knowledge No externals
Industry Knowledge No vacancies |  |  | 1
Finance No public sector |  |  | 0.5
Finance No externals | 3 |  | 0.25
Finance No vacancies |  |  | 0
Analysis No public sector
Analysis externals
Analysis No vacancies
Communications and Stakeholder No public sector | 3
Communications and Stakeholder No externals
Communications and Stakeholder No vacancies |  |  |  |  | 0.3
Other 3 No public sector | 2 |  | 1.33
Other 3 No externals
Other 3 No vacancies |  |  |  |  | 1
Other 4 No public sector
Other 4 No externals
Other 4 No vacancies
Total No public sector employees working on the project | 18 | 1.95 | 5.86 | 9 | 2.05
Total No external contractors working on the project | 8 | 2 | 3.25 | 5 | 0
Total No employees funded to work on project | 29 | 3.95 | 10.11 | 23 | 3.35
GMPP - IPA ID Number | DFT_0020_1314-Q2 | DFT_0025_1617-Q1 | DFT_0005_1112-Q1 | DfT_0022_1415-Q4 | DFT_0029_1617-Q1
GMPP - IPA ID Number 2 | 1.01.2 | 1.01.2 | 1.01.2 | 1.01.2 | 1.01.2
GMPP - Dept | DfT | DfT | DfT | DfT | DfT
GMPP - Main reason for joining GMPP | High Value Novel | High Vaule | High Value Complex (interfaces & dependencies) | High Level Novel & Contentious Complex | High Value
GMPP - IPA DCA | Amber | Amber/Red | Amber | Amber/red | Amber/Red
GMPP - IPA DCA Commentary | plastic | nail | What you see if all there is | screw driver | screw | The mind is not a vessel to be filled but a fire to be lighted
GMPP - SRO ID
GMPP - PD ID
GMPP Annual Report Category | Infrastructure and Construction | Infrastructure and Construction | Infrastructure and Construction | Infrastructure and Construction | Infrastructure and Construction
GMPP Quarter ID
Re-baseline this quarter
Re-baseline ALB/Programme milestones
Re-baseline ALB/Programme cost
Re-baseline ALB/Programme benefits
Re-baseline IPDC milestones
Re-baseline IPDC cost
Re-baseline IPDC benefits
Re-baseline HMT milestones
Re-baseline HMT cost
Re-baseline HMT benefits
Pre-profile RDEL | 0 | 0 | 45.98 | 0 | 4.94
Pre-profile CDEL Forecast one off new costs | 68.8 | 337.8 | 192 | 26.01 | 68
Pre 16-17 RDEL Actual - Whole Life Cost breakdown | 0 | 0 | 45.98 | 0 | 4.94
Pre 16-17 CDEL Actual - Whole Life Cost breakdown | 68.8 | 0 | 0 | 26.01 | 0
Pre-profile Forecast Non-Gov |  | 337.8 | 192 | 0 | 68
Total CDEL Forecast Total WLC | 1402.9 | 774.2 | 622.25 | 4395.01 | 542.8
Total CDEL Forecast Total WLC (old) | 1402.9 | 0 | 46.25 | 4395.01 | 0
Total Forecast - Non-Gov both Revenue and Capital | 0 | 774.2 | 576 | 0 | 542.8
Unprofiled Remainder CDEL Forecast - Whole Life Cost breakdown (GMPP - Remaining Spend) | 0 | 0 | 0 | 3413.2 | 0
Unprofiled Remainder RDEL Forecast - Non-Gov both Revenue and Capital (GMPP - Remaining Spend) |  | 299.4 | 5700 | 0 | 0
Unprofiled CDEL Forecast Total WLC | 0 | 299.4 | 5700 | 3413.2 | 0