## Master
Project/Programme Name | Falcon 9
Department | DFT
Delivery Body | Highways England
GMPP - IPA ID Number | DfT_0022_1415-Q4
Controls Project ID number
Project Type (for IPA use)
Classification | OFFICIAL SENSITIVE
GMPP (GMPP - formally joined GMPP) | 1415-Q4
Reporting period (GMPP - Snapshot Date) | Q4 1920
Snapshot Date | 2020-03-31
Senior Responsible Owner (SRO) | John Lennon
Senior Responsible Owner (SRO) - Email | john.l@highwaysengland.co.uk
Senior Responsible Owner (SRO) - ID number
SRO Sign-Off
Project Director (PD) | P G Wodehouse
Project Director (PD) - Email | wodehouse@uk.pwc.com
Project Director (PD) - ID number
Date Report Approved by PD? | 2020-04-03
Working Contact Name | Lord Wilmore
Working Contact Email | Lord.Wilmore@highengland.co.uk
Project Accountant with responsibility for Spend - Email
Project Benefits Mngr with responsibility for Benefits - Email
Project Planner with responsibility for Milestones - Email
IPA's Departmental Single Point of Contact
IPA's Departmental Single Point of Contact - Email
IPA Analysis & Insight Unit (AIU) Lead
IPA Analysis & Insight Unit (AIU) Lead - Email
Date Report Approved by AIU?
IPA Strategic Delivery Advisor (SDA) - Email
Date Report Approved by SDA?
Departmental PPM HoP copied in submission email?
Departmental PPM HoP - Email
Departmental HR HoP copied in submission email?
Departmental HR HoP - Email
Departmental Finance HoP copied in submission email?
Departmental Finance HoP - Email
Departmental Economics HoP copied in submission email?
Departmental Economics HoP - Email
Departmental Legal HoP copied in submission email?
Departmental Legal HoP - Email
Departmental Commercial l HoP copied in submission email?
Departmental Commercial HoP - Email
Departmental IT HoP copied in submission email?
Departmental IT HoP - Email
HMT Spending Team Lead copied in submission email?
HMT Spending Team Lead - Email
Quarter Joined
DFT ID Number
Working Contact Telephone | 07712 542999
DfT Group | Roads Places and Environment Group
DfT Division
Brief project description (GMPP - brief descripton) | Protagonist
GMPP - Dept | DFT
Agency or delivery partner (GMPP - Delivery Organisation primary) | Highways England
Delivery Organisation Secondary
Project status | Ongoing
Is the SRO for this project an MPLA Graduate? | Yes
Is the PD for this project an MPLA Graduate? | No
Does the Project have an issued SRO appointment letter? | Yes - published
Has the SRO issued an appointment letter to the PD? | Yes
Delivery Structure | Project
Change Delivery Methodology | Waterfall
Delivery Narrative | plastic
DN Type 1 | Economic Growth
DN Description 1 | What you see if all there is
DN Type 2 | Improved Service
DN Description 2 | Don't you know an apparition is just a cheap date. What have you been drinking these days
DN Type 3 | Environmental Impact
DN Description 3 | screw
DN Type 4 | Social Benefits
DN Description 4 | wood
DN Type 5 | Efficiency Savings
DN Description 5 | Don't you know an apparition is just a cheap date. What have you been drinking these days
Primary Category | Infrastructure
Secondary Category
Tertiary Category
GMPP Annual Report Category | Infrastructure and Construction
Significant Steel Requirement | Yes
For all construction infrastructure or capital investment procurements >£10M have you adopted the Government's Balanced Scorecard approach | Yes
GMPP - Main reason for joining GMPP
Second reason for joining GMPP (if applicable)
List Strategic Outcomes (GMPP - Intended Outcome 1) | Don't you know an apparition is just a cheap date. What have you been drinking these days
IO1 | 1
IO1 - Monetised? | Wider UK Economic
IO1 PESTLE | Economic
List Strategic Outcomes (GMPP - Intended Outcome 2) | Don't you know an apparition is just a cheap date. What have you been drinking these days
IO2 | 2
IO2 - Monetised? | Wider UK Economic
IO2 PESTLE | Economic
List Strategic Outcomes (GMPP - Intended Outcome 3) | screw driver
IO3 | 3
IO3 - Monetised? | Wider UK Economic
IO3 PESTLE | Economic
List Strategic Outcomes (GMPP - Intended Outcome 4) | nail
IO4 | 4
IO4 - Monetised? | Wider UK Economic
IO4 PESTLE | Environmental
List Strategic Outcomes (GMPP - Intended Outcome 5) | plastic
IO5 | 5
IO5 - Monetised? | Wider UK Economic
IO5 PESTLE | Social
List Strategic Outcomes (GMPP - Intended Outcome 6) | The sea gets deeper the further you go into it
IO6
IO6 - Monetised?
IO6 PESTLE
List Strategic Outcomes (GMPP - Intended Outcome 7) | nail
IO7
IO7 - Monetised?
IO7 PESTLE
List Strategic Outcomes (GMPP - Intended Outcome 8) | Don't you know an apparition is just a cheap date. What have you been drinking these days
IO8
IO8 - Monetised?
IO8 PESTLE
List Strategic Outcomes (GMPP - Intended Outcome 9)
IO9
IO9 - Monetised?
IO9 PESTLE
List Strategic Outcomes (GMPP - Intended Outcome 10)
IO10
IO10 - Monetised?
IO10 PESTLE
Primary investment Objective | Addressing the problems caused by congestion and unreliable journeys improvements in road crossing capacity are also required to support economic growth and improve the environment.
IO11 Monetised | Economy
Secondary Investment Objective
IO12 Monetised
Is successful completion of this project dependent on another GMPP project? | No
Dependency 1 - Department
Dependency 1 - GMPP Project
Dependency 2 - Department
Dependency 2 - GMPP Project
Dependency 3 - Department
Dependency 3 - GMPP Project
Project Scope | The protagonist of the novel. Dantès is an intelligent, honest, and loving man who turns bitter and vengeful after he is framed for a crime he does not commit. When Dantès finds himself free and enormously wealthy, he takes it upon himself to act as the agent of Providence, rewarding those who have helped him in his plight and punishing those responsible for his years of agony.
Departmental DCA | Amber
Departmental DCA Narrative | The Bretton Woods system of monetary management established the rules for commercial and financial relations among the United States, Canada, Western European countries, Australia, and Japan after the 1944 Bretton Woods Agreement. The Bretton Woods system was the first example of a fully negotiated monetary order intended to govern monetary relations among independent states. The chief features of the Bretton Woods system were an obligation for each country to adopt a monetary policy that maintained its external exchange rates within 1 percent by tying its currency to gold and the ability of the IMF to bridge temporary imbalances of payments. Also, there was a need to address the lack of cooperation among other countries and to prevent competitive devaluation of the currencies as well.
GMPP - IPA DCA | Amber
GMPP - IPA DCA Commentary | screw
Risk Level (RPA) | Banana
Risk Level (RPA) Date | 2019-10-01
Brief Risk Decription 1 | The sea gets deeper the further you go into it
BRD 1Risk Category | Social
BRD 1 Primary Risk to | Schedule
BRD 1 Internal Control | Tolerate
BRD 1 Residual Impact | High
BRD 1 Residual Likelihood | Very High
Brief Risk Decription 2 | hammer
BRD 2 Risk Category | Technological
BRD 2 Primary Risk to | Schedule
BRD 2 Internal Control | Treat - Corrective
BRD 2 Residual Impact | Very High
BRD 2 Residual Likelihood | High
Brief Risk Decription 3 | The mind is not a vessel to be filled but a fire to be lighted
BRD 3 Risk Category | Technological
BRD 3 Primary Risk to | Schedule
BRD 3 Internal Control | Treat - Corrective
BRD 3 Residual Impact | Medium
BRD 3 Residual Likelihood | Low
Brief Risk Decription 4 | screw driver
BRD 4 Risk Category | Environmental
BRD 4 Primary Risk to | Costs
BRD 4 Internal Control | Treat - Corrective
BRD 4 Residual Impact | High
BRD 4 Residual Likelihood | Medium
Brief Risk Decription 5 | The sea gets deeper the further you go into it
BRD 5 Risk Category | Social
BRD 5 Primary Risk to | Schedule
BRD 5 Internal Control | Treat - Corrective
BRD 5 Residual Impact | Medium
BRD 5 Residual Likelihood | Medium
1st Scope Change - Description / Type
SC1 Date Scope Change Implemented
SC1 Date Implemented: Actual or Forecast?
SC1 Impact on Project End Date?
SC1 Is change in Project End Date solely due to the scope change?
SC1 Impact on Costs?
SC1 Is change in Costs solely due to the scope change?
SC1 Impact on Intended Outcomes?
SC1 Has the Business Case been updated as a result of this scope change?
SC1 If Yes new Business Case Type?
SC1 New Business Case Version Number
SC1 Has HMT approved this new business case?
2nd Scope Change - Description / Type
SC2 Date Scope Change Implemented
SC2 Date Implemented: Actual or Forecast?
SC2 Impact on Project End Date?
SC2 Is change in Project End Date solely due to the scope change?
SC2 Impact on Costs?
SC2 Is change in Costs solely due to the scope change?
SC2 Impact on Intended Outcomes?
SC2 Has the Business Case been updated as a result of this scope change?
SC2 If Yes new Business Case Type?
SC2 New Business Case Version Number
SC2 Has HMT approved this new business case?
3rd Scope Change - Description / Type
SC3 Date Scope Change Implemented
SC3 Date Implemented: Actual or Forecast?
SC3 Impact on Project End Date?
SC3 Is change in Project End Date solely due to the scope change?
SC3 Impact on Costs?
SC3 Is change in Costs solely due to the scope change?
SC3 Impact on Intended Outcomes?
SC3 Has the Business Case been updated as a result of this scope change?
SC3 If Yes new Business Case Type?
SC3 New Business Case Version Number
SC3 Has HMT approved this new business case?
4th Scope Change - Description / Type
SC4 Date Scope Change Implemented
SC4 Date Implemented: Actual or Forecast?
SC4 Impact on Project End Date?
SC4 Is change in Project End Date solely due to the scope change?
SC4 Impact on Costs?
SC4 Is change in Costs solely due to the scope change?
SC4 Impact on Intended Outcomes?
SC4 Has the Business Case been updated as a result of this scope change?
SC4 If Yes new Business Case Type?
SC4 New Business Case Version Number
SC4 Has HMT approved this new business case?
SRO Is this position currently filled? | Yes - Permanent
GMPP - SRO ID
SRO Last Name | Lennon
SRO First Name | John
SRO Full Name | John Lennon
SRO Email | john.l@highwaysengland.co.uk
SRO Phone No. | 01306 999999
SRO Tenure Start Date | 2014-10-09
SRO Tenure End Date | 2025-12-31
SRO Length of tenure (years) | 11.2356
If SRO Tenure End Date change please advise reason
Job Title / Grade | Important person
SRO Grade | SCS1
SRO Career Anchor - Primary | Project Delivery
SRO Career Anchor - Secondary | Science and Engineering
Percentage of time spent on SRO Role | 0.25
If new SRO reason for change
SRO - SRO or PD on a Previous GMPP Project
SRO - Most Recent GMPP Project?
If there are further SROs please name and explain why?
PD Is this position currently filled? | Yes - Interim
GMPP - PD ID
PD Last Name | Pelham
PD First Name | Wodehouse
PD Full Name | P G Wodehouse
PD Email | wodehouse@uk.pwc.com
PD Phone No. | 07711 771 246
PD Tenure Start Date | 2019-07-22
PD Tenure End Date | 2020-07-22
PD Length of tenure (years) | 1.0027
If PD Tenure End Date change please advise reason and Type | Contract has been extended
Job Title | VIP
PD Grade | SCS1
PD Career Anchor - Primary | Project Delivery
PD Career Anchor - Secondary | Operational Delivery
Percentage of time spent on PD Role | 1
If new PD reason for change | Interim following the departure of the previous PD
PD - SRO or PD on a Previous GMPP Project | No
PD - Most Recent GMPP Project?
Secondary PDs please name?
No public sector employees working on the project | 26
No external contractors working on the project | 10
Total Number working in the project team FTEs | 36
No employees funded to work on project | 38
Total Number or vacancies on the project | 2
Resource Gap (%) | -0.052632
Project Team Turnover since last Quarter - Qualitative Assessment | Low
Resources commentary | nail
Digital - Now | Green
Digital - Future | Green
Digital Short Narrative (Amber or Red)
Information Technology - Now | N/A
Information Technology - Future | N/A
Information Technology Short Narrative (Amber or Red)
Legal Commercial Contract Management - Now | Green
Legal Commercial Contract Management - Future | Amber
Legal Commercial & Contract Management Short Narrative (Amber or Red) | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project Delivery - Now | Green
Project Delivery - Future | Green
Project Delivery Short Narrative (Amber or Red) | hammer
Change Implementation - Now | Green
Change Implementation - Future | Green
Change Implementation Short Narrative (Amber or Red) | nail
Technical - Now | Green
Technical - Future | Green
Technical Short Narrative (Amber or Red) | Green lumber fallacy
Industry Knowledge - Now | N/A
Industry Knowledge - Future | N/A
Industry Knowledge Short Narrative (Amber or Red) | Green lumber fallacy
Finance - Now | Green
Finance - Future | Green
Finance Short Narrative (Amber or Red) | hammer
Analysis Now | N/A
Analysis - future | N/A
Analysis Short Narrative (Amber or Red) | plastic
Communications & Stakeholder Engagement - Now | Green
Communications & Stakeholder Engagement - Future | Green
Communications & Stakeholder Engagement Short Narrative (Amber or Red)
Additional Capability 1 Descriptor
Additional Capability 1 Now
Additional Capability 1 Future
Additional Capability 1 Short Narrative (Amber or Red)
Additional Capability 2 Descriptor
Additional Capability 2 Now
Additional Capability 2 Future
Additional Capability 2 Short Narrative (Amber or Red)
Additional Capability 3 Descriptor
Other Capability 3 - Now
Other Capability 3 - Future
Additional Capability 3 Short Narrative (Amber or Red)
Additional Capability 4 Descriptor
Other Capability 4 - Now
Other Capability 4 - Future
Additional Capability 4 Short Narrative (Amber or Red)
Additional Capability 5 Descriptor
Additional Capability 5 Now
Additional Capability 5 Future
Additional Capability 5 Short Narrative (Amber or Red)
Overall Resource DCA - Now | Green
Overall Resource DCA - Future | Amber
Approval MM1 | Earth Command
Approval MM1 Gov Type | hammer
Approval MM1 Ver No | 0
Approval MM1 Original Baseline | 2015-10-28
Approval MM1 Forecast / Actual | 2015-10-28
Approval MM1 Variance | 0
Approval MM1 Status | Complete
Approval MM1 Notes | Memento mori and amor fati
Approval MM2 | Standard B
Approval MM2 Gov Type | wood
Approval MM2 Ver No | 1.6
Approval MM2 Original Baseline | 2016-01-18
Approval MM2 Forecast / Actual | 2016-01-18
Approval MM2 Variance | 0
Approval MM2 Status | Complete
Approval MM2 Notes | Memento mori and amor fati
Approval MM3 | Team Liftoff
Approval MM3 Gov Type | screw
Approval MM3 Ver No | 1.6
Approval MM3 Original Baseline | 2016-01-18
Approval MM3 Forecast / Actual | 2016-01-18
Approval MM3 Variance | 0
Approval MM3 Status | Complete
Approval MM3 Notes | What you see if all there is
Approval MM4 | Gravity Landing
Approval MM4 Gov Type | screw driver
Approval MM4 Ver No | 0
Approval MM4 Original Baseline | 2019-11-27
Approval MM4 Forecast / Actual | 2019-11-27
Approval MM4 Variance | 0
Approval MM4 Status | Complete
Approval MM4 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Approval MM5 | Standard C
Approval MM5 Gov Type | wood
Approval MM5 Ver No | 0
Approval MM5 Original Baseline | 2019-06-24
Approval MM5 Forecast / Actual | 2019-12-09
Approval MM5 Variance | 168
Approval MM5 Status | Complete
Approval MM5 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM6 | Sputnik Radiation
Approval MM6 Gov Type | wood
Approval MM6 Ver No | 0
Approval MM6 Original Baseline | 2019-09-30
Approval MM6 Forecast / Actual | 2020-03-31
Approval MM6 Variance | 183
Approval MM6 Status | Live
Approval MM6 Notes | The sea gets deeper the further you go into it
Approval MM7 | Spaceship Magma
Approval MM7 Gov Type | hammer
Approval MM7 Ver No | 0
Approval MM7 Original Baseline | 2021-08-31
Approval MM7 Forecast / Actual | 2021-08-31
Approval MM7 Variance | 0
Approval MM7 Status | Live
Approval MM7 Notes | What you see if all there is
Approval MM8 | Standard D
Approval MM8 Gov Type | screw
Approval MM8 Ver No | 0
Approval MM8 Original Baseline | 2021-10-31
Approval MM8 Forecast / Actual | 2021-10-31
Approval MM8 Variance | 0
Approval MM8 Status | Live
Approval MM8 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM9 | Gemini Cosmonauts
Approval MM9 Gov Type | screw
Approval MM9 Ver No | 0
Approval MM9 Original Baseline | 2021-12-31
Approval MM9 Forecast / Actual | 2021-12-31
Approval MM9 Variance | 0
Approval MM9 Status | Live
Approval MM9 Notes | Green lumber fallacy
Approval MM10 | Moon Cosmonauts
Approval MM10 Gov Type | nail
Approval MM10 Ver No | 0
Approval MM10 Original Baseline | 2022-01-31
Approval MM10 Forecast / Actual | 2022-02-14
Approval MM10 Variance | 14
Approval MM10 Status | Live
Approval MM10 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Approval MM11 | Spaceship Checklist
Approval MM11 Gov Type | wood
Approval MM11 Ver No | 0
Approval MM11 Original Baseline | 2017-12-20
Approval MM11 Forecast / Actual | 2017-12-20
Approval MM11 Variance | 0
Approval MM11 Status | Complete
Approval MM11 Notes | Green lumber fallacy
Approval MM12 | Space Kestrel
Approval MM12 Gov Type | screw driver
Approval MM12 Ver No | 0
Approval MM12 Original Baseline | 2020-07-31
Approval MM12 Forecast / Actual
Approval MM12 Variance
Approval MM12 Status | Redundant
Approval MM12 Notes | The sea gets deeper the further you go into it
Approval MM13 | Soyuz Armstrong
Approval MM13 Gov Type | nail
Approval MM13 Ver No | 0
Approval MM13 Original Baseline | 2025-11-30
Approval MM13 Forecast - Actual | 2025-11-30
Approval MM13 Variance | 0
Approval MM13 Status | Live
Approval MM13 Notes | Green lumber fallacy
Approval MM14 | Earth Walk
Approval MM14 Gov Type | screw
Approval MM14 Ver No | 0
Approval MM14 Original Baseline | 2018-05-21
Approval MM14 Forecast - Actual | 2018-05-21
Approval MM14 Variance | 0
Approval MM14 Status | Complete
Approval MM14 Notes | What you see if all there is
Approval MM15 | Craters Cosmic
Approval MM15 Gov Type | screw
Approval MM15 Ver No | 0
Approval MM15 Original Baseline | 2020-06-30
Approval MM15 Forecast - Actual | 2020-06-30
Approval MM15 Variance | 0
Approval MM15 Status | Live
Approval MM15 Notes | The sea gets deeper the further you go into it
Approval MM16 | Apollo Cosmonauts
Approval MM16 Gov Type | nail
Approval MM16 Ver No | 0
Approval MM16 Original Baseline | 2021-12-31
Approval MM16 Forecast - Actual | 2021-12-31
Approval MM16 Variance | 0
Approval MM16 Status | Live
Approval MM16 Notes | Memento mori and amor fati
Approval MM17 | Soyuz Magnetic
Approval MM17 Gov Type | screw
Approval MM17 Ver No | 0
Approval MM17 Original Baseline | 2020-12-31
Approval MM17 Forecast / Actual | 2020-12-31
Approval MM17 Variance | 0
Approval MM17 Status | Live
Approval MM17 Notes | The sea gets deeper the further you go into it
Approval MM18 | Team Aldridge
Approval MM18 Gov Type | nail
Approval MM18 Ver No | 0
Approval MM18 Original Baseline | 2020-06-01
Approval MM18 Forecast / Actual | 2020-06-01
Approval MM18 Variance | 0
Approval MM18 Status | Live
Approval MM18 Notes | What you see if all there is
Approval MM19 | Mercury Hypatia
Approval MM19 Gov Type | plastic
Approval MM19 Ver No | 0
Approval MM19 Original Baseline | 2020-06-30
Approval MM19 Forecast / Actual | 2020-06-30
Approval MM19 Variance | 0
Approval MM19 Status | Live
Approval MM19 Notes | What you see if all there is
Approval MM20
Approval MM20 Gov Type | nail
Approval MM20 Ver No
Approval MM20 Original Baseline
Approval MM20 Forecast / Actual
Approval MM20 Variance
Approval MM20 Status
Approval MM20 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM21
Approval MM21 Gov Type | screw driver
Approval MM21 Ver No
Approval MM21 Original Baseline
Approval MM21 Forecast / Actual
Approval MM21 Variance
Approval MM21 Status
Approval MM21 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM22
Approval MM22 Gov Type | screw driver
Approval MM22 Ver No
Approval MM22 Original Baseline
Approval MM22 Forecast / Actual
Approval MM22 Variance
Approval MM22 Status
Approval MM22 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM23
Approval MM23 Gov Type | plastic
Approval MM23 Ver No
Approval MM23 Original Baseline
Approval MM23 Forecast / Actual
Approval MM23 Variance
Approval MM23 Status
Approval MM23 Notes | The sea gets deeper the further you go into it
Approval MM24
Approval MM24 Gov Type | screw driver
Approval MM24 Ver No
Approval MM24 Original Baseline
Approval MM24 Forecast / Actual
Approval MM24 Variance
Approval MM24 Status
Approval MM24 Notes | Memento mori and amor fati
Approval MM25
Approval MM25 Gov Type | plastic
Approval MM25 Ver No
Approval MM25 Original Baseline
Approval MM25 Forecast / Actual
Approval MM25 Variance
Approval MM25 Status
Approval MM25 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Approval MM26
Approval MM26 Gov Type | hammer
Approval MM26 Ver No
Approval MM26 Original Baseline
Approval MM26 Forecast / Actual
Approval MM26 Variance
Approval MM26 Status
Approval MM26 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Approval MM27
Approval MM27 Gov Type | plastic
Approval MM27 Ver No
Approval MM27 Original Baseline
Approval MM27 Forecast / Actual
Approval MM27 Variance
Approval MM27 Status
Approval MM27 Notes | Memento mori and amor fati
Approval MM28
Approval MM28 Gov Type | nail
Approval MM28 Ver No
Approval MM28 Original Baseline
Approval MM28 Forecast / Actual
Approval MM28 Variance
Approval MM28 Status
Approval MM28 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM29
Approval MM29 Gov Type | plastic
Approval MM29 Ver No
Approval MM29 Original Baseline
Approval MM29 Forecast / Actual
Approval MM29 Variance
Approval MM29 Status
Approval MM29 Notes | Green lumber fallacy
Approval MM30
Approval MM30 Gov Type | nail
Approval MM30 Ver No
Approval MM30 Original Baseline
Approval MM30 Forecast / Actual
Approval MM30 Variance
Approval MM30 Status
Approval MM30 Notes | Green lumber fallacy
Approval MM31
Approval MM31 Gov Type | screw driver
Approval MM31 Ver No
Approval MM31 Original Baseline
Approval MM31 Forecast / Actual
Approval MM31 Variance
Approval MM31 Status
Approval MM31 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM32
Approval MM32 Gov Type | plastic
Approval MM32 Ver No
Approval MM32 Original Baseline
Approval MM32 Forecast / Actual
Approval MM32 Variance
Approval MM32 Status
Approval MM32 Notes | What you see if all there is
Approval MM33
Approval MM33 Gov Type | nail
Approval MM33 Ver No
Approval MM33 Original Baseline
Approval MM33 Forecast / Actual
Approval MM33 Variance
Approval MM33 Status
Approval MM33 Notes | Memento mori and amor fati
Approval MM34
Approval MM34 Gov Type | screw
Approval MM34 Ver No
Approval MM34 Original Baseline
Approval MM34 Forecast / Actual
Approval MM34 Variance
Approval MM34 Status
Approval MM34 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM35
Approval MM35 Gov Type | screw driver
Approval MM35 Ver No
Approval MM35 Original Baseline
Approval MM35 Forecast / Actual
Approval MM35 Variance
Approval MM35 Status
Approval MM35 Notes | The sea gets deeper the further you go into it
Approval MM36
Approval MM36 Gov Type | screw
Approval MM36 Ver No
Approval MM36 Original Baseline
Approval MM36 Forecast / Actual
Approval MM36 Variance
Approval MM36 Status
Approval MM36 Notes | Green lumber fallacy
Approval MM37
Approval MM37 Gov Type | plastic
Approval MM37 Ver No
Approval MM37 Original Baseline
Approval MM37 Forecast / Actual
Approval MM37 Variance
Approval MM37 Status
Approval MM37 Notes | Green lumber fallacy
Approval MM38
Approval MM38 Gov Type | wood
Approval MM38 Ver No
Approval MM38 Original Baseline
Approval MM38 Forecast / Actual
Approval MM38 Variance
Approval MM38 Status
Approval MM38 Notes | Memento mori and amor fati
Approval MM39
Approval MM39 Gov Type | nail
Approval MM39 Ver No
Approval MM39 Original Baseline
Approval MM39 Forecast / Actual
Approval MM39 Variance
Approval MM39 Status
Approval MM39 Notes | Green lumber fallacy
Approval MM40
Approval MM40 Gov Type | hammer
Approval MM40 Ver No
Approval MM40 Original Baseline
Approval MM40 Forecast / Actual
Approval MM40 Variance
Approval MM40 Status
Approval MM40 Notes | Green lumber fallacy
Approval MM41
Approval MM41 Gov Type | screw
Approval MM41 Ver No
Approval MM41 Original Baseline
Approval MM41 Forecast / Actual
Approval MM41 Variance
Approval MM41 Status
Approval MM41 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Approval MM42
Approval MM42 Gov Type | hammer
Approval MM42 Ver No
Approval MM42 Original Baseline
Approval MM42 Forecast / Actual
Approval MM42 Variance
Approval MM42 Status
Approval MM42 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM43
Approval MM43 Gov Type | hammer
Approval MM43 Ver No
Approval MM43 Original Baseline
Approval MM43 Forecast / Actual
Approval MM43 Variance
Approval MM43 Status
Approval MM43 Notes | Memento mori and amor fati
Approval MM44
Approval MM44 Gov Type | screw
Approval MM44 Ver No
Approval MM44 Original Baseline
Approval MM44 Forecast / Actual
Approval MM44 Variance
Approval MM44 Status
Approval MM44 Notes | The sea gets deeper the further you go into it
Approval MM45
Approval MM45 Gov Type | hammer
Approval MM45 Ver No
Approval MM45 Original Baseline
Approval MM45 Forecast / Actual
Approval MM45 Variance
Approval MM45 Status
Approval MM45 Notes | Memento mori and amor fati
Approval MM46
Approval MM46 Gov Type | hammer
Approval MM46 Ver No
Approval MM46 Original Baseline
Approval MM46 Forecast / Actual
Approval MM46 Variance
Approval MM46 Status
Approval MM46 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM47
Approval MM47 Gov Type | hammer
Approval MM47 Ver No
Approval MM47 Original Baseline
Approval MM47 Forecast / Actual
Approval MM47 Variance
Approval MM47 Status
Approval MM47 Notes | Memento mori and amor fati
Approval MM48
Approval MM48 Gov Type | nail
Approval MM48 Ver No
Approval MM48 Original Baseline
Approval MM48 Forecast / Actual
Approval MM48 Variance
Approval MM48 Status
Approval MM48 Notes | The mind is not a vessel to be filled but a fire to be lighted
Approval MM49
Approval MM49 Gov Type | hammer
Approval MM49 Ver No
Approval MM49 Original Baseline
Approval MM49 Forecast / Actual
Approval MM49 Variance
Approval MM49 Status
Approval MM49 Notes | Green lumber fallacy
Approval MM50
Approval MM50 Gov Type | nail
Approval MM50 Ver No
Approval MM50 Original Baseline
Approval MM50 Forecast / Actual
Approval MM50 Variance
Approval MM50 Status
Approval MM50 Notes | The sea gets deeper the further you go into it
IPDC approval point | Outline Business Case
Re-baseline this quarter | Yes
Re-baseline ALB/Programme milestones | Yes
Re-baseline ALB/Programme cost | Yes
Re-baseline ALB/Programme benefits | Yes
Re-baseline IPDC milestones | Yes
Re-baseline IPDC cost | Yes
Re-baseline IPDC benefits | Yes
Re-baseline HMT milestones | Yes
Re-baseline HMT cost | Yes
Re-baseline HMT benefits | Yes
Assurance MM1 | Inverted Cosmonauts
Assurance MM1 LoD | screw driver
Assurance MM1 Original Baseline | 2014-10-30
Assurance MM1 Forecast - Actual | 2014-10-30
Assurance MM1 Variance | 0
Assurance MM1 Status | Redundant
Assurance MM1 Notes | The sea gets deeper the further you go into it
Assurance MM2 | Inverted Lade
Assurance MM2 LoD | hammer
Assurance MM2 Original Baseline | 2016-09-15
Assurance MM2 Forecast - Actual | 2016-09-15
Assurance MM2 Variance | 0
Assurance MM2 Status | Complete
Assurance MM2 Notes | Memento mori and amor fati
Assurance MM3 | Space Liftoff
Assurance MM3 LoD | screw
Assurance MM3 Original Baseline | 2020-04-24
Assurance MM3 Forecast - Actual | 2020-04-24
Assurance MM3 Variance | 0
Assurance MM3 Status | Live
Assurance MM3 Notes | Green lumber fallacy
Assurance MM4 | Space Cosmic
Assurance MM4 LoD | plastic
Assurance MM4 Original Baseline | 2021-09-30
Assurance MM4 Forecast - Actual | 2021-09-30
Assurance MM4 Variance | 0
Assurance MM4 Status | Live
Assurance MM4 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM5 | Challenger Walk
Assurance MM5 LoD | wood
Assurance MM5 Original Baseline | 2027-10-30
Assurance MM5 Forecast - Actual | 2027-10-30
Assurance MM5 Variance | 0
Assurance MM5 Status | Live
Assurance MM5 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM6 | Apollo Command
Assurance MM6 LoD | screw driver
Assurance MM6 Original Baseline | 2028-12-31
Assurance MM6 Forecast - Actual | 2028-12-31
Assurance MM6 Variance | 0
Assurance MM6 Status | Live
Assurance MM6 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM7 | Gemini Sea
Assurance MM7 LoD | screw
Assurance MM7 Original Baseline | 2027-09-30
Assurance MM7 Forecast - Actual | 2027-09-30
Assurance MM7 Variance | 0
Assurance MM7 Status | Live
Assurance MM7 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM8 | Gravity Walk
Assurance MM8 LoD | plastic
Assurance MM8 Original Baseline | 2028-11-22
Assurance MM8 Forecast - Actual | 2028-11-22
Assurance MM8 Variance | 0
Assurance MM8 Status | Live
Assurance MM8 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM9 | Meteorite Cosmonauts
Assurance MM9 LoD | nail
Assurance MM9 Original Baseline | 2021-11-30
Assurance MM9 Forecast - Actual | 2021-11-30
Assurance MM9 Variance | 0
Assurance MM9 Status | Live
Assurance MM9 Notes | Memento mori and amor fati
Assurance MM10 | Man Ocean
Assurance MM10 LoD | plastic
Assurance MM10 Original Baseline | 2022-08-30
Assurance MM10 Forecast - Actual | 2022-08-30
Assurance MM10 Variance | 0
Assurance MM10 Status | Live
Assurance MM10 Notes | The sea gets deeper the further you go into it
Assurance MM11 | Inverted Hypatia
Assurance MM11 LoD | screw driver
Assurance MM11 Original Baseline | 2020-07-13
Assurance MM11 Forecast - Actual | 2020-07-13
Assurance MM11 Variance | 0
Assurance MM11 Status | Live
Assurance MM11 Notes | Green lumber fallacy
Assurance MM12 | Space Walk
Assurance MM12 LoD | plastic
Assurance MM12 Original Baseline | 2017-05-19
Assurance MM12 Forecast - Actual | 2017-05-19
Assurance MM12 Variance | 0
Assurance MM12 Status | Complete
Assurance MM12 Notes | What you see if all there is
Assurance MM13 | Moon Liftoff
Assurance MM13 LoD | plastic
Assurance MM13 Original Baseline | 2015-10-20
Assurance MM13 Forecast - Actual | 2015-11-23
Assurance MM13 Variance | 34
Assurance MM13 Status | Complete
Assurance MM13 Notes | Green lumber fallacy
Assurance MM14 | Lunar Liftoff
Assurance MM14 LoD | hammer
Assurance MM14 Original Baseline | 2017-01-10
Assurance MM14 Forecast - Actual | 2017-01-10
Assurance MM14 Variance | 0
Assurance MM14 Status | Complete
Assurance MM14 Notes | The sea gets deeper the further you go into it
Assurance MM15 | Inverted Landing
Assurance MM15 LoD | wood
Assurance MM15 Original Baseline | 2014-10-30
Assurance MM15 Forecast - Actual | 2014-10-30
Assurance MM15 Variance | 0
Assurance MM15 Status | Complete
Assurance MM15 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM16 | Serenity Eleven
Assurance MM16 LoD | plastic
Assurance MM16 Original Baseline | 2018-08-31
Assurance MM16 Forecast - Actual | 2019-12-18
Assurance MM16 Variance | 474
Assurance MM16 Status | Complete
Assurance MM16 Notes | What you see if all there is
Assurance MM17
Assurance MM17 LoD | screw driver
Assurance MM17 Original Baseline
Assurance MM17 Forecast - Actual
Assurance MM17 Variance
Assurance MM17 Status
Assurance MM17 Notes | What you see if all there is
Assurance MM18
Assurance MM18 LoD | plastic
Assurance MM18 Original Baseline
Assurance MM18 Forecast - Actual
Assurance MM18 Variance
Assurance MM18 Status
Assurance MM18 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM19
Assurance MM19 LoD | screw driver
Assurance MM19 Original Baseline
Assurance MM19 Forecast - Actual
Assurance MM19 Variance
Assurance MM19 Status
Assurance MM19 Notes | Memento mori and amor fati
Assurance MM20
Assurance MM20 LoD | hammer
Assurance MM20 Original Baseline
Assurance MM20 Forecast - Actual
Assurance MM20 Variance
Assurance MM20 Status
Assurance MM20 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM21
Assurance MM21 LoD | wood
Assurance MM21 Original Baseline
Assurance MM21 Forecast - Actual
Assurance MM21 Variance
Assurance MM21 Status
Assurance MM21 Notes | Memento mori and amor fati
Assurance MM22
Assurance MM22 LoD | plastic
Assurance MM22 Original Baseline
Assurance MM22 Forecast - Actual
Assurance MM22 Variance
Assurance MM22 Status
Assurance MM22 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM23
Assurance MM23 LoD | screw
Assurance MM23 Original Baseline
Assurance MM23 Forecast - Actual
Assurance MM23 Variance
Assurance MM23 Status
Assurance MM23 Notes | Memento mori and amor fati
Assurance MM24
Assurance MM24 LoD | screw
Assurance MM24 Original Baseline
Assurance MM24 Forecast - Actual
Assurance MM24 Variance
Assurance MM24 Status
Assurance MM24 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM25
Assurance MM25 LoD | hammer
Assurance MM25 Original Baseline
Assurance MM25 Forecast - Actual
Assurance MM25 Variance
Assurance MM25 Status
Assurance MM25 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM26
Assurance MM26 LoD | nail
Assurance MM26 Original Baseline
Assurance MM26 Forecast - Actual
Assurance MM26 Variance
Assurance MM26 Status
Assurance MM26 Notes | The sea gets deeper the further you go into it
Assurance MM27
Assurance MM27 LoD | hammer
Assurance MM27 Original Baseline
Assurance MM27 Forecast - Actual
Assurance MM27 Variance
Assurance MM27 Status
Assurance MM27 Notes | Green lumber fallacy
Assurance MM28
Assurance MM28 LoD | plastic
Assurance MM28 Original Baseline
Assurance MM28 Forecast - Actual
Assurance MM28 Variance
Assurance MM28 Status
Assurance MM28 Notes | What you see if all there is
Assurance MM29
Assurance MM29 LoD | screw
Assurance MM29 Original Baseline
Assurance MM29 Forecast - Actual
Assurance MM29 Variance
Assurance MM29 Status
Assurance MM29 Notes | Green lumber fallacy
Assurance MM30
Assurance MM30 LoD | screw
Assurance MM30 Original Baseline
Assurance MM30 Forecast - Actual
Assurance MM30 Variance
Assurance MM30 Status
Assurance MM30 Notes | The sea gets deeper the further you go into it
Assurance MM31
Assurance MM31 LoD | screw driver
Assurance MM31 Original Baseline
Assurance MM31 Forecast - Actual
Assurance MM31 Variance
Assurance MM31 Status
Assurance MM31 Notes | Memento mori and amor fati
Assurance MM32
Assurance MM32 LoD | nail
Assurance MM32 Original Baseline
Assurance MM32 Forecast - Actual
Assurance MM32 Variance
Assurance MM32 Status
Assurance MM32 Notes | What you see if all there is
Assurance MM33
Assurance MM33 LoD | nail
Assurance MM33 Original Baseline
Assurance MM33 Forecast - Actual
Assurance MM33 Variance
Assurance MM33 Status
Assurance MM33 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM34
Assurance MM34 LoD | plastic
Assurance MM34 Original Baseline
Assurance MM34 Forecast - Actual
Assurance MM34 Variance
Assurance MM34 Status
Assurance MM34 Notes | What you see if all there is
Assurance MM35
Assurance MM35 LoD | hammer
Assurance MM35 Original Baseline
Assurance MM35 Forecast - Actual
Assurance MM35 Variance
Assurance MM35 Status
Assurance MM35 Notes | The sea gets deeper the further you go into it
Assurance MM36
Assurance MM36 LoD | nail
Assurance MM36 Original Baseline
Assurance MM36 Forecast - Actual
Assurance MM36 Variance
Assurance MM36 Status
Assurance MM36 Notes | What you see if all there is
Assurance MM37
Assurance MM37 LoD | screw driver
Assurance MM37 Original Baseline
Assurance MM37 Forecast - Actual
Assurance MM37 Variance
Assurance MM37 Status
Assurance MM37 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM38
Assurance MM38 LoD | hammer
Assurance MM38 Original Baseline
Assurance MM38 Forecast - Actual
Assurance MM38 Variance
Assurance MM38 Status
Assurance MM38 Notes | Memento mori and amor fati
Assurance MM39
Assurance MM39 LoD | wood
Assurance MM39 Original Baseline
Assurance MM39 Forecast - Actual
Assurance MM39 Variance
Assurance MM39 Status
Assurance MM39 Notes | What you see if all there is
Assurance MM40
Assurance MM40 LoD | plastic
Assurance MM40 Original Baseline
Assurance MM40 Forecast - Actual
Assurance MM40 Variance
Assurance MM40 Status
Assurance MM40 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM41
Assurance MM41 LoD | plastic
Assurance MM41 Original Baseline
Assurance MM41 Forecast - Actual
Assurance MM41 Variance
Assurance MM41 Status
Assurance MM41 Notes | The sea gets deeper the further you go into it
Assurance MM42
Assurance MM42 LoD | wood
Assurance MM42 Original Baseline
Assurance MM42 Forecast - Actual
Assurance MM42 Variance
Assurance MM42 Status
Assurance MM42 Notes | Memento mori and amor fati
Assurance MM43
Assurance MM43 LoD | screw driver
Assurance MM43 Original Baseline
Assurance MM43 Forecast - Actual
Assurance MM43 Variance
Assurance MM43 Status
Assurance MM43 Notes | Memento mori and amor fati
Assurance MM44
Assurance MM44 LoD | screw
Assurance MM44 Original Baseline
Assurance MM44 Forecast - Actual
Assurance MM44 Variance
Assurance MM44 Status
Assurance MM44 Notes | Green lumber fallacy
Assurance MM45
Assurance MM45 LoD | screw
Assurance MM45 Original Baseline
Assurance MM45 Forecast - Actual
Assurance MM45 Variance
Assurance MM45 Status
Assurance MM45 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM46
Assurance MM46 LoD | screw driver
Assurance MM46 Original Baseline
Assurance MM46 Forecast - Actual
Assurance MM46 Variance
Assurance MM46 Status
Assurance MM46 Notes | Green lumber fallacy
Assurance MM47
Assurance MM47 LoD | hammer
Assurance MM47 Original Baseline
Assurance MM47 Forecast - Actual
Assurance MM47 Variance
Assurance MM47 Status
Assurance MM47 Notes | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM48
Assurance MM48 LoD | nail
Assurance MM48 Original Baseline
Assurance MM48 Forecast - Actual
Assurance MM48 Variance
Assurance MM48 Status
Assurance MM48 Notes | The sea gets deeper the further you go into it
Assurance MM49
Assurance MM49 LoD | plastic
Assurance MM49 Original Baseline
Assurance MM49 Forecast - Actual
Assurance MM49 Variance
Assurance MM49 Status
Assurance MM49 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Assurance MM50
Assurance MM50 LoD | wood
Assurance MM50 Original Baseline
Assurance MM50 Forecast - Actual
Assurance MM50 Variance
Assurance MM50 Status
Assurance MM50 Notes | What you see if all there is
Project MM18 | Standard A
Project MM18 CP | Yes
Project MM18 Original Baseline | 2014-05-30
Project MM18 Forecast - Actual | 2014-05-30
Project MM18 Variance | 0
Project MM18 Status | Complete
Project MM18 Notes | The sea gets deeper the further you go into it
Project MM19 | Standard H
Project MM19 CP | No
Project MM19 Original Baseline | 2028-12-22
Project MM19 Forecast - Actual | 2028-12-22
Project MM19 Variance | 0
Project MM19 Status | Live
Project MM19 Notes | Green lumber fallacy
Project MM20 | Lunar Radiation
Project MM20 CP | No
Project MM20 Original Baseline | 2086-12-31
Project MM20 Forecast - Actual | 2086-12-31
Project MM20 Variance | 0
Project MM20 Status | Live
Project MM20 Notes | Memento mori and amor fati
Project MM21 | Standard E
Project MM21 CP | Yes
Project MM21 Original Baseline | 2022-09-30
Project MM21 Forecast - Actual | 2022-09-30
Project MM21 Variance | 0
Project MM21 Status | Live
Project MM21 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM22 | Standard F
Project MM22 CP | Yes
Project MM22 Original Baseline | 2027-12-31
Project MM22 Forecast - Actual | 2027-12-31
Project MM22 Variance | 0
Project MM22 Status | Live
Project MM22 Notes | Memento mori and amor fati
Project MM23 | Standard G
Project MM23 CP | Yes
Project MM23 Original Baseline | 2027-12-31
Project MM23 Forecast - Actual | 2027-12-31
Project MM23 Variance | 0
Project MM23 Status | Live
Project MM23 Notes | The sea gets deeper the further you go into it
Project MM24 | Columbia Hypatia
Project MM24 CP | Yes
Project MM24 Original Baseline | 2017-03-02
Project MM24 Forecast - Actual | 2017-03-02
Project MM24 Variance | 0
Project MM24 Status | Complete
Project MM24 Notes | The sea gets deeper the further you go into it
Project MM25 | Astronauts Walk
Project MM25 CP | Yes
Project MM25 Original Baseline | 2016-01-26
Project MM25 Forecast - Actual | 2016-01-26
Project MM25 Variance | 0
Project MM25 Status | Complete
Project MM25 Notes | The sea gets deeper the further you go into it
Project MM26
Project MM26 CP
Project MM26 Original Baseline
Project MM26 Forecast - Actual
Project MM26 Variance
Project MM26 Status
Project MM26 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM27
Project MM27 CP
Project MM27 Original Baseline
Project MM27 Forecast - Actual
Project MM27 Variance
Project MM27 Status
Project MM27 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM28
Project MM28 CP
Project MM28 Original Baseline
Project MM28 Forecast - Actual
Project MM28 Variance
Project MM28 Status
Project MM28 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM29
Project MM29 CP
Project MM29 Original Baseline
Project MM29 Forecast - Actual
Project MM29 Variance
Project MM29 Status
Project MM29 Notes | The sea gets deeper the further you go into it
Project MM30
Project MM30 CP
Project MM30 Original Baseline
Project MM30 Forecast - Actual
Project MM30 Variance
Project MM30 Status
Project MM30 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM31
Project MM31 CP
Project MM31 Original Baseline
Project MM31 Forecast - Actual
Project MM31 Variance
Project MM31 Status
Project MM31 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM32
Project MM32 CP
Project MM32 Original Baseline
Project MM32 Forecast - Actual
Project MM32 Variance
Project MM32 Status
Project MM32 Notes | What you see if all there is
Project MM33
Project MM33 CP
Project MM33 Original Baseline
Project MM33 Forecast - Actual
Project MM33 Variance
Project MM33 Status
Project MM33 Notes | Memento mori and amor fati
Project MM34
Project MM34 CP
Project MM34 Original Baseline
Project MM34 Forecast - Actual
Project MM34 Variance
Project MM34 Status
Project MM34 Notes | Memento mori and amor fati
Project MM35
Project MM35 CP
Project MM35 Original Baseline
Project MM35 Forecast - Actual
Project MM35 Variance
Project MM35 Status
Project MM35 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM36
Project MM36 CP
Project MM36 Original Baseline
Project MM36 Forecast - Actual
Project MM36 Variance
Project MM36 Status
Project MM36 Notes | What you see if all there is
Project MM37
Project MM37 CP
Project MM37 Original Baseline
Project MM37 Forecast - Actual
Project MM37 Variance
Project MM37 Status
Project MM37 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM38
Project MM38 CP
Project MM38 Original Baseline
Project MM38 Forecast - Actual
Project MM38 Variance
Project MM38 Status
Project MM38 Notes | What you see if all there is
Project MM39
Project MM39 CP
Project MM39 Original Baseline
Project MM39 Forecast - Actual
Project MM39 Variance
Project MM39 Status
Project MM39 Notes | Memento mori and amor fati
Project MM40
Project MM40 CP
Project MM40 Original Baseline
Project MM40 Forecast - Actual
Project MM40 Variance
Project MM40 Status
Project MM40 Notes | The sea gets deeper the further you go into it
Project MM41
Project MM41 CP
Project MM41 Original Baseline
Project MM41 Forecast - Actual
Project MM41 Variance
Project MM41 Status
Project MM41 Notes | Memento mori and amor fati
Project MM42
Project MM42 CP
Project MM42 Original Baseline
Project MM42 Forecast - Actual
Project MM42 Variance
Project MM42 Status
Project MM42 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM43
Project MM43 CP
Project MM43 Original Baseline
Project MM43 Forecast - Actual
Project MM43 Variance
Project MM43 Status
Project MM43 Notes | The sea gets deeper the further you go into it
Project MM44
Project MM44 CP
Project MM44 Original Baseline
Project MM44 Forecast - Actual
Project MM44 Variance
Project MM44 Status
Project MM44 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM45
Project MM45 CP
Project MM45 Original Baseline
Project MM45 Forecast - Actual
Project MM45 Variance
Project MM45 Status
Project MM45 Notes | Green lumber fallacy
Project MM46
Project MM46 CP
Project MM46 Original Baseline
Project MM46 Forecast - Actual
Project MM46 Variance
Project MM46 Status
Project MM46 Notes | Memento mori and amor fati
Project MM47
Project MM47 CP
Project MM47 Original Baseline
Project MM47 Forecast - Actual
Project MM47 Variance
Project MM47 Status
Project MM47 Notes | Green lumber fallacy
Project MM48
Project MM48 CP
Project MM48 Original Baseline
Project MM48 Forecast - Actual
Project MM48 Variance
Project MM48 Status
Project MM48 Notes | Memento mori and amor fati
Project MM49
Project MM49 CP
Project MM49 Original Baseline
Project MM49 Forecast - Actual
Project MM49 Variance
Project MM49 Status
Project MM49 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM50
Project MM50 CP
Project MM50 Original Baseline
Project MM50 Forecast - Actual
Project MM50 Variance
Project MM50 Status
Project MM50 Notes | Memento mori and amor fati
Project MM51
Project MM51 CP
Project MM51 Original Baseline
Project MM51 Forecast - Actual
Project MM51 Variance
Project MM51 Status
Project MM51 Notes | What you see if all there is
Project MM52
Project MM52 CP
Project MM52 Original Baseline
Project MM52 Forecast - Actual
Project MM52 Variance
Project MM52 Status
Project MM52 Notes | What you see if all there is
Project MM53
Project MM53 CP
Project MM53 Original Baseline
Project MM53 Forecast - Actual
Project MM53 Variance
Project MM53 Status
Project MM53 Notes | Memento mori and amor fati
Project MM54
Project MM54 CP
Project MM54 Original Baseline
Project MM54 Forecast - Actual
Project MM54 Variance
Project MM54 Status
Project MM54 Notes | Green lumber fallacy
Project MM55
Project MM55 CP
Project MM55 Original Baseline
Project MM55 Forecast - Actual
Project MM55 Variance
Project MM55 Status
Project MM55 Notes | What you see if all there is
Project MM56
Project MM56 CP
Project MM56 Original Baseline
Project MM56 Forecast - Actual
Project MM56 Variance
Project MM56 Status
Project MM56 Notes | Green lumber fallacy
Project MM57
Project MM57 CP
Project MM57 Original Baseline
Project MM57 Forecast - Actual
Project MM57 Variance
Project MM57 Status
Project MM57 Notes | Green lumber fallacy
Project MM58
Project MM58 CP
Project MM58 Original Baseline
Project MM58 Forecast - Actual
Project MM58 Variance
Project MM58 Status
Project MM58 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM59
Project MM59 CP
Project MM59 Original Baseline
Project MM59 Forecast - Actual
Project MM59 Variance
Project MM59 Status
Project MM59 Notes | The sea gets deeper the further you go into it
Project MM60
Project MM60 CP
Project MM60 Original Baseline
Project MM60 Forecast - Actual
Project MM60 Variance
Project MM60 Status
Project MM60 Notes | The mind is not a vessel to be filled but a fire to be lighted
Project MM61
Project MM61 CP
Project MM61 Original Baseline
Project MM61 Forecast - Actual
Project MM61 Variance
Project MM61 Status
Project MM61 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM62
Project MM62 CP
Project MM62 Original Baseline
Project MM62 Forecast - Actual
Project MM62 Variance
Project MM62 Status
Project MM62 Notes | Memento mori and amor fati
Project MM63
Project MM63 CP
Project MM63 Original Baseline
Project MM63 Forecast - Actual
Project MM63 Variance
Project MM63 Status
Project MM63 Notes | Memento mori and amor fati
Project MM64
Project MM64 CP
Project MM64 Original Baseline
Project MM64 Forecast - Actual
Project MM64 Variance
Project MM64 Status
Project MM64 Notes | Green lumber fallacy
Project MM65
Project MM65 CP
Project MM65 Original Baseline
Project MM65 Forecast - Actual
Project MM65 Variance
Project MM65 Status
Project MM65 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days
Project MM66
Project MM66 CP
Project MM66 Original Baseline
Project MM66 Forecast - Actual
Project MM66 Variance
Project MM66 Status
Project MM66 Notes | The sea gets deeper the further you go into it
Project MM67
Project MM67 CP
Project MM67 Original Baseline
Project MM67 Forecast - Actual
Project MM67 Variance
Project MM67 Status
Project MM67 Notes | Memento mori and amor fati
Milestone Commentary | The 2010–11 Ashes series (known as the Vodafone Ashes Series for sponsorship reasons) was the 66th series of Test cricket matches played to contest The Ashes. The series was played in Australia as part of the England cricket team's tour of the country during the 2010–11 season. Five Tests were played from 25 November 2010 to 7 January 2011.[1] England won the series 3–1 and retained the Ashes, having won the previous series in 2009 by two Tests to one. As of 2019, it remains the most recent occasion that a visiting team has won an Ashes series.
SRO Schedule Confidence | Red
Project stage | Define
Project Stage if Other
Latest Treasury Approval Point (TAP) or equivalent | Strategic Outline Case
Version Number Of Document used to Source Figures (GMPP - TAP version Number) | 1
Business Case & Version No. | Strategic Outline Case 1
Date of TAP used to source figures | 2016-01-18
If no HMT Business Case please advise why?
Is your HMT Business case updated / approved annually by HMT or more frequently? | No
Does the HMT Businesss Case cover the full life of the project? | Yes
If not please provide explanation as to why
If not please advise how many years are covered
If not please advise how much cost is covered as a percentage
Are the baselines in this return from the most recent HMT Approved Business Case? | Yes
If not what is the source of baselines in this returns?
If not please give a reason why baselines
What is the source of all forecasts in this return? | nail
Please provide details of any formal arrangement with HMT regarding Business cases that are outside the classical model
Real or Nominal - Baseline | Nominal
Real or Nominal - Actual/Forecast | Nominal
Index Year
Deflator
Are you reporting the full costs of the project? | Yes
If no please provide reason why?
Does this project create income? | No
Who recieves the income?
Do you net the income with your costs in the GMPP return
Income Against which Cost category?
Income Baseline - Real or Nominal
Income Forecast - Real or Nominal
Income If real Index Year used?
Income If real Deflator used?
Are you reporting the full income of the project?
Income If no please provide reason why?
Does this project create monetised benefits? | Yes
Benefits Baseline - Real or Nominal | Real
Benefits Forecast - Real or Nominal | Real
Benefits If real Index Year used | 2010
Benefits If real Deflator used | 0.03
Are you reporting the full benefits of the project? | Yes
Benefits If no please provide reason why?
Source of Finance | Public
Other Finance type Description
Has this project applied cost uplifts using Optimism Bias? | No
Is this Optimism Bias included within the WLC? | No
Overall figure for Optimism Bias (£m) | 0
Does this project have allocated contingency? | Yes
Is this Continency amount included within the WLC? | Yes
Overall contingency (£m) | 398
NPV for all projects and NPV for programmes if available | 2952
Adjusted Benefits Cost Ratio (BCR) | 1.54
Benefits Map | Yes
Benefits Analysed | Yes
Benefits Realisation Plan | Yes
Initial Benefits Cost Ratio (BCR) | 0.78
VfM Category single entry | Medium
VfM Category lower range
VfM Category upper range
Present Value Cost (PVC) | 2831
Present Value Benefit (PVB) | 4364
Project Costs Narrative | screw
Cost comparison with last quarters cost narrative | wood
Cost comparison within this quarters cost narrative | screw
Total BL | 6091.81
Total Forecast | 6391.73
Pre 19-20 RDEL BL one off new costs | 0
Pre 19-20 RDEL BL recurring new costs | 0
Pre 19-20 RDEL BL recurring old costs | 0
Pre 19-20 RDEL BL Non Gov costs | 0
Pre 19-20 RDEL BL Total | 0
Pre 19-20 RDEL BL Income | 0
Pre-profile RDEL Forecast one off new costs | 0
Pre 19-20 RDEL Forecast recurring new costs | 0
Pre 19-20 RDEL Forecast recurring old costs | 0
Pre 19-20 RDEL Forecast Non Gov costs | 0
Pre-profile RDEL | 0
Pre 19-20 RDEL Forecast Income | 0
19-20 RDEL BL one off new costs | 0
19-20 RDEL BL recurring new costs | 0
19-20 RDEL BL recurring old costs | 0
19-20 RDEL BL Non Gov costs | 0
19-20 RDEL BL Total | 0
19-20 RDEL BL Income | 0
19-20 RDEL Forecast one off new costs | 0
19-20 RDEL Forecast recurring new costs | 0
19-20 RDEL Forecast recurring old costs | 0
19-20 RDEL Forecast Non Gov costs | 0
19-20 RDEL Forecast Total | 0
19-20 RDEL Forecast Income | 0
20-21 RDEL BL one off new costs | 0
20-21 RDEL BL recurring new costs | 0
20-21 RDEL BL recurring old costs | 0
20-21 RDEL BL Non Gov costs | 0
20-21 RDEL BL Total | 0
20-21 RDEL BL Income | 0
20-21 RDEL Forecast one off new costs | 0
20-21 RDEL Forecast recurring new costs | 0
20-21 RDEL Forecast recurring old costs | 0
20-21 RDEL Forecast Non Gov costs | 0
20-21 RDEL Forecast Total | 0
20-21 RDEL Forecast Income | 0
21-22 RDEL BL one off new costs | 0
21-22 RDEL BL recurring new costs | 0
21-22 RDEL BL recurring old costs | 0
21-22 RDEL BL Non Gov costs | 0
21-22 RDEL BL Total | 0
21-22 RDEL BL Income | 0
21-22 RDEL Forecast one off new costs | 0
21-22 RDEL Forecast recurring new costs | 0
21-22 RDEL Forecast recurring old costs | 0
21-22 RDEL Forecast Non Gov costs | 0
21-22 RDEL Forecast Total | 0
21-22 RDEL Forecast Income | 0
22-23 RDEL BL one off new costs | 0
22-23 RDEL BL recurring new costs | 0
22-23 RDEL BL recurring old costs | 0
22-23 RDEL BL Non Gov costs | 0
22-23 RDEL BL Total | 0
22-23 RDEL BL Income | 0
22-23 RDEL Forecast one off new costs | 0
22-23 RDEL Forecast recurring new costs | 0
22-23 RDEL Forecast recurring old costs | 0
22-23 RDEL Forecast Non Gov costs | 0
22-23 RDEL Forecast Total | 0
22-23 RDEL Forecast Income | 0
23-24 RDEL BL one off new costs | 0
23-24 RDEL BL recurring new costs | 0
23-24 RDEL BL recurring old costs | 0
23-24 RDEL BL Non Gov costs | 0
23-24 RDEL BL Total | 0
23-24 RDEL BL Income | 0
23-24 RDEL Forecast one off new costs | 0
23-24 RDEL Forecast recurring new costs | 0
23-24 RDEL Forecast recurring old costs | 0
23-24 RDEL Forecast Non Gov costs | 0
23-24 RDEL Forecast Total | 0
23-24 RDEL Forecast Income | 0
24-25 RDEL BL one off new costs | 0
24-25 RDEL BL recurring new costs | 0
24-25 RDEL BL recurring old costs | 0
24-25 RDEL BL Non Gov costs | 0
24-25 RDEL BL Total | 0
24-25 RDEL BL Income | 0
24-25 RDEL Forecast one off new costs | 0
24-25 RDEL Forecast recurring new costs | 0
24-25 RDEL Forecast recurring old costs | 0
24-25 RDEL Forecast Non Gov costs | 0
24-25 RDEL Forecast Total | 0
24-25 RDEL Forecast Income | 0
25-26 RDEL BL one off new costs | 0
25-26 RDEL BL recurring new costs | 0
25-26 RDEL BL recurring old costs | 0
25-26 RDEL BL Non Gov costs | 0
25-26 RDEL BL Total | 0
25-26 RDEL BL Income | 0
25-26 RDEL Forecast one off new costs | 0
25-26 RDEL Forecast recurring new costs | 0
25-26 RDEL Forecast recurring old costs | 0
25-26 RDEL Forecast Non Gov costs | 0
25-26 RDEL Forecast Total | 0
25-26 RDEL Forecast Income | 0
26-27 RDEL BL one off new costs | 0
26-27 RDEL BL recurring new costs | 0
26-27 RDEL BL recurring old costs | 0
26-27 RDEL BL Non Gov costs | 0
26-27 RDEL BL Total | 0
26-27 RDEL BL Income | 0
26-27 RDEL Forecast one off new costs | 0
26-27 RDEL Forecast recurring new costs | 0
26-27 RDEL Forecast recurring old costs | 0
26-27 RDEL Forecast Non Gov costs | 0
26-27 RDEL Forecast Total | 0
26-27 RDEL Forecast Income | 0
27-28 RDEL BL one off new costs | 0
27-28 RDEL BL recurring new costs | 0
27-28 RDEL BL recurring old costs | 0
27-28 RDEL BL Non Gov costs | 0
27-28 RDEL BL Total | 0
27-28 RDEL BL Income | 0
27-28 RDEL Forecast one off new costs | 0
27-28 RDEL Forecast recurring new costs | 0
27-28 RDEL Forecast recurring old costs | 0
27-28 RDEL Forecast Non Gov costs | 0
27-28 RDEL Forecast Total | 0
27-28 RDEL Forecast Income | 0
28-29 RDEL BL one off new costs | 0
28-29 RDEL BL recurring new costs | 0
28-29 RDEL BL recurring old costs | 0
28-29 RDEL BL Non Gov costs | 0
28-29 RDEL BL Total | 0
28-29 RDEL BL Income | 0
28-29 RDEL Forecast one off new costs | 0
28-29 RDEL Forecast recurring new costs | 0
28-29 RDEL Forecast recurring old costs | 0
28-29 RDEL Forecast Non Gov costs | 0
28-29 RDEL Forecast Total | 0
28-29 RDEL Forecast Income | 0
Unprofiled RDEL BL one off new costs | 0
Unprofiled RDEL BL recurring new costs | 0
Unprofiled RDEL BL recurring old costs | 0
Unprofiled RDEL BL Non Gov costs | 0
Unprofiled RDEL BL Total | 0
Unprofiled RDEL BL Income | 0
Unprofiled RDEL Forecast one off new costs | 0
Unprofiled RDEL Forecast recurring new costs | 0
Unprofiled RDEL Forecast recurring old costs | 0
Unprofiled RDEL Forecast Non Gov costs | 0
Unprofiled RDEL Forecast Total | 0
Unprofiled RDEL Forecast Income | 0
Total RDEL BL one off new costs | 0
Total RDEL BL recurring new costs | 0
Total RDEL BL recurring old costs | 0
Total RDEL BL Non Gov costs | 0
Total RDEL BL Total | 0
Total RDEL BL Income | 0
Total RDEL Forecast one off new costs | 0
Total RDEL Forecast recurring new costs | 0
Total RDEL Forecast recurring old costs | 0
Total RDEL Forecast Non Gov costs | 0
Total RDEL Forecast Total | 0
Total RDEL Forecast Income | 0
Year RDEL spend stops | No Spend
Pre 19-20 CDEL BL one off new costs | 188.2
Pre 19-20 CDEL BL recurring new costs | 0
Pre 19-20 CDEL BL recurring old costs | 0
Pre 19-20 BL Non-Gov | 0
Pre 19-20 CDEL BL WLC | 188.2
Pre 19-20 BL Income both Revenue and Capital | 0
Pre-profile CDEL Forecast one off new costs | 188.2
Pre 19-20 CDEL Forecast recurring new costs | 0
Pre 19-20 CDEL Forecast recurring old costs | 0
Pre-profile Forecast Non-Gov | 0
Pre-profile CDEL WLC | 188.2
Pre 19-20 Actual Income both Revenue and Capital | 0
19-20 CDEL BL one off new costs | 177.49
19-20 CDEL BL recurring new costs | 0
19-20 CDEL BL recurring old costs | 0
19-20 BL Non-Gov | 0
19-20 CDEL BL WLC | 177.49
19-20 BL Income both Revenue and Capital | 0
19-20 CDEL Forecast one off new costs | 177.49
19-20 CDEL Forecast recurring new costs | 0
19-20 CDEL Forecast recurring old costs | 0
19-20 Forecast Non-Gov | 0
19-20 CDEL Forecast Total WLC | 177.49
19-20 Forecast - Income both Revenue and Capital | 0
20-21 CDEL BL one off new costs | 245
20-21 CDEL BL recurring new costs | 0
20-21 CDEL BL recurring old costs | 0
20-21 BL Non-Gov | 0
20-21 CDEL BL WLC | 245
20-21 BL Income both Revenue and Capital | 0
20-21 CDEL Forecast one off new costs | 245
20-21 CDEL Forecast recurring new costs | 0
20-21 CDEL Forecast recurring old costs | 0
20-21 Forecast Non-Gov | 0
20-21 CDEL Forecast Total WLC | 245
20-21 Forecast - Income both Revenue and Capital | 0
21-22 CDEL BL one off new costs | 411.3
21-22 CDEL BL recurring new costs | 0
21-22 CDEL BL recurring old costs | 0
21-22 BL Non-Gov | 0
21-22 CDEL BL WLC | 411.3
21-22 BL - Income both Revenue and Capital | 0
21-22 CDEL Forecast one off new costs | 411.3
21-22 CDEL Forecast recurring new costs | 0
21-22 CDEL Forecast recurring old costs | 0
21-22 Forecast Non-Gov | 0
21-22 CDEL Forecast Total WLC | 411.3
21-22 Forecast - Income both Revenue and Capital | 0
22-23 CDEL BL one off new costs | 443.2
22-23 CDEL BL recurring new costs | 0
22-23 CDEL BL recurring old costs | 0
22-23 BL Non-Gov | 0
22-23 CDEL BL WLC | 443.2
22-23 BL Income both Revenue and Capital | 0
22-23 CDEL Forecast one off new costs | 443.2
22-23 CDEL Forecast recurring new costs | 0
22-23 CDEL Forecast recurring old costs | 0
22-23 Forecast Non-Gov | 0
22-23 CDEL Forecast Total WLC | 443.2
22-23 Forecast - Income both Revenue and Capital | 0
23-24 CDEL BL one off new costs | 728.1
23-24 CDEL BL recurring new costs | 0
23-24 CDEL BL recurring old costs | 0
23-24 BL Non-Gov | 0
23-24 CDEL BL WLC | 728.1
23-24 BL Income both Revenue and Capital | 0
23-24 CDEL Forecast one off new costs | 728.1
23-24 CDEL Forecast recurring new costs | 0
23-24 CDEL Forecast recurring old costs | 0
23-24 Forecast Non-Gov | 0
23-24 CDEL Forecast Total WLC | 728.1
23-24 Forecast - Income both Revenue and Capital | 0
24-25 CDEL BL one off new costs | 1046.6
24-25 CDEL BL recurring new costs | 0
24-25 CDEL BL recurring old costs | 0
24-25 BL Non-Gov | 0
24-25 CDEL BL WLC | 1046.6
24-25 BL Income both Revenue and Capital | 0
24-25 CDEL Forecast one off new costs | 1046.6
24-25 CDEL Forecast recurring new costs | 0
24-25 CDEL Forecast recurring old costs | 0
24-25 Forecast Non-Gov | 0
24-25 CDEL Forecast Total WLC | 1046.6
24-25 Forecast - Income both Revenue and Capital | 0
25-26 CDEL BL one off new costs | 1141.08
25-26 CDEL BL recurring new costs | 0
25-26 CDEL BL recurring old costs | 0
25-26 BL Non-Gov | 0
25-26 CDEL BL WLC | 1141.08
25-26 BL Income both Revenue and Capital | 0
25-26 CDEL Forecast one off new costs | 1441
25-26 CDEL Forecast recurring new costs | 0
25-26 CDEL Forecast recurring old costs | 0
25-26 Forecast Non-Gov | 0
25-26 CDEL Forecast Total WLC | 1441
25-26 Forecast - Income both Revenue and Capital | 0
26-27 CDEL BL one off new costs | 1315
26-27 CDEL BL recurring new costs | 0
26-27 CDEL BL recurring old costs | 0
26-27 BL Non-Gov | 0
26-27 CDEL BL WLC | 1315
26-27 BL Income both Revenue and Capital | 0
26-27 CDEL Forecast one off new costs | 1315
26-27 CDEL Forecast recurring new costs | 0
26-27 CDEL Forecast recurring old costs | 0
26-27 Forecast Non-Gov | 0
26-27 CDEL Forecast Total WLC | 1315
26-27 Forecast - Income both Revenue and Capital | 0
27-28 CDEL BL one off new costs | 395.84
27-28 CDEL BL recurring new costs | 0
27-28 CDEL BL recurring old costs | 0
27-28 BL Non-Gov | 0
27-28 CDEL BL WLC | 395.84
27-28 BL Income both Revenue and Capital | 0
27-28 CDEL Forecast one off new costs | 395.84
27-28 CDEL Forecast recurring new costs | 0
27-28 CDEL Forecast recurring old costs | 0
27-28 Forecast Non-Gov | 0
27-28 CDEL Forecast Total WLC | 395.84
27-28 Forecast - Income both Revenue and Capital | 0
28-29 CDEL BL one off new costs | 0
28-29 CDEL BL recurring new costs | 0
28-29 CDEL BL recurring old costs | 0
28-29 BL Non-Gov | 0
28-29 CDEL BL WLC | 0
28-29 BL Income both Revenue and Capital | 0
28-29 CDEL Forecast one off new costs | 0
28-29 CDEL Forecast recurring new costs | 0
28-29 CDEL Forecast recurring old costs | 0
28-29 Forecast Non-Gov | 0
28-29 CDEL Forecast Total WLC | 0
28-29 Forecast - Income both Revenue and Capital | 0
Unprofiled CDEL BL one off new costs | 0
Unprofiled CDEL BL recurring new costs | 0
Unprofiled CDEL BL recurring old costs | 0
Unprofiled BL Non-Gov | 0
Unprofiled CDEL BL WLC | 0
Unprofiled BL Income | 0
Unprofiled CDEL Forecast one off new costs | 0
Unprofiled CDEL Forecast recurring new costs | 0
Unprofiled CDEL Forecast recurring old costs | 0
Unprofiled Forecast Non-Gov | 0
Unprofiled CDEL Forecast Total WLC | 0
Unprofiled Forecast - Income both Revenue and Capital | 0
Total CDEL BL one off new costs | 6091.81
Total CDEL BL recurring new costs | 0
Total CDEL BL recurring old costs | 0
Non-Gov Total Budget/BL | 0
Total CDEL BL WLC | 6091.81
Total Baseline - Income both Revenue and Capital | 0
Total CDEL Forecast one off new costs | 6391.73
Total CDEL Forecast recurring new costs | 0
Total CDEL Forecast recurring old costs | 0
Non-Gov Total Forecast | 0
Total CDEL Forecast Total WLC | 6391.73
Total Forecast - Income both Revenue and Capital | 0
Year CDEL spend stops | 2026/2027
SRO Finance confidence | Amber
Benefits Narrative | Datamaps allows for data to be collected from multiple users using pre-defined forms, built out of Excel spreadsheets. The form can be as complex or as simple as you like - Datamaps does the hard work of collecting the data into one place for onward processing or analysis, whilst ensuring that the data is valid according to expectations. Datamaps acknowledges that in the office environment, we use Excel for everything, but using it to collect data requires help - which is where Datamaps excels.
Ben comparison with last quarters cost - narrative | nail
Ben comparison within this quarters cost - narrative | What you see if all there is
Narrative on any project Non-Monetised benefits | wood
If benefits profile (by years) not provided please provide reason and date for when they will be | What you see if all there is
Pre 19-20 BEN Baseline - Gov. Cashable | 0
Pre 19-20 BEN Baseline - Gov. Non-Cashable | 0
Pre 19-20 BEN Baseline - Economic (inc Private Partner) | 0
Pre 19-20 BEN Baseline - Disbenefit UK Economic | 0
Pre 19-20 BEN Baseline - Total Monetised Benefits | 0
Pre-profile BEN Forecast Gov Cashable | 0
Pre-profile BEN Forecast Gov Non-Cashable | 0
Pre-profile BEN Forecast - Economic (inc Private Partner) | 0
Pre-profile BEN Forecast - Disbenefit UK Economic | 0
Pre-profile BEN Total | 0
19-20 BEN Baseline - Gov. Cashable | 0
19-20 BEN Baseline - Gov. Non-Cashable | 0
19-20 BEN Baseline - Economic (inc Private Partner) | 0
19-20 BEN Baseline - Disbenefit UK Economic | 0
19-20 BEN Baseline - Total Monetised Benefits | 0
19-20 BEN Forecast - Gov. Cashable | 0
19-20 BEN Forecast - Gov. Non-Cashable | 0
19-20 BEN Forecast - Economic (inc Private Partner) | 0
19-20 BEN Forecast - Disbenefit UK Economic | 0
19-20 BEN Forecast - Total Monetised Benefits | 0
20-21 BEN Baseline - Gov. Cashable | 0
20-21 BEN Baseline - Gov. Non-Cashable | 0
20-21 BEN Baseline - Economic (inc Private Partner) | 0
20-21 BEN Baseline - Disbenefit UK Economic | 0
20-21 BEN Baseline - Total Monetised Benefits | 0
20-21 BEN Forecast - Gov. Cashable | 0
20-21 BEN Forecast - Gov. Non-Cashable | 0
20-21 BEN Forecast - Economic (inc Private Partner) | 0
20-21 BEN Forecast - Disbenefit UK Economic | 0
20-21 BEN Forecast - Total Monetised Benefits | 0
21-22 BEN Baseline - Gov. Cashable | 0
21-22 BEN Baseline - Gov. Non-Cashable | 0
21-22 BEN Baseline - Economic (inc Private Partner) | 0
21-22 BEN Baseline - Disbenefit UK Economic | 0
21-22 BEN Baseline - Total Monetised Benefits | 0
21-22 BEN Forecast - Gov. Cashable | 0
21-22 BEN Forecast - Gov. Non-Cashable | 0
21-22 BEN Forecast - Economic (inc Private Partner) | 0
21-22 BEN Forecast - Disbenefit UK Economic | 0
21-22 BEN Forecast - Total Monetised Benefits | 0
22-23 BEN Baseline - Gov. Cashable | 0
22-23 BEN Baseline - Gov. Non-Cashable | 0
22-23 BEN Baseline - Economic (inc Private Partner) | 0
22-23 BEN Baseline - Disbenefit UK Economic | -50
22-23 BEN Baseline - Total Monetised Benefits | -50
22-23 BEN Forecast - Gov. Cashable | 0
22-23 BEN Forecast - Gov. Non-Cashable | 0
22-23 BEN Forecast - Economic (inc Private Partner) | 0
22-23 BEN Forecast - Disbenefit UK Economic | -50
22-23 BEN Forecast - Total Monetised Benefits | -50
23-24 BEN Baseline - Gov. Cashable | 0
23-24 BEN Baseline - Gov. Non-Cashable | 0
23-24 BEN Baseline - Economic (inc Private Partner) | 0
23-24 BEN Baseline - Disbenefit UK Economic | -50
23-24 BEN Baseline - Total Monetised Benefits | -50
23-24 BEN Forecast - Gov. Cashable | 0
23-24 BEN Forecast - Gov. Non-Cashable | 0
23-24 BEN Forecast - Economic (inc Private Partner) | 0
23-24 BEN Forecast - Disbenefit UK Economic | -50
23-24 BEN Forecast - Total Monetised Benefits | -50
24-25 BEN Baseline - Gov. Cashable | 0
24-25 BEN Baseline - Gov. Non-Cashable | 0
24-25 BEN Baseline - Economic (inc Private Partner) | 0
24-25 BEN Baseline - Disbenefit UK Economic | -50
24-25 BEN Baseline - Total Monetised Benefits | -50
24-25 BEN Forecast - Gov. Cashable | 0
24-25 BEN Forecast - Gov. Non-Cashable | 0
24-25 BEN Forecast - Economic (inc Private Partner) | 0
24-25 BEN Forecast - Disbenefit UK Economic | -50
24-25 BEN Forecast - Total Monetised Benefits | -50
25-26 BEN Baseline - Gov. Cashable | 0
25-26 BEN Baseline - Gov. Non-Cashable | 0
25-26 BEN Baseline - Economic (inc Private Partner) | 0
25-26 BEN Baseline - Disbenefit UK Economic | -50
25-26 BEN Baseline - Total Monetised Benefits | -50
25-26 BEN Forecast - Gov. Cashable | 0
25-26 BEN Forecast - Gov. Non-Cashable | 0
25-26 BEN Forecast - Economic (inc Private Partner) | 0
25-26 BEN Forecast - Disbenefit UK Economic | -50
25-26 BEN Forecast - Total Monetised Benefits | -50
26-27 BEN Baseline - Gov. Cashable | 0
26-27 BEN Baseline - Gov. Non-Cashable | 0
26-27 BEN Baseline - Economic (inc Private Partner) | 0
26-27 BEN Baseline - Disbenefit UK Economic | 0
26-27 BEN Baseline - Total Monetised Benefits | 0
26-27 BEN Forecast - Gov. Cashable | 0
26-27 BEN Forecast - Gov. Non-Cashable | 0
26-27 BEN Forecast - Economic (inc Private Partner) | 0
26-27 BEN Forecast - Disbenefit UK Economic | 0
26-27 BEN Forecast - Total Monetised Benefits | 0
27-28 BEN Baseline - Gov. Cashable | 0
27-28 BEN Baseline - Gov. Non-Cashable | 0
27-28 BEN Baseline - Economic (inc Private Partner) | 0
27-28 BEN Baseline - Disbenefit UK Economic | 0
27-28 BEN Baseline - Total Monetised Benefits | 0
27-28 BEN Forecast - Gov. Cashable | 0
27-28 BEN Forecast - Gov. Non-Cashable | 0
27-28 BEN Forecast - Economic (inc Private Partner) | 0
27-28 BEN Forecast - Disbenefit UK Economic | 0
27-28 BEN Forecast - Total Monetised Benefits | 0
28-29 BEN Baseline - Gov. Cashable | 0
28-29 BEN Baseline - Gov. Non-Cashable | 0
28-29 BEN Baseline - Economic (inc Private Partner) | 0
28-29 BEN Baseline - Disbenefit UK Economic | 0
28-29 BEN Baseline - Total Monetised Benefits | 0
28-29 BEN Forecast - Gov. Cashable | 0
28-29 BEN Forecast - Gov. Non-Cashable | 0
28-29 BEN Forecast - Economic (inc Private Partner) | 0
28-29 BEN Forecast - Disbenefit UK Economic | 0
28-29 BEN Forecast - Total Monetised Benefits | 0
Unprofiled Remainder BEN Baseline - Gov. Cashable | 0
Unprofiled Remainder BEN Baseline - Gov. Non-Cashable | 0
Unprofiled Remainder BEN Baseline - Economic (inc Private Partner) | 4564
Unprofiled Remainder BEN Baseline - Disbenefit UK Economic | 0
Unprofiled Remainder BEN Baseline - Total Monetised Benefits | 4564
Unprofiled Remainder BEN Forecast - Gov. Cashable | 0
Unprofiled Remainder BEN Forecast - Gov. Non-Cashable | 0
Unprofiled Remainder BEN Forecast - Economic (inc Private Partner) | 4564
Unprofiled Remainder BEN Forecast - Disbenefit UK Economic | 0
Unprofiled Remainder BEN Forecast - Total Monetised Benefits | 4564
Total BEN Baseline - Gov. Cashable | 0
Total BEN Baseline - Gov. Non-Cashable | 0
Total BEN Baseline - Economic (inc Private Partner) | 4564
Total BEN Baseline - Disbenefit UK Economic | -200
Total BEN Baseline - Total Monetised Benefits | 4364
Total BEN Forecast - Gov. Cashable | 0
Total BEN Forecast - Gov. Non-Cashable | 0
Total BEN Forecast - Economic (inc Private Partner) | 4564
Total BEN Forecast - Disbenefit UK Economic | -200
Total BEN Forecast - Total Monetised Benefits | 4364
Year BEN spend stops | 2085/2086
No Deductions - Net Benefits Provided | No
Deduct RDEL One Off New Costs? | No
Deduct CDEL one off New Costs? | No
Deduct RDEL Recurring New Costs? | No
Deduct CDEL Recurring New Costs? | No
Deduct RDEL Recurring Old Costs? | No
Deduct CDEL Recurring Old Costs? | No
No Monetised Benefits / Initial Business Case Being Prepared | No
No Deductions - Net Benefits Provided stored | No
Deduct RDEL One Off New Costs? Stored | No
Deduct CDEL one off New Costs? Stored | No
Deduct RDEL Recurring New Costs? Stored | No
Deduct CDEL Recurring New Costs? Stored | No
Deduct RDEL Recurring Old Costs? Stored | No
Deduct CDEL Recurring Old Costs? Stored | No
No Monetised Benefits / Initial Business Case Being Prepared Stored | No
SRO Benefits RAG | Amber
Last time at BICC | 2019-12-09
Next at BICC | 2020-06-01