## Constructed BICC Data Master
Project/Programme Name | Sea of Tranquility | Apollo 11 | Apollo 13 | Falcon 9 | Columbia
Approval MM1 | Standard B | Standard B | Standard B | Standard B | Standard C
Approval MM1 Gov Type | plastic | nail | wood | hammer | screw
Approval MM1 Ver No | 1 |  | SOBC | 1.6 | 1
Approval MM1 Original Baseline | 2013-10-24 | 2019-01-31 | 2006-11-01 | 2016-05-30 | 2013-07-04
Approval MM1 Forecast / Actual | 2013-10-24 | 2019-07-18 | 2006-11-01 | 2016-01-18 | 2013-07-04
Approval MM1 Variance | 0 |  | 0 | -133 | 0
Approval MM1 Status | Complete |  | Complete | Complete | Superceded
Approval MM1 Notes | Green lumber fallacy | What you see if all there is | The mind is not a vessel to be filled but a fire to be lighted | The mind is not a vessel to be filled but a fire to be lighted | Green lumber fallacy
Assurance MM1 | Oxygen Module | Oxygen Magnetic | Space Command | Gemini Sea | Tranquility Collins
Assurance MM1 LoD | nail | wood | wood | nail | hammer
Assurance MM1 Original Baseline | 2016-06-30 |  | 2006-12-30 | 2028-03-31 | 2017-01-18
Assurance MM1 Forecast - Actual | 2016-06-28 |  | 2006-12-30 | 2027-04-01 | 2017-01-18
Assurance MM1 Variance | -2 |  | 0 | -365 | 0
Assurance MM1 Status | Complete |  | Complete | Live | Complete
Assurance MM1 Notes | Memento mori and amor fati | The sea gets deeper the further you go into it | Memento mori and amor fati | Green lumber fallacy | The mind is not a vessel to be filled but a fire to be lighted
Assurance MM1 DCA
Project MM18 | Standard A | Standard A | Standard A | Standard A | Standard A
Project MM18 CP | Yes |  | No | Yes | No
Project MM18 Original Baseline | 2012-09-01 |  | 2005-06-01 | 2014-05-30 | 2012-07-16
Project MM18 Forecast - Actual | 2012-09-01 | 2013-10-01 | 2005-06-01 | 2014-05-30 | 2012-07-16
Project MM18 Variance | 0 |  | 0 | 0 | 0
Project MM18 Status | Complete |  | Complete | Complete | Complete
Project MM18 Notes | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | Don't you know an apparition is just a cheap date. What have you been drinking these days | What you see if all there is | Memento mori and amor fati
DFT ID Number | A1 | B2 | B3 | C4 | D5
DfT Group |  | HSMRPG