## Constructed BICC Data Master
Project/Programme Name | Apollo 13 | Falcon 9 | Columbia
Project stage | Delivery | Define | Delivery
Project Stage if Other
Latest Treasury Approval Point (TAP) or equivalent | Full Business Case | Strategic Outline Case | Full Business Case
Version Number Of Document used to Source Figures (GMPP - TAP version Number) | Full Business Case | Strategic Outline Case | Full Business Case (SW Route Capacity Programme included rolling stock and infrastructure intervensions). As refreshed in January 2018.
Business Case & Version No. | Full Business Case Full Business Case | Strategic Outline Case Strategic Outline Case | Full Business Case Full Business Case (SW Route Capacity Programme included rolling stock and infrastructure intervensions). As refreshed in January 2018.
Date of TAP used to source figures | 2011-11-28 | 2016-01-18 | 2014-08-01
If no HMT Business Case, please advise why?
Is your HMT Business case updated / approved annually by HMT, or more frequently? | No | No | Yes
Does the HMT Businesss Case cover the full life of the project? | Yes | Yes | Yes
If not, please provide explanation as to why |  |  | n/a
If not, please advise how many years are covered |  |  | n/a
If not, please advise how much cost is covered, as a percentage |  |  | n/a
Are the baselines in this return from the most recent HMT Approved Business Case? | Yes | Yes | Yes
If not, what is the source of baselines in this returns?
If not, please give a reason why baselines
What is the source of all forecasts in this return? | The sea gets deeper the further you go into it | Don't you know an apparition is just a cheap date. What have you been drinking these days | nail | Green lumber fallacy
Please provide details of any formal arrangement with HMT regarding Business cases, that are outside the classical model
Real or Nominal - Baseline | Nominal | Nominal | Nominal
Real or Nominal - Actual/Forecast | Nominal | Nominal | Nominal
Index Year
Deflator
Are you reporting the full costs of the project? | Yes | Yes | Yes
If no, please provide reason why?
Does this project create income? | No | Yes | Yes
Who recieves the income? |  | HMT | Government
Do you net the income with your costs in the GMPP return |  | No | No
Income Against which Cost category? |  | RDEL New Recurring costs | No
Income Baseline - Real or Nominal |  | Nominal | Nominal
Income Forecast - Real or Nominal |  | Nominal | Nominal
Income If real, Index Year used?
Income If real, Deflator used?
Are you reporting the full income of the project? |  | Yes | No
Income If no, please provide reason why? |  |  | Realised thorough franchise
Does this project create monetised benefits? | Yes | Yes | No
Benefits Baseline - Real or Nominal | Nominal | Real
Benefits Forecast - Real or Nominal | Nominal | Real
Benefits If real, Index Year used? |  | 2010
Benefits If real, Deflator used?
Are you reporting the full benefits of the project? | Yes | Yes
Benefits If no, please provide reason why?
Source of Finance | PFI | Public | Public
Other Finance type Description |  | N/A | all below tbc next quarter
Optimism Bias Percentage Used in Cost Baselines |  | 0
Overall figure for Optimism Bias (£m) |  | 0
Built in contingency (% of Whole Life Cost) |  | 0.11
Overall contingency (£m) |  | 609
NPV for all projects and NPV for programmes if available | 1985 | 2952
Internal Rate of Return (IRR) |  | N/A
Adjusted Benefits Cost Ratio (BCR) | 2.3 | 1.52 | 0.38
Total Budget/BL | 6576.85 | 4648.8 | 747.7
Total Forecast | 6460.63 | 5692.07 | 682.16
Pre 18-19 RDEL BL one off new costs | 73.25 | 0 | 63.06
Pre 18-19 RDEL BL recurring new costs | 0 | 0 | 0
Pre 18-19 RDEL BL recurring old costs | 0 | 0 | 0
Pre 18-19 RDEL BL Non Gov costs | 0 | 0 | 0
Pre 18-19 RDEL BL Total | 73.25 | 0 | 63.06
Pre 18-19 RDEL BL Income | 0 | 0 | 0
Pre 18-19 RDEL Forecast one off new costs | 62.07 | 0 | 63.02
Pre 18-19 RDEL Forecast recurring new costs | 0 | 0 | 0
Pre 18-19 RDEL Forecast recurring old costs | 0 | 0 | 0
Pre 18-19 RDEL Forecast Non Gov costs | 0 | 0 | 0
Pre 18-19 RDEL Forecast Total | 62.07 | 0 | 63.02
Pre 18-19 RDEL Forecast Income | 0 | 0 | 0
18-19 RDEL BL one off new costs | 24.1 | 0 | 36.22
18-19 RDEL BL recurring new costs | 0 | 0 | 0
18-19 RDEL BL recurring old costs | 0 | 0 | 0
18-19 RDEL BL Non Gov costs | 0 | 0 | 0
18 -19 RDEL BL Total | 24.1 | 0 | 36.22
18-19 RDEL BL Income | 0 | 0 | 0
18-19 RDEL Forecast one off new costs | 1.08 | 0 | 36.22
18-19 RDEL Forecast recurring new costs | 0 | 0 | 0
18-19 RDEL Forecast recurring old costs | 0 | 0 | 0
18-19 RDEL Forecast Non Gov costs | 0 | 0 | 0
18-19 RDEL Forecast Total | 1.08 | 0 | 36.22
18-19 RDEL Forecast Income | 0 | 0 | 0
19-20 RDEL BL one off new costs | 24.7 | 0 | 33.42
19-20 RDEL BL recurring new costs | 0 | 0 | 0
19-20 RDEL BL recurring old costs | 0 | 0 | 0
19-20 RDEL BL Non Gov costs | 0 | 0 | 0
19-20 RDEL BL Total | 24.7 | 0 | 33.42
19-20 RDEL BL Income | 0 | 0 | 0
19-20 RDEL Forecast one off new costs | 2 | 0 | 33.42
19-20 RDEL Forecast recurring new costs | 0 | 0 | 0
19-20 RDEL Forecast recurring old costs | 0 | 0 | 0
19-20 RDEL Forecast Non Gov costs | 0 | 0 | 0
19-20 RDEL Forecast Total | 2 | 0 | 33.42
19-20 RDEL Forecast Income | 0 | 0 | 0
20-21 RDEL BL one off new costs | 25.3 | 0 | 0
20-21 RDEL BL recurring new costs | 0 | 0 | 0
20-21 RDEL BL recurring old costs | 0 | 0 | 0
20-21 RDEL BL Non Gov costs | 0 | 0 | 0
20-21 RDEL BL Total | 25.3 | 0 | 0
20-21 RDEL BL Income | 0 | 0 | 0
20-21 RDEL Forecast one off new costs | 1.5 | 0 | 0
20-21 RDEL Forecast recurring new costs | 0 | 0 | 0
20-21 RDEL Forecast recurring old costs | 0 | 0 | 0
20-21 RDEL Forecast Non Gov costs | 0 | 0 | 0
20-21 RDEL Forecast Total | 1.5 | 0 | 0
20-21 RDEL Forecast Income | 0 | 0 | 0
21-22 RDEL BL one off new costs | 0 | 0 | 0
21-22 RDEL BL recurring new costs | 0 | 0 | 0
21-22 RDEL BL recurring old costs | 0 | 0 | 0
21-2 RDEL BL Non Gov costs | 0 | 0 | 0
21-22 RDEL BL Total | 0 | 0 | 0
21-22 RDEL BL Income | 0 | 0 | 0
21-22 RDEL Forecast one off new costs | 0 | 0 | 0
21-22 RDEL Forecast recurring new costs | 0 | 0 | 0
21-22 RDEL Forecast recurring old costs | 0 | 0 | 0
21-22 RDEL Forecast Non Gov costs | 0 | 0 | 0
21-22 RDEL Forecast Total | 0 | 0 | 0
21-22 RDEL Forecast Income | 0 | 0 | 0
22-23 RDEL BL one off new costs | 0 | 0 | 0
22-23 RDEL BL recurring new costs | 0 | 0 | 0
22-23 RDEL BL recurring old costs | 0 | 0 | 0
22-23 RDEL BL Non Gov costs | 0 | 0 | 0
22-23 RDEL BL Total | 0 | 0 | 0
22-23 RDEL BL Income | 0 | 0 | 0
22-23 RDEL Forecast one off new costs | 0 | 0 | 0
22-23 RDEL Forecast recurring new costs | 0 | 0 | 0
22-23 RDEL Forecast recurring old costs | 0 | 0 | 0
22-23 RDEL Forecast Non Gov costs | 0 | 0 | 0
22-23 RDEL Forecast Total | 0 | 0 | 0
22-23 RDEL Forecast Income | 0 | 0 | 0
23-24 RDEL BL one off new costs | 0 | 0 | 0
23-24 RDEL BL recurring new costs | 0 | 0 | 0
23-24 RDEL BL recurring old costs | 0 | 0 | 0
23-24 RDEL BL Non Gov costs | 0 | 0 | 0
23-24 RDEL BL Total | 0 | 0 | 0
23-24 RDEL BL Income | 0 | 0 | 0
23-24 RDEL Forecast one off new costs | 0 | 0 | 0
23-24 RDEL Forecast recurring new costs | 0 | 0 | 0
23-24 RDEL Forecast recurring old costs | 0 | 0 | 0
23-24 RDEL Forecast Non Gov costs | 0 | 0 | 0
23-24 RDEL Forecast Total | 0 | 0 | 0
23-24 RDEL Forecast Income | 0 | 0 | 0
24-25 RDEL BL one off new costs | 0 | 0 | 0
24-25 RDEL BL recurring new costs | 0 | 0 | 0
24-25 RDEL BL recurring old costs | 0 | 0 | 0
24-25 RDEL BL Non Gov costs | 0 | 0 | 0
24-25 RDEL BL Total | 0 | 0 | 0
24-25 RDEL BL Income | 0 | 0 | 0
24-25 RDEL Forecast one off new costs | 0 | 0 | 0
24-25 RDEL Forecast recurring new costs | 0 | 0 | 0
24-25 RDEL Forecast recurring old costs | 0 | 0 | 0
24-25 RDEL Forecast Non Gov costs | 0 | 0 | 0
24-25 RDEL Forecast Total | 0 | 0 | 0
24-25 RDEL Forecast Income | 0 | 0 | 0
25-26 RDEL BL one off new costs | 0 | 0 | 0
25-26 RDEL BL recurring new costs | 0 | 0 | 0
25-26 RDEL BL recurring old costs | 0 | 0 | 0
25-26 RDEL BL Non Gov costs | 0 | 0 | 0
25-26 RDEL BL Total | 0 | 0 | 0
25-26 RDEL BL Income | 0 | 0 | 0
25-26 RDEL Forecast one off new costs | 0 | 0 | 0
25-26 RDEL Forecast recurring new costs | 0 | 0 | 0
25-26 RDEL Forecast recurring old costs | 0 | 0 | 0
25-26 RDEL Forecast Non Gov costs | 0 | 0 | 0
25-26 RDEL Forecast Total | 0 | 0 | 0
25-26 RDEL Forecast Income | 0 | 0 | 0
26-27 RDEL BL one off new costs | 0 | 0 | 0
26-27 RDEL BL recurring new costs | 0 | 0 | 0
26-27 RDEL BL recurring old costs | 0 | 0 | 0
26-27 RDEL BL Non Gov costs | 0 | 0 | 0
26-27 RDEL BL Total | 0 | 0 | 0
26-27 RDEL BL Income | 0 | 0 | 0
26-27 RDEL Forecast one off new costs | 0 | 0 | 0
26-27 RDEL Forecast recurring new costs | 0 | 0 | 0
26-27 RDEL Forecast recurring old costs | 0 | 0 | 0
26-27 RDEL Forecast Non Gov costs | 0 | 0 | 0
26-27 RDEL Forecast Total | 0 | 0 | 0
26-27 RDEL Forecast Income | 0 | 0 | 0
27-28 RDEL BL one off new costs | 0 | 0 | 0
27-28 RDEL BL recurring new costs | 0 | 0 | 0
27-28 RDEL BL recurring old costs | 0 | 0 | 0
27-28 RDEL BL Non Gov costs | 0 | 0 | 0
27-28 RDEL BL Total | 0 | 0 | 0
27-28 RDEL BL Income | 0 | 0 | 0
27-28 RDEL Forecast one off new costs | 0 | 0 | 0
27-28 RDEL Forecast recurring new costs | 0 | 0 | 0
27-28 RDEL Forecast recurring old costs | 0 | 0 | 0
27-28 RDEL Forecast Non Gov costs | 0 | 0 | 0
27-28 RDEL Forecast Total | 0 | 0 | 0
27-28 RDEL Forecast Income | 0 | 0 | 0
Unprofiled RDEL BL one off new costs | 83.2 | 0 | 0
Unprofiled RDEL BL recurring new costs | 0 | 0 | 0
Unprofiled RDEL BL recurring old costs | 0 | 0 | 0
Unprofiled RDEL BL Non Gov costs | 0 | 0 | 0
Unprofiled RDEL BL Total | 83.2 | 0 | 0
Unprofiled RDEL BL Income | 0 | 0 | 0
Unprofiled RDEL Forecast one off new costs | 0 | 0 | 0
Unprofiled RDEL Forecast recurring new costs | 0 | 0 | 0
Unprofiled RDEL Forecast recurring old costs | 0 | 0 | 0
Unprofiled RDEL Forecast Non Gov costs | 0 | 0 | 0
Unprofiled RDEL Forecast Total | 0 | 0 | 0
Unprofiled RDEL Forecast Income | 0 | 0 | 0
Total RDEL BL one off new costs | 230.55 | 0 | 132.7
Total RDEL BL recurring new costs | 0 | 0 | 0
Total RDEL BL recurring old costs | 0 | 0 | 0
Total RDEL BL Non Gov costs | 0 | 0 | 0
Total RDEL BL Total | 230.55 | 0 | 132.7
Total RDEL BL Income | 0 | 0 | 0
Total RDEL Forecast one off new costs | 66.65 | 0 | 132.66
Total RDEL Forecast recurring new costs | 0 | 0 | 0
Total RDEL Forecast recurring old costs | 0 | 0 | 0
Total RDEL Forecast Non Gov costs | 0 | 0 | 0
Total RDEL Forecast Total | 66.65 | 0 | 132.66
Total RDEL Forecast Income | 0 | 0 | 0
Year RDEL spend stops | 2021/2022 | No Spend | 2019/2020
Pre 18-19 CDEL BL Total | 166.3 | 103.2 | 0
Pre 18-19 CDEL BL recurring new costs | 0 | 0 | 0
Pre 18-19 CDEL BL recurring old costs | 0 | 0 | 0
Pre 18-19 BL Non-Gov | 384 | 0 | 385
Pre 18-19 CDEL BL WLC | 550.3 | 103.2 | 385
Pre 18-19 BL Income both Revenue and Capital | 0 | 0 | 0
Pre 18-19 CDEL Forecast Total | 199.73 | 109.8 | 0
Pre 18-19 CDEL Forecast recurring new costs | 0 | 0 | 0
Pre 18-19 CDEL Forecast recurring old costs | 0 | 0 | 0
Pre 18-19 Forecast Non-Gov | 384 | 0 | 437.9
Pre 18-19 CDEL Forecast Total WLC | 583.73 | 109.8 | 437.9
Pre 18-19 Actual Income both Revenue and Capital | 0 | 0 | 0
18 -19 CDEL BL Total | 0 | 61.9 | 0
18-19 CDEL BL recurring new costs | 0 | 0 | 0
18-19 CDEL BL recurring old costs | 0 | 0 | 0
18-19 BL Non-Gov | 96 | 0 | 141
18 -19 CDEL BL WLC | 96 | 61.9 | 141
18-19 BL Income both Revenue and Capital | 0 | 0 | 0
18-19 CDEL Forecast Total | 14.25 | 78.4 | 0
18-19 CDEL Forecast recurring new costs | 0 | 0 | 0
18-19 CDEL Forecast recurring old costs | 0 | 0 | 0
18-19 Forecast Non-Gov | 96 | 0 | 99.9
18-19 CDEL Forecast Total WLC | 110.25 | 78.4 | 99.9
18-19 Forecast - Income both Revenue and Capital | 0 | 0 | 0
19-20 CDEL BL Total | 0 | 64.3 | 0
19-20 CDEL BL recurring new costs | 0 | 0 | 0
19-20 CDEL BL recurring old costs | 0 | 0 | 0
19-20 BL Non-Gov | 0 | 0 | 89
19-20 CDEL BL WLC | 0 | 64.3 | 89
19-20 BL Income both Revenue and Capital | 0 | 0 | 0
19-20 CDEL Forecast Total | 0 | 165 | 0
19-20 CDEL Forecast recurring new costs | 0 | 0 | 0
19-20 CDEL Forecast recurring old costs | 0 | 0 | 0
19-20 Forecast Non-Gov | 0 | 0 | 11.7
19-20 CDEL Forecast Total WLC | 0 | 165 | 11.7
19-20 Forecast - Income both Revenue and Capital | 0 | 0 | 0
20-21 CDEL BL Total | 0 | 1053.4 | 0
20-21 CDEL BL recurring new costs | 0 | 0 | 0
20-21 CDEL BL recurring old costs | 0 | 0 | 0
20-21 BL Non-Gov | 0 | 0
20-21 CDEL BL WLC | 0 | 1053.4 | 0
20-21 BL - Income both Revenue and Capital | 0 | 0 | 0
20-21 CDEL Forecast Total | 0 | 216.1 | 0
20-21 CDEL Forecast recurring new costs | 0 | 0 | 0
20-21 CDEL Forecast recurring old costs | 0 | 0 | 0
20-21 Forecast Non-Gov | 0 | 0
20-21 CDEL Forecast Total WLC | 0 | 216.1 | 0
20-21 Forecast - Income both Revenue and Capital | 0 | 0 | 0
21-22 CDEL BL Total | 0 | 778.3 | 0
21-22 CDEL BL recurring new costs | 0 | 0 | 0
21-22 CDEL BL recurring old costs | 0 | 0 | 0
21-22 BL Non-Gov | 0 | 0 | 0
21-22 CDEL BL WLC | 0 | 778.3 | 0
21-22 BL Income both Revenue and Capital | 0 | 0 | 0
21-22 CDEL Forecast Total | 0 | 323.95 | 0
21-22 CDEL Forecast recurring new costs | 0 | 0 | 0
21-22 CDEL Forecast recurring old costs | 0 | 0 | 0
21-22 Forecast Non-Gov | 0 | 0
21-22 CDEL Forecast Total WLC | 0 | 323.95 | 0
21-22 Forecast - Income both Revenue and Capital | 0 | 0 | 0
22-23 CDEL BL Total | 0 | 778.3 | 0
22-23 CDEL BL recurring new costs | 0 | 0 | 0
22-23 CDEL BL recurring old costs | 0 | 0 | 0
22-23 BL Non-Gov | 0 | 0 | 0
22-23 CDEL BL WLC | 0 | 778.3 | 0
22-23 BL Income both Revenue and Capital | 0 | 0 | 0
22-23 CDEL Forecast Total | 0 | 825.71 | 0
22-23 CDEL Forecast recurring new costs | 0 | 0 | 0
22-23 CDEL Forecast recurring old costs | 0 | 0 | 0
22-23 Forecast Non-Gov | 0 | 0
22-23 CDEL Forecast Total WLC | 0 | 825.71 | 0
22-23 Forecast - Income both Revenue and Capital | 0 | 0 | 0
23-24 CDEL BL Total | 0 | 778.3 | 0
23-24 CDEL BL recurring new costs | 0 | 0 | 0
23-24 CDEL BL recurring old costs | 0 | 0 | 0
23-24 BL Non-Gov | 0 | 0 | 0
23-24 CDEL BL WLC | 0 | 778.3 | 0
23-24 BL Income both Revenue and Capital | 0 | 0 | 0
23-24 CDEL Forecast Total | 0 | 909.19 | 0
23-24 CDEL Forecast recurring new costs | 0 | 0 | 0
23-24 CDEL Forecast recurring old costs | 0 | 0 | 0
23-24 Forecast Non-Gov | 0 | 0
23-24 CDEL Forecast Total WLC | 0 | 909.19 | 0
23-24 Forecast - Income both Revenue and Capital | 0 | 0 | 0
24-25 CDEL BL Total | 0 | 778.3 | 0
24-25 CDEL BL recurring new costs | 0 | 0 | 0
24-25 CDEL BL recurring old costs | 0 | 0 | 0
24-25 BL Non-Gov | 0 | 0 | 0
24-25 CDEL BL WLC | 0 | 778.3 | 0
24-25 BL Income both Revenue and Capital | 0 | 0 | 0
24-25 CDEL Forecast Total | 0 | 1216.59 | 0
24-25 CDEL Forecast recurring new costs | 0 | 0 | 0
24-25 CDEL Forecast recurring old costs | 0 | 0 | 0
24-25 Forecast Non-Gov | 0 | 0 | 0
24-25 CDEL Forecast Total WLC | 0 | 1216.59 | 0
24-25 Forecast - Income both Revenue and Capital | 0 | 0 | 0
25-26 CDEL BL Total | 0 | 252.8 | 0
25-26 CDEL BL recurring new costs | 0 | 0 | 0
25-26 CDEL BL recurring old costs | 0 | 0 | 0
25-26 BL Non-Gov | 0 | 0 | 0
25-26 CDEL BL WLC | 0 | 252.8 | 0
25-26 BL Income both Revenue and Capital | 0 | 0 | 0
25-26 CDEL Forecast Total | 0 | 1141.08 | 0
25-26 CDEL Forecast recurring new costs | 0 | 0 | 0
25-26 CDEL Forecast recurring old costs | 0 | 0 | 0
25-26 Forecast Non-Gov | 0 | 0 | 0
25-26 CDEL Forecast Total WLC | 0 | 1141.08 | 0
25-26 Forecast - Income both Revenue and Capital | 0 | 0 | 0
26-27 CDEL BL Total | 0 | 0 | 0
26-27 CDEL BL recurring new costs | 0 | 0 | 0
26-27 CDEL BL recurring old costs | 0 | 0 | 0
26-27 BL Non-Gov | 0 | 0 | 0
26-27 CDEL BL WLC | 0 | 0 | 0
26-27 BL Income both Revenue and Capital | 0 | 0 | 0
26-27 CDEL Forecast Total | 0 | 706.25 | 0
26-27 CDEL Forecast recurring new costs | 0 | 0 | 0
26-27 CDEL Forecast recurring old costs | 0 | 0 | 0
26-27 Forecast Non-Gov | 0 | 0 | 0
26-27 CDEL Forecast Total WLC | 0 | 706.25 | 0
26-27 Forecast - Income both Revenue and Capital | 0 | 0 | 0
27-28 CDEL BL Total | 0 | 0 | 0
27-28 CDEL BL recurring new costs | 0 | 0 | 0
27-28 CDEL BL recurring old costs | 0 | 0 | 0
27-28 BL Non-Gov | 0 | 0 | 0
27-28 CDEL BL WLC | 0 | 0 | 0
27-28 BL Income both Revenue and Capital | 0 | 0 | 0
27-28 CDEL Forecast Total | 0 | 0 | 0
27-28 CDEL Forecast recurring new costs | 0 | 0 | 0
27-28 CDEL Forecast recurring old costs | 0 | 0 | 0
27-28 Forecast Non-Gov | 0 | 0 | 0
27-28 CDEL Forecast Total WLC | 0 | 0 | 0
27-28 Forecast - Income both Revenue and Capital | 0 | 0 | 0
Unprofiled CDEL BL Total | 0 | 0 | 0
Unprofiled CDEL BL recurring new costs | 0 | 0 | 0
Unprofiled CDEL BL recurring old costs | 0 | 0 | 0
Unprofiled BL Non-Gov | 5700 | 0 | 0
Unprofiled CDEL BL WLC | 5700 | 0 | 0
Unprofiled BL Income | 0 | 0 | 0
Unprofiled CDEL Forecast Total | 0 | 0 | 0
Unprofiled CDEL Forecast recurring new costs | 0 | 0 | 0
Unprofiled CDEL Forecast recurring old costs | 0 | 0 | 0
Unprofiled Forecast Non-Gov | 5700 | 0 | 0
Unprofiled CDEL Forecast Total WLC | 5700 | 0 | 0
Unprofiled Forecast - Income both Revenue and Capital | 0 | 0 | 0
Total CDEL BL Total | 166.3 | 4648.8 | 0
Total CDEL BL recurring new costs | 0 | 0 | 0
Total CDEL BL recurring old costs | 0 | 0 | 0
Non-Gov Total Budget/BL | 6180 | 0 | 615
Total CDEL BL WLC | 6346.3 | 4648.8 | 615
Total Baseline - Income both Revenue and Capital | 0 | 0 | 0
Total CDEL Forecast Total | 213.98 | 5692.07 | 0
Total CDEL Forecast recurring new costs | 0 | 0 | 0
Total CDEL Forecast recurring old costs | 0 | 0 | 0
Non-Gov Total Forecast | 6180 | 0 | 549.5
Total CDEL Forecast Total WLC | 6393.98 | 5692.07 | 549.5
Total Forecast - Income both Revenue and Capital | 0 | 0 | 0
Year CDEL spend stops | 2046/2047 | 2026/2027 | 2018/2019
VfM Category single entry | High | Medium | Poor
Present Value Cost (PVC) | 833 | 2952 | 1172
Present Value Benefit (PVB) | 3494 | 4487 | 738.36
Re-baseline ALB/Programme milestones |  |  | Yes
Re-baseline ALB/Programme cost |  |  | Yes
Re-baseline ALB/Programme benefits |  |  | Yes
Re-baseline IPDC milestones |  |  | Yes
Re-baseline IPDC cost |  | Yes | Yes
Re-baseline IPDC benefits |  |  | Yes
Re-baseline HMT milestones |  |  | Yes
Re-baseline HMT cost |  |  | Yes
Re-baseline HMT benefits |  |  | Yes
Pre-profile RDEL | 62.07 | 0 | 63.02
Pre-profile CDEL | 583.73 | 109.8 | 437.9
Re-baseline this quarter