## Master
Project/Programme Name | Mars | Sea of Tranquility | Apollo 11 | Apollo 13 | Falcon 9 | Columbia
IPDC approval point | Pre Strategic Outline Business Case | Full Business Case | Pre Strategic Outline Business Case | Full Business Case | Outline Business Case | Full Business Case
Re-baseline this quarter | Yes
Re-baseline ALB/Programme milestones | Yes
Re-baseline ALB/Programme cost | Yes
Re-baseline ALB/Programme benefits | Yes
Re-baseline IPDC milestones | Yes
Re-baseline IPDC cost | Yes
Re-baseline IPDC benefits | Yes
Re-baseline HMT milestones | Yes
Re-baseline HMT cost | Yes
Re-baseline HMT benefits | Yes
Latest Treasury Approval Point (TAP) or equivalent |  | Full Business Case |  | Full Business Case | Strategic Outline Case | Full Business Case
Version Number Of Document used to Source Figures (GMPP - TAP version Number) |  | 1 | EWRCo Sep 18 | IEP-Bus Case-12 | 1 | Full Business Case (SW Route Capacity Programme including rolling stock and infrastructure interventions). As refreshed in January 2018.
Business Case & Version No. |  | Full Business Case 1 |  | Full Business Case IEP-Bus Case-12 | Strategic Outline Case 1 | Full Business Case Full Business Case (SW Route Capacity Programme including rolling stock and infrastructure interventions). As refreshed in January 2018.
Date of TAP used to source figures |  | 2016-06-30 |  | 2011-11-28 | 2016-01-18 | 2014-08-01
If no HMT Business Case please advise why?
Is your HMT Business case updated / approved annually by HMT or more frequently? |  | No |  | No | No | Yes
Does the HMT Businesss Case cover the full life of the project? |  | Yes |  | Yes | Yes | Yes
If not please provide explanation as to why
If not please advise how many years are covered
If not please advise how much cost is covered as a percentage
Are the baselines in this return from the most recent HMT Approved Business Case? |  | Yes |  | Yes | Yes | Yes
If not what is the source of baselines in this returns?
If not please give a reason why baselines
What is the source of all forecasts in this return? | Memento mori and amor fati | The mind is not a vessel to be filled but a fire to be lighted | nail | What you see if all there is | nail | screw driver
Please provide details of any formal arrangement with HMT regarding Business cases that are outside the classical model
Real or Nominal - Baseline | Nominal | Nominal | Nominal | Nominal | Nominal | Nominal | S
Real or Nominal - Actual/Forecast | Nominal | Nominal | Nominal | Nominal | Nominal | Nominal
Index Year
Deflator
Are you reporting the full costs of the project? | Yes | Yes | Yes | Yes | Yes | Yes
If no please provide reason why?
Does this project create income? |  | No | Yes | No | No | Yes
Who recieves the income? |  |  | Private Sector - Service Provider |  |  | Government
Do you net the income with your costs in the GMPP return
Income Against which Cost category?
Income Baseline - Real or Nominal |  |  | Nominal |  |  | Nominal
Income Forecast - Real or Nominal |  |  | Nominal |  |  | Nominal
Income If real Index Year used?
Income If real Deflator used?
Are you reporting the full income of the project? |  |  | Yes |  |  | No
Income If no please provide reason why? | [5 empty] | Realised thorough franchise
Does this project create monetised benefits? | Yes | Yes | Yes | Yes | Yes | No
Benefits Baseline - Real or Nominal | Nominal | Real | Nominal | Nominal | Real
Benefits Forecast - Real or Nominal | Nominal | Real | Nominal | Nominal | Real
Benefits If real Index Year used |  | 2010 |  |  | 2010
Benefits If real Deflator used |  | 0.03 |  |  | 0.03
Are you reporting the full benefits of the project? | No | Yes | Yes | Yes | Yes
Benefits If no please provide reason why? | Not all benefits of the project could be monetised at this stage. These are still described in the SOBC.
Source of Finance | Public | Public | Public & Private | PFI | Public | Public
Other Finance type Description | [5 empty] | all below tbc next quarter
Has this project applied cost uplifts using Optimism Bias? | Yes | No |  | Yes | No
Is this Optimism Bias included within the WLC? | No |  |  | No | No
Overall figure for Optimism Bias (£m) | 3387.2 |  |  |  | 0
Does this project have allocated contingency? | No | No |  | Yes | Yes
Is this Continency amount included within the WLC? | No |  |  | No | Yes
Overall contingency (£m) | 0 |  |  |  | 398
NPV for all projects and NPV for programmes if available | 30292.2 | 1469.2 |  | 1985 | 2952
Adjusted Benefits Cost Ratio (BCR) | 21.45 | 2.58 |  | 2.3 | 1.54 | 0.38
Benefits Map | Yes | Yes | No | Yes | Yes
Benefits Analysed | Yes | Yes |  | Yes | Yes
Benefits Realisation Plan | No | Yes |  | No | Yes
Initial Benefits Cost Ratio (BCR) | 19.72 | 1.36 |  | 2.3 | 0.78 | 0.63
VfM Category single entry | Very High | High |  | High | Medium | Poor
VfM Category lower range
VfM Category upper range
Present Value Cost (PVC) | 1481.6 | 928 |  | 833 | 2831 | 1172
Present Value Benefit (PVB) | 31773.8 | 2398 |  | 3494 | 4364 | 738.36
DfT Group |  | Roads Places and Environment Group | HSMRPG | Rail Group | Roads Places and Environment Group | Rail Group