## Finance
Group | Project Name | Business Case Stage (Achieved) | Project Stage | Forecast WLC (£m) | Change (£m) |  | Aggregate Spend | Contractually Committed | Remaining | P-Value | Contingency | Optimism Bias | SRO Finance DCA
[5 empty] | Against Last Qrt | Against Baseline | [6 empty] | This Qrt | -3 mths | -6 mths | -9 mths | Baseline
AMIS
Roads, Places and Environment | Mars | SOBC | Outline Business Case | 2722.0371 | - | - | 0 |  |  |  | 0 | 266.2027 | A |  |  |  | A
| Sea of Tranquility | FBC |  | 1478.68 | 806.38 | 806.38 | 1409.33 | [5 empty] | A/G
| Apollo 13 | FBC |  | 6485.95 | -4.42 | -4.42 | 751.9516 | [5 empty] | A/R
| Falcon 9 | OBC |  | 6751.6 | 359.87 | 359.87 | 471.4 |  |  |  | 396 | 0 | R
| Columbia | FBC |  | 469.7 | -202.6 | -202.6 | 468.7 | [5 empty] | G
Rail
HSMRPG
Rail (Infrastructure)

## Schedule
Group | Project Name | Business Case Stage (Achieved) | Project Stage | Next Approval Milestone (Forecast) |  | Change (Days) |  | Start of Construction (Forecast) | Change (Days) |  | Start of Operations (Forecast) | Change (Days) |  | Full Operation (Forecast) | Change (Days) |  | Project End Date (Forecast) | Change (Days) |  | SRO Schedule DCA
[6 empty] | Against Last Qrt | Against Baseline |  | Against Last Qrt | Against Baseline |  | Against Last Qrt | Against Baseline |  | Against Last Qrt | Against Baseline |  | Against Last Qrt | Against Baseline | This Qrt | -3 mths | -6 mths | -9 mths | Baseline
AMIS
Roads, Places and Environment | Mars |  |  | Tranquility Hypatia | 2020-09-21 | [14 empty] | G |  |  |  | G
| Sea of Tranquility |  |  | Inverted Cosmonauts | 2013-09-20 | [14 empty] | R
| Apollo 13 |  |  | Space Command | 2006-12-30 | [14 empty] | A/R
| Falcon 9 |  |  | Earth Command | 2015-10-28 | [14 empty] | A
| Columbia |  |  | Team Magma | 2015-10-31 | [14 empty] | A/G
Rail
HSMRPG
Rail (Infrastructure)

## Benefits_VfM
Group | Project Name | Business Case Stage (Achieved) | Project Stage | BCR (Initial) |  | BCR (Adjusted) |  | VfM category(s) |  | Total Monetised Benefits |  | In-year Monetised Benefits |  | SRO Benefits DCA
|  |  |  | This Qrt Forecast | Baseline | This Qrt Forecast | Baseline | This Qrt Forecast | Baseline | This Qrt Forecast (£m) | Change Against Baseline (£m) | This Qrt Forecast (£m) | Change Against Baseline (£m) | This Qrt | -3 mths | -6 mths | -9 mths | Baseline
AMIS
Roads, Places and Environment | Mars | SOBC |  | 12.98 |  | 14.58 |  | Very High |  | 43618.66 |  | 0 |  | A/G | G
| Sea of Tranquility | FBC |  | 1.36 |  | 2.58 |  | High |  | 2397.79 |  | 21 |  | G | G | A | G
| Apollo 13 | FBC |  | 2.3 |  | 2.3 |  | High |  | 3494 |  | 0 |  | A/G | A | A | A
| Falcon 9 | OBC |  | 0.74 |  | 1.46 |  | Medium |  | 4312 |  | 0 |  | A | A | A | A
| Columbia | FBC |  | 0.63 |  | 0.38 |  | Poor |  | 0 |  | 0 |  | A | A | A | A
Rail
HSMRPG
Rail (Infrastructure)

## Overall
Project Name | Business Case Stage (Achieved) | Project Stage | Forecast WLC (£m) | Change (£m) |  | VfM Category | Project End Date (Forecast) | Change (Days) |  | Last at / Next at IPDC |  | IPA GMPP Rating | SRO DCA Rating
|  |  |  | Against Last Qrt | Against Baseline |  |  | Against Last Qrt | Against Baseline | Last IPDC | Next IPDC |  | This Qrt | -3 mths | -6 mths | -9 mths | Baseline
Mars
Sea of Tranquility
Apollo 13
Falcon 9
Columbia