## Master
Project/Programme Name | Mars | Sea of Tranquility | Apollo 13 | Falcon 9 | Columbia
IPDC approval point | Strategic Outline Case | Full Business Case | Full Business Case | Outline Business Case | Full Business Case
Re-baseline this quarter | No | No | No | No | No
Re-baseline ALB/Programme milestones
Re-baseline ALB/Programme cost
Re-baseline ALB/Programme benefits
Re-baseline IPDC milestones
Re-baseline IPDC cost | Yes
Re-baseline IPDC benefits | Yes
Re-baseline HMT milestones
Re-baseline HMT cost
Re-baseline HMT benefits
Latest Treasury Approval Point (TAP) or equivalent |  | Full Business Case | Full Business Case | Outline Business Case | Full Business Case
Version Number Of Document used to Source Figures (GMPP - TAP version Number) |  | 1 | Case-12 | 1 | Full Business Case (
Business Case & Version No. |  | Full Business Case 1 | Full Business Case | Outline Business Case 1 | Full Business Case Full
Date of TAP used to source figures |  | 2016-06-30 | 2011-11-28 | 2020-05-20 | 2014-08-01
If no HMT Business Case please advise why?
Is your HMT Business case updated / approved annually by HMT or more frequently? |  | No | No | No | Yes
Does the HMT Businesss Case cover the full life of the project? |  | Yes | Yes | Yes | Yes
If not please provide explanation as to why
If not please advise how many years are covered
If not, please advise how much cost is covered £m
Are the baselines in this return from the most recent HMT Approved Business Case? |  | Yes | Yes | Yes | Yes
If not please give a reason why baselines
Please provide details of any formal arrangement with HMT regarding Business cases that are outside the classical model |  |  |  | N/A
Has the project been using an evidenced range of costs for planning and approval decisions? | Yes | Yes | No | Yes
Whole Life Cost Range From | 2597.1 | 1446.2 |  | £5.73bn
Whole Life Cost Range To | 2722.01 | 1478.68 |  | £9.01bn
Are you reporting the full costs of the project? | No | Yes | Yes | Yes | Yes
If not, please advise how many years of cost are covered | Contract Costs from 2024-25 onwards for a 10 year operational period at all Bases
If not, please advise how much costs are covered | Contract Costs constitutes 99% of the whole life cost of programme. The remaining £26.84m (1%) for legal, technical and procurement support is consistent across all options and ranges.
If no please provide reason why?
Does this project create income? |  | No | No | No | Yes
Who recieves the income? |  |  |  |  | Government
Has the project been using an evidenced range of income for planning and approval decisions?
Whole Life Income Range From
Whole Life Income Range To
Are you reporting the full income of the project? |  |  |  |  | No
Income If no please provide reason why? |  |  |  |  | Realised thorough franchise
Does this project create monetised benefits? | Yes | Yes | Yes | Yes | No
Has the project been using an evidenced range of Benefits for planning and approval decisions? | Yes | Yes | No | No
Whole Life Benefits Range From | 21821 | £2.397m
Whole Life Benefits Range To | 43642 | £2.398m
Are you reporting the full benefits of the project? | No | Yes | Yes | Yes
Benefits If no please provide reason why? | Not all benefits of the project could be monetised. These are explored indetail within the business cases.
Source of Finance | Public | Public | PFI | Public | Public
Has this project applied cost uplifts using Optimism Bias? | Yes | No | Yes | No
Is this Optimism Bias included within the WLC? | No |  | No
Overall figure for Optimism Bias (£m) | 266.2027 |  |  | 0
Does this project have allocated contingency? | No | No | Yes | Yes
Is this Continency amount included within the WLC? |  |  | No | Yes
Overall contingency (£m) | 0 |  |  | 396
Has the Projects Net Present Value (NPV) been calculated? | Yes | Yes | Yes | Yes
NPV for all projects and NPV for programmes if available | 28369 | 1469.2 | 1985 | 1356
Has the Projects Benefits to Cost Ratio (BCR) been calculated? | Yes | Yes | Yes | Yes | Yes
Initial Benefits Cost Ratio (BCR) | 12.98 | 1.36 | 2.3 | 0.74 | 0.63
Adjusted Benefits Cost Ratio (BCR) | 14.58 | 2.58 | 2.3 | 1.46 | 0.38
In calculating the NPV and/or BCR, was the GDP Deflator used? | No | Yes | No | Yes
If no, please explain what was used as a deflator instead? | WebTAG Retail Price Index | N/A | Models constructed to deflate future nominal (cash) prices by the RPI index | N/A
Present Value Cost (PVC) | 2089 | 928 | 833 | 2956 | 1172
Present Value Benefit (PVB) | 30458 | 2398 | 3494 | 4312 | 738.36
Benefits Map | Yes | Yes | Yes | No | Yes
Benefits Analysed | Yes | Yes | Yes | Yes
Benefits Realisation Plan | Yes | Yes | No | Yes | Yes
VfM Category single entry | Very High | High | High | Medium | Poor
VfM Category lower range | Very High | High |  | N/A
VfM Category upper range | Very High | High |  | N/A
SRO Finance confidence | Amber | Amber/Green | Amber/Green | Amber | Green
Project Costs Narrative
Cost comparison with last quarters cost narrative | screw driver | The mind is not a vessel to be filled but a fire to be lighted | The sea gets deeper the further you go into it | wood | Green lumber fallacy
Cost comparison within this quarters cost narrative | screw driver | screw driver | What you see if all there is | screw | nail
Total BL | 0 | 1435.3 | 6465.89 | 6391.04 | 694.9
Total Forecast | 2722.0371 | 1478.68 | 6485.95 | 6751.6 | 469.7
RDEL & CDEL BL In Year Total | 0 | 19.6 | 2.96 | 245 | 19.2
RDEL & CDEL Forecast In Year Total | 0 | 68.9 | 9.7 | 265 | 19.2
RDEL & CDEL BL Income Total | 0 | 0 | 0 | 0 | 0
RDEL & CDEL Forecast Income Total | 0 | 0 | 0 | 0 | 0
RDEL & CDEL BL In Year Income Total | 0 | 0 | 0 | 0 | 0
RDEL & CDEL Forecast In Year Income Total | 0 | 0 | 0 | 0 | 0
Pre 19-20 RDEL BL one off new costs | 0 | 0 | 55.05 | 0 | 132.7
Pre 19-20 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 RDEL BL Total | 0 | 0 | 55.05 | 0 | 132.7
Pre 19-20 RDEL BL Income | 0 | 0 | 0 | 0 | 0
Pre-profile RDEL Forecast one off new costs | 0 | 0 | 56.72 | 0 | 89.9
Pre 19-20 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
Pre-profile RDEL | 0 | 0 | 56.72 | 0 | 89.9
Pre 19-20 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
19-20 RDEL BL one off new costs | 0 | 0 | 2 | 0 | 33.42
19-20 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
19-20 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
19-20 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
19-20 RDEL BL Total | 0 | 0 | 2 | 0 | 33.42
19-20 RDEL BL Income | 0 | 0 | 0 | 0 | 0
19-20 RDEL Forecast one off new costs | 0 |  | 34.49 | 0 | 33.42
19-20 RDEL Forecast recurring new costs | 0 |  |  | 0 | 0
19-20 RDEL Forecast recurring old costs | 0 |  | 0 | 0 | 0
19-20 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
19-20 RDEL Forecast Total | 0 | 0 | 34.49 | 0 | 33.42
19-20 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
20-21 RDEL STD one off new costs | 0 | 0 | 0.803 | 0 | 0
20-21 RDEL STD recurring new costs | 0 | 0 |  | 0 | 0
20-21 RDEL STD recurring old costs | 0 | 0 |  | 0 | 0
20-21 RDEL STD Non Gov costs | 0 | 0 |  | 0 | 0
20-21 RDEL STD Total | 0 | 0 | 0.803 | 0 | 0
20-21 RDEL STD Income | 0 | 0 | 0 | 0 | 0
20-21 RDEL BL one off new costs | 0 | 0 | 1.5 | 0 | 0
20-21 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
20-21 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
20-21 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
20-21 RDEL BL Total | 0 | 0 | 1.5 | 0 | 0
20-21 RDEL BL Income | 0 | 0 | 0 | 0 | 0
20-21 RDEL Forecast one off new costs | 0 | 0 | 1.5 | 0 | 0
20-21 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
20-21 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
20-21 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
20-21 RDEL Forecast Total | 0 | 0 | 1.5 | 0 | 0
20-21 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
21-22 RDEL BL one off new costs | 0 | 0 | 0.5 | 0 | 0
21-22 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
21-22 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
21-22 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
21-22 RDEL BL Total | 0 | 0 | 0.5 | 0 | 0
21-22 RDEL BL Income | 0 | 0 | 0 | 0 | 0
21-22 RDEL Forecast one off new costs | 0 | 0 | 0.5 | 0 | 0
21-22 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
21-22 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
21-22 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
21-22 RDEL Forecast Total | 0 | 0 | 0.5 | 0 | 0
21-22 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
22-23 RDEL BL one off new costs | 0 | 0 | 0.4 | 0 | 0
22-23 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
22-23 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
22-23 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
22-23 RDEL BL Total | 0 | 0 | 0.4 | 0 | 0
22-23 RDEL BL Income | 0 | 0 | 0 | 0 | 0
22-23 RDEL Forecast one off new costs | 0 | 0 | 0.4 | 0 | 0
22-23 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
22-23 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
22-23 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
22-23 RDEL Forecast Total | 0 | 0 | 0.4 | 0 | 0
22-23 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
23-24 RDEL BL one off new costs | 0 | 0 | 0.3 | 0 | 0
23-24 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
23-24 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
23-24 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
23-24 RDEL BL Total | 0 | 0 | 0.3 | 0 | 0
23-24 RDEL BL Income | 0 | 0 | 0 | 0 | 0
23-24 RDEL Forecast one off new costs | 0 | 0 | 0.3 | 0 | 0
23-24 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
23-24 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
23-24 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
23-24 RDEL Forecast Total | 0 | 0 | 0.3 | 0 | 0
23-24 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
24-25 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
24-25 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
24-25 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
24-25 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
24-25 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
24-25 RDEL BL Income | 0 | 0 | 0 | 0 | 0
24-25 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
24-25 RDEL Forecast recurring new costs | 26.46 | 0 | 0 | 0 | 0
24-25 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
24-25 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
24-25 RDEL Forecast Total | 26.46 | 0 | 0.2 | 0 | 0
24-25 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
25-26 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
25-26 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
25-26 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
25-26 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
25-26 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
25-26 RDEL BL Income | 0 | 0 | 0 | 0 | 0
25-26 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
25-26 RDEL Forecast recurring new costs | 103.1 | 0 | 0 | 0 | 0
25-26 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
25-26 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
25-26 RDEL Forecast Total | 103.1 | 0 | 0.2 | 0 | 0
25-26 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
26-27 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
26-27 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
26-27 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
26-27 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
26-27 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
26-27 RDEL BL Income | 0 | 0 | 0 | 0 | 0
26-27 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
26-27 RDEL Forecast recurring new costs | 190.28 | 0 | 0 | 0 | 0
26-27 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
26-27 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
26-27 RDEL Forecast Total | 190.28 | 0 | 0.2 | 0 | 0
26-27 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
27-28 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
27-28 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
27-28 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
27-28 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
27-28 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
27-28 RDEL BL Income | 0 | 0 | 0 | 0 | 0
27-28 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
27-28 RDEL Forecast recurring new costs | 215.57 | 0 | 0 | 0 | 0
27-28 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
27-28 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
27-28 RDEL Forecast Total | 215.57 | 0 | 0.2 | 0 | 0
27-28 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
28-29 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
28-29 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
28-29 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
28-29 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
28-29 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
28-29 RDEL BL Income | 0 | 0 | 0 | 0 | 0
28-29 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
28-29 RDEL Forecast recurring new costs | 216.93 | 0 | 0 | 0 | 0
28-29 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
28-29 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
28-29 RDEL Forecast Total | 216.93 | 0 | 0.2 | 0 | 0
28-29 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
29-30 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
29-30 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
29-30 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
29-30 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
29-30 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
29-30 RDEL BL Income | 0 | 0 | 0 | 0 | 0
29-30 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
29-30 RDEL Forecast recurring new costs | 219.97 | 0 | 0 | 0 | 0
29-30 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
29-30 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
29-30 RDEL Forecast Total | 219.97 | 0 | 0.2 | 0 | 0
29-30 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
30-31 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
30-31 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
30-31 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
30-31 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
30-31 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
30-31 RDEL BL Income | 0 | 0 | 0 | 0 | 0
30-31 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
30-31 RDEL Forecast recurring new costs | 223.06 | 0 | 0 | 0 | 0
30-31 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
30-31 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
30-31 RDEL Forecast Total | 223.06 | 0 | 0.2 | 0 | 0
30-31 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
31-32 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
31-32 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
31-32 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
31-32 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
31-32 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
31-32 RDEL BL Income | 0 | 0 | 0 | 0 | 0
31-32 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
31-32 RDEL Forecast recurring new costs | 226.19 | 0 | 0 | 0 | 0
31-32 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
31-32 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
31-32 RDEL Forecast Total | 226.19 | 0 | 0.2 | 0 | 0
31-32 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
32-33 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
32-33 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
32-33 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
32-33 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
32-33 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
32-33 RDEL BL Income | 0 | 0 | 0 | 0 | 0
32-33 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
32-33 RDEL Forecast recurring new costs | 229.36 | 0 | 0 | 0 | 0
32-33 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
32-33 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
32-33 RDEL Forecast Total | 229.36 | 0 | 0.2 | 0 | 0
32-33 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
33-34 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
33-34 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
33-34 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
33-34 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
33-34 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
33-34 RDEL BL Income | 0 | 0 | 0 | 0 | 0
33-34 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
33-34 RDEL Forecast recurring new costs | 232.56 | 0 | 0 | 0 | 0
33-34 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
33-34 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
33-34 RDEL Forecast Total | 232.56 | 0 | 0.2 | 0 | 0
33-34 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
34-35 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
34-35 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
34-35 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
34-35 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
34-35 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
34-35 RDEL BL Income | 0 | 0 | 0 | 0 | 0
34-35 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
34-35 RDEL Forecast recurring new costs | 216.62 | 0 | 0 | 0 | 0
34-35 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
34-35 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
34-35 RDEL Forecast Total | 216.62 | 0 | 0.2 | 0 | 0
34-35 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
35-36 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
35-36 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
35-36 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
35-36 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
35-36 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
35-36 RDEL BL Income | 0 | 0 | 0 | 0 | 0
35-36 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
35-36 RDEL Forecast recurring new costs | 145.26 | 0 | 0 | 0 | 0
35-36 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
35-36 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
35-36 RDEL Forecast Total | 145.26 | 0 | 0.2 | 0 | 0
35-36 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
36-37 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
36-37 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
36-37 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
36-37 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
36-37 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
36-37 RDEL BL Income | 0 | 0 | 0 | 0 | 0
36-37 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
36-37 RDEL Forecast recurring new costs | 51.19 | 0 | 0 | 0 | 0
36-37 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
36-37 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
36-37 RDEL Forecast Total | 51.19 | 0 | 0.2 | 0 | 0
36-37 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
37-38 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
37-38 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
37-38 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
37-38 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
37-38 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
37-38 RDEL BL Income | 0 | 0 | 0 | 0 | 0
37-38 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
37-38 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
37-38 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
37-38 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
37-38 RDEL Forecast Total | 0 | 0 | 0.2 | 0 | 0
37-38 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
38-39 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
38-39 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
38-39 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
38-39 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
38-39 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
38-39 RDEL BL Income | 0 | 0 | 0 | 0 | 0
38-39 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
38-39 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
38-39 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
38-39 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
38-39 RDEL Forecast Total | 0 | 0 | 0.2 | 0 | 0
38-39 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
39-40 RDEL BL one off new costs | 0 | 0 | 0.2 | 0 | 0
39-40 RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
39-40 RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
39-40 RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
39-40 RDEL BL Total | 0 | 0 | 0.2 | 0 | 0
39-40 RDEL BL Income | 0 | 0 | 0 | 0 | 0
39-40 RDEL Forecast one off new costs | 0 | 0 | 0.2 | 0 | 0
39-40 RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
39-40 RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
39-40 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
39-40 RDEL Forecast Total | 0 | 0 | 0.2 | 0 | 0
39-40 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL BL one off new costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL BL Total | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL BL Income | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL Forecast one off new costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL Forecast Total | 0 | 0 | 0 | 0 | 0
Unprofiled RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
Total RDEL BL one off new costs | 0 | 0 | 60.95 | 0 | 132.7
Total RDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
Total RDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
Total RDEL BL Non Gov costs | 0 | 0 | 0 | 0 | 0
Total RDEL BL Total | 0 | 0 | 60.95 | 0 | 132.7
Total RDEL BL Income | 0 | 0 | 0 | 0 | 0
Total RDEL Forecast one off new costs | 0 | 0 | 62.62 | 0 | 89.9
Total RDEL Forecast recurring new costs | 2296.55 | 0 | 0 | 0 | 0
Total RDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
Total RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
Total RDEL Forecast Total | 2296.55 | 0 | 62.62 | 0 | 89.9
Total RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
Year RDEL spend stops | 2036/2037 | No Spend | 2021/2022 | No Spend | 2019/2020
Pre 19-20 CDEL BL one off new costs | 0 | 1415.7 | 202.76 | 365 | 16
Pre 19-20 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 BL Non-Gov | 0 | 0 | 480 | 0 | 526
Pre 19-20 CDEL BL WLC | 0 | 1415.7 | 682.76 | 365 | 542
Pre 19-20 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
Pre-profile CDEL Forecast one off new costs | 0 | 1356.74 | 214.41 | 352 | 15.46
Pre 19-20 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
Pre 19-20 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
Pre-profile Forecast Non-Gov | 0 | 0 | 480 | 0 | 344.14
Pre-profile CDEL WLC | 0 | 1356.74 | 694.41 | 352 | 359.6
Pre 19-20 Actual Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
19-20 CDEL BL one off new costs | 0 | 401 | 36.46 | 177.49 | 16
19-20 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
19-20 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
19-20 BL Non-Gov | 0 | 0 | 0 | 0 | 0
19-20 CDEL BL WLC | 0 | 401 | 36.46 | 177.49 | 16
19-20 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
19-20 CDEL Forecast one off new costs | 0 | 243.9 | 0 | 64.3 | 0
19-20 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
19-20 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
19-20 Forecast Non-Gov | 0 |  |  | 0 | 30.7
19-20 CDEL Forecast Total WLC | 0 | 320.9 | 0 | 165 | 11.7
19-20 Forecast - Income both Revenue and Capital | 0 |  |  |  | 0
20-21 CDEL STD one off new costs |  | 52.59 | 0.0186 | 119.4 | 19.2
20-21 CDEL STD recurring new costs |  | 0 | 0 | 0 | 0
20-21 CDEL STD recurring old costs |  | 0 | 0 | 0 | 0
20-21 CDEL STD Non Gov costs |  | 0 | 0 | 0 | 0
20-21 CDEL STD Total | 0 | 52.59 | 0.0186 | 119.4 | 19.2
20-21 CDEL STD Income |  | 0 | 0 | 0 | 0
20-21 CDEL BL one off new costs | 0 | 19.6 | 1.46 | 245 | 19.2
20-21 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
20-21 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
20-21 BL Non-Gov | 0 | 0 | 0 | 0 | 0
20-21 CDEL BL WLC | 0 | 19.6 | 1.46 | 245 | 19.2
20-21 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
20-21 CDEL Forecast one off new costs | 0 | 68.9 | 8.2 | 265 | 19.2
20-21 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
20-21 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
20-21 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
20-21 CDEL Forecast Total WLC | 0 | 68.9 | 8.2 | 265 | 19.2
20-21 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
21-22 CDEL BL one off new costs | 0 | 0 | 9.2 | 411.3 | 1
21-22 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
21-22 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
21-22 BL Non-Gov | 0 | 0 | 0 | 0 | 0
21-22 CDEL BL WLC | 0 | 0 | 9.2 | 411.3 | 1
21-22 BL - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
21-22 CDEL Forecast one off new costs | 0 | 38.97 | 9.2 | 295.3 | 1
21-22 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
21-22 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
21-22 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
21-22 CDEL Forecast Total WLC | 0 | 38.97 | 9.2 | 295.3 | 1
21-22 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
22-23 CDEL BL one off new costs | 0 | 0 | 4 | 443.2 | 0
22-23 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
22-23 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
22-23 BL Non-Gov | 0 | 0 | 0 | 0 | 0
22-23 CDEL BL WLC | 0 | 0 | 4 | 443.2 | 0
22-23 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
22-23 CDEL Forecast one off new costs | 0 | 14.07 | 4 | 924.6 | 0
22-23 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
22-23 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
22-23 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
22-23 CDEL Forecast Total WLC | 0 | 14.07 | 4 | 924.6 | 0
22-23 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
23-24 CDEL BL one off new costs | 0 | 0 | 0.48 | 728.1 | 0
23-24 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
23-24 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
23-24 BL Non-Gov | 0 | 0 | 0 | 0 | 0
23-24 CDEL BL WLC | 0 | 0 | 0.48 | 728.1 | 0
23-24 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
23-24 CDEL Forecast one off new costs | 119.87 | 0 | 0.48 | 1115.3 | 0
23-24 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
23-24 CDEL Forecast recurring old costs |  | 0 | 0 | 0 | 0
23-24 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
23-24 CDEL Forecast Total WLC | 119.87 | 0 | 0.48 | 1115.3 | 0
23-24 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
24-25 CDEL BL one off new costs | 0 | 0 | 0.4 | 1046.6 | 0
24-25 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
24-25 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
24-25 BL Non-Gov | 0 | 0 | 0 | 0 | 0
24-25 CDEL BL WLC | 0 | 0 | 0.4 | 1046.6 | 0
24-25 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
24-25 CDEL Forecast one off new costs | 120.56 | 0 | 0.4 | 1214.9 | 0
24-25 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
24-25 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
24-25 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
24-25 CDEL Forecast Total WLC | 120.56 | 0 | 0.4 | 1214.9 | 0
24-25 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
25-26 CDEL BL one off new costs | 0 | 0 | 0.4 | 1441 | 0
25-26 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
25-26 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
25-26 BL Non-Gov | 0 | 0 | 0 | 0 | 0
25-26 CDEL BL WLC | 0 | 0 | 0.4 | 1441 | 0
25-26 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
25-26 CDEL Forecast one off new costs | 185.0571 | 0 | 0.4 | 1284.2 | 0
25-26 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
25-26 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
25-26 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
25-26 CDEL Forecast Total WLC | 185.0571 | 0 | 0.4 | 1284.2 | 0
25-26 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
26-27 CDEL BL one off new costs | 0 | 0 | 0.4 | 1315 | 0
26-27 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
26-27 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
26-27 BL Non-Gov | 0 | 0 | 0 | 0 | 0
26-27 CDEL BL WLC | 0 | 0 | 0.4 | 1315 | 0
26-27 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
26-27 CDEL Forecast one off new costs | 0 | 0 | 0.4 | 934 | 0
26-27 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
26-27 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
26-27 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
26-27 CDEL Forecast Total WLC | 0 | 0 | 0.4 | 934 | 0
26-27 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
27-28 CDEL BL one off new costs | 0 | 0 | 0.4 | 395.84 | 0
27-28 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
27-28 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
27-28 BL Non-Gov | 0 | 0 | 0 | 0 | 0
27-28 CDEL BL WLC | 0 | 0 | 0.4 | 395.84 | 0
27-28 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
27-28 CDEL Forecast one off new costs | 0 | 0 | 0.4 | 318.4 | 0
27-28 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
27-28 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
27-28 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
27-28 CDEL Forecast Total WLC | 0 | 0 | 0.4 | 318.4 | 0
27-28 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
28-29 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
28-29 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
28-29 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
28-29 BL Non-Gov | 0 | 0 | 0 | 0 | 0
28-29 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
28-29 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
28-29 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 47 | 0
28-29 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
28-29 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
28-29 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
28-29 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 47 | 0
28-29 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
29-30 CDEL BL one off new costs | 0 | 0 | 0.4 | 0 | 0
29-30 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
29-30 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
29-30 BL Non-Gov | 0 | 0 | 0 | 0 | 0
29-30 CDEL BL WLC | 0 | 0 | 0.4 | 0 | 0
29-30 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
29-30 CDEL Forecast one off new costs | 0 | 0 | 0.4 | 0.9 | 0
29-30 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
29-30 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
29-30 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
29-30 CDEL Forecast Total WLC | 0 | 0 | 0.4 | 0.9 | 0
29-30 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
30-31 CDEL BL one off new costs | 0 | 0 | 0.4 | 0 | 0
30-31 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
30-31 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
30-31 BL Non-Gov | 0 | 0 | 0 | 0 | 0
30-31 CDEL BL WLC | 0 | 0 | 0.4 | 0 | 0
30-31 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
30-31 CDEL Forecast one off new costs | 0 | 0 | 0.4 | 0 | 0
30-31 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
30-31 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
30-31 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
30-31 CDEL Forecast Total WLC | 0 | 0 | 0.4 | 0 | 0
30-31 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
31-32 CDEL BL one off new costs | 0 | 0 | 0.4 | 0 | 0
31-32 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
31-32 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
31-32 BL Non-Gov | 0 | 0 | 0 | 0 | 0
31-32 CDEL BL WLC | 0 | 0 | 0.4 | 0 | 0
31-32 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
31-32 CDEL Forecast one off new costs | 0 | 0 | 0.4 | 0 | 0
31-32 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
31-32 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
31-32 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
31-32 CDEL Forecast Total WLC | 0 | 0 | 0.4 | 0 | 0
31-32 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
32-33 CDEL BL one off new costs | 0 | 0 | 0.4 | 0 | 0
32-33 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
32-33 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
32-33 BL Non-Gov | 0 | 0 | 0 | 0 | 0
32-33 CDEL BL WLC | 0 | 0 | 0.4 | 0 | 0
32-33 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
32-33 CDEL Forecast one off new costs | 0 | 0 | 0.4 | 0 | 0
32-33 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
32-33 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
32-33 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
32-33 CDEL Forecast Total WLC | 0 | 0 | 0.4 | 0 | 0
32-33 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
33-34 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
33-34 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
33-34 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
33-34 BL Non-Gov | 0 | 0 | 0 | 0 | 0
33-34 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
33-34 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
33-34 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 0 | 0
33-34 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
33-34 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
33-34 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
33-34 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 0 | 0
33-34 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
34-35 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
34-35 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
34-35 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
34-35 BL Non-Gov | 0 | 0 | 0 | 0 | 0
34-35 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
34-35 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
34-35 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 0 | 0
34-35 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
34-35 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
34-35 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
34-35 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 0 | 0
34-35 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
35-36 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
35-36 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
35-36 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
35-36 BL Non-Gov | 0 | 0 | 0 | 0 | 0
35-36 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
35-36 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
35-36 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 0 | 0
35-36 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
35-36 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
35-36 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
35-36 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 0 | 0
35-36 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
36-37 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
36-37 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
36-37 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
36-37 BL Non-Gov | 0 | 0 | 0 | 0 | 0
36-37 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
36-37 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
36-37 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 0 | 0
36-37 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
36-37 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
36-37 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
36-37 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 0 | 0
36-37 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
37-38 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
37-38 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
37-38 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
37-38 BL Non-Gov | 0 | 0 | 0 | 0 | 0
37-38 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
37-38 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
37-38 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 0 | 0
37-38 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
37-38 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
37-38 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
37-38 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 0 | 0
37-38 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
38-39 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
38-39 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
38-39 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
38-39 BL Non-Gov | 0 | 0 | 0 | 0 | 0
38-39 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
38-39 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
38-39 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 0 | 0
38-39 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
38-39 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
38-39 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
38-39 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 0 | 0
38-39 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
39-40 CDEL BL one off new costs | 0 | 0 | 0.48 | 0 | 0
39-40 CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
39-40 CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
39-40 BL Non-Gov | 0 | 0 | 0 | 0 | 0
39-40 CDEL BL WLC | 0 | 0 | 0.48 | 0 | 0
39-40 BL Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
39-40 CDEL Forecast one off new costs | 0 | 0 | 0.48 | 0 | 0
39-40 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
39-40 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
39-40 Forecast Non-Gov | 0 | 0 | 0 | 0 | 0
39-40 CDEL Forecast Total WLC | 0 | 0 | 0.48 | 0 | 0
39-40 Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
Unprofiled CDEL BL one off new costs | 0 | 0 | 0 | 0 | 0
Unprofiled CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
Unprofiled CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
Unprofiled BL Non-Gov | 0 | 0 | 5700 | 0 | 0
Unprofiled CDEL BL WLC | 0 | 0 | 5700 | 0 | 0
Unprofiled BL Income | 0 | 0 | 0 | 0 | 0
Unprofiled CDEL Forecast one off new costs | 0 | 0 | 0 | 0 | 0
Unprofiled CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
Unprofiled CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
Unprofiled Forecast Non-Gov | 0 | 0 | 5700 | 0 | 0
Unprofiled CDEL Forecast Total WLC | 0 | 0 | 5700 | 0 | 0
Unprofiled Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
Total CDEL BL one off new costs | 0 | 1435.3 | 224.94 | 6391.04 | 36.2
Total CDEL BL recurring new costs | 0 | 0 | 0 | 0 | 0
Total CDEL BL recurring old costs | 0 | 0 | 0 | 0 | 0
Non-Gov Total Budget/BL | 0 | 0 | 6180 | 0 | 526
Total CDEL BL WLC | 0 | 1435.3 | 6404.94 | 6391.04 | 562.2
Total Baseline - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
Total CDEL Forecast one off new costs | 425.4871 | 1478.68 | 243.33 | 6751.6 | 35.66
Total CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
Total CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
Non-Gov Total Forecast | 0 | 0 | 6180 | 0 | 344.14
Total CDEL Forecast Total WLC | 425.4871 | 1478.68 | 6423.33 | 6751.6 | 379.8
Total Forecast - Income both Revenue and Capital | 0 | 0 | 0 | 0 | 0
Year CDEL spend stops | 2026-27 | 2021/2022 | 2046/2047 | 2026/2027 | 2018/2019
SRO Benefits RAG | Amber/Green | Green | Amber/Green | Amber | Amber
Benefits Narrative |  | Python is an interpreted, high-level, general-purpose programming language. Created by Guido van Rossum and first released in 1991, Python's design philosophy emphasizes code readability with its notable use of significant whitespace. Its language constructs and object-oriented approach aim to help programmers write clear, logical code for small and large-scale projects.[28] | PyCharm is an integrated development environment (IDE) used in computer programming, specifically for the Python language. It is developed by the Czech company JetBrains.[6] It provides code analysis, a graphical debugger, an integrated unit tester, integration with version control systems (VCSes), and supports web development with Django as well as Data Science with Anaconda.[7] | Datamaps allows for data to be collected from multiple users using pre-defined forms, built out of Excel spreadsheets. The form can be as complex or as simple as you like - Datamaps does the hard work of collecting the data into one place for onward processing or analysis, whilst ensuring that the data is valid according to expectations. Datamaps acknowledges that in the office environment, we use Excel for everything, but using it to collect data requires help - which is where Datamaps excels. | GitHub, Inc. is an American multinational corporation that provides hosting for software development and version control using Git. It offers the distributed version control and source code management (SCM) functionality of Git, plus its own features. It provides access control and several collaboration features such as bug tracking, feature requests, task management, and wikis for every project.[3] Headquartered in California, it has been a subsidiary of Microsoft since 2018.[4]
Ben comparison with last quarters cost - narrative | Memento mori and amor fati | What you see if all there is | Don't you know an apparition is just a cheap date. What have you been drinking these days | nail | nail
Ben comparison within this quarters cost - narrative | What you see if all there is | Green lumber fallacy | plastic | What you see if all there is | plastic
BEN Totals Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
BEN Totals Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
BEN Totals Gov. Cashable Variance (£m) | 0 | 0 | 0 | 0 | 0
BEN Totals Gov. Cashable Variance (%) | 0% | 0% | 0% | 0% | 0%
BEN Totals Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
BEN Totals Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
BEN Totals Gov. Non-Cashable Variance (£m) | 0 | 0 | 0 | 0 | 0
BEN Totals Gov. Non-Cashable Variance (%) | 0% | 0% | 0% | 0% | 0%
BEN Totals Baseline - Economic (inc Private Partner) | 0 | 2397.79 | 3919 | 4512 | 0
BEN Totals Forecast - Economic (inc Private Partner) | 43637 | 2397.79 | 3919 | 4512 | 0
BEN Totals - Economic (inc Private Partner) Variance (£m) | 43637 | 0 | 0 | 0 | 0
BEN Totals - Economic (inc Private Partner) Variance (%) | 0% | 0 | 0 | 0 | 0%
BEN Totals Baseline - Disbenefit UK Economic | 0 | 0 | -425 | -200 | 0
BEN Totals Forecast - Disbenefit UK Economic | -18.34 | 0 | -425 | -200 | 0
BEN Totals - Disbenefit UK Economic Variance (£m) | -18.34 | 0 | 0 | 0 | 0
BEN Totals - Disbenefit UK Economic Variance (%) | 0% | 0% | 0 | 0 | 0%
BEN Totals Baseline | 0 | 2397.79 | 3494 | 4312 | 0
BEN Totals Forecast | 43618.66 | 2397.79 | 3494 | 4312 | 0
BEN Totals Variance (£m) | 43618.66 | 0 | 0 | 0 | 0
BEN Totals Variance (%) | 0% | 0 | 0 | 0 | 0%
BEN Totals Baseline In-Year | 0 | 21 | 0 | 0 | 0
BEN Forecast In-Year | 0 | 21 | 0 | 0 | 0
BEN In-Year Variance (£m) | 0 | 0 | 0 | 0 | 0
BEN In-Year Variance (%) | 0% | 0 | 0% | 0% | 0%
Pre 19-20 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
Pre 19-20 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
Pre 19-20 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
Pre 19-20 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
Pre 19-20 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
Pre-profile BEN Forecast Gov Cashable | 0 | 0 | 0 | 0 | 0
Pre-profile BEN Forecast Gov Non-Cashable | 0 | 0 | 0 | 0 | 0
Pre-profile BEN Forecast - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
Pre-profile BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
Pre-profile BEN Total | 0 | 0 | 0 | 0 | 0
19-20 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
19-20 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
19-20 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
19-20 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
19-20 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
19-20 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
19-20 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
19-20 BEN Forecast - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
19-20 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
19-20 BEN Forecast - Total | 0 | 0 | 0 | 0 | 0
20-21 Forecast BEN to Date Gov. Cashable
20-21 Forecast BEN to Date Gov. Non-Cashable
20-21 Forecast BEN to Date Economic (inc Private Partner)
20-21 Forecast BEN to Date Disbenefit Economic
20-21 Forecast BEN to Date Total | 0 | 0 | 0 | 0 | 0
20-21 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
20-21 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
20-21 BEN Baseline - Economic (inc Private Partner) | 0 | 21 | 0 | 0 | 0
20-21 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
20-21 BEN Baseline - Total | 0 | 21 | 0 | 0 | 0
20-21 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
20-21 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
20-21 BEN Forecast - Economic (inc Private Partner) | 0 | 21 | 0 | 0 | 0
20-21 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
20-21 BEN Forecast - Total | 0 | 21 | 0 | 0 | 0
21-22 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
21-22 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
21-22 BEN Baseline - Economic (inc Private Partner) | 0 | 22.51 | 0 | 0 | 0
21-22 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
21-22 BEN Baseline - Total | 0 | 22.51 | 0 | 0 | 0
21-22 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
21-22 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
21-22 BEN Forecast - Economic (inc Private Partner) | 0 | 22.51 | 0 | 0 | 0
21-22 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
21-22 BEN Forecast - Total | 0 | 22.51 | 0 | 0 | 0
22-23 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
22-23 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
22-23 BEN Baseline - Economic (inc Private Partner) | 0 | 23.97 | 0 | 0 | 0
22-23 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | -50 | 0
22-23 BEN Baseline - Total | 0 | 23.97 | 0 | -50 | 0
22-23 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
22-23 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
22-23 BEN Forecast - Economic (inc Private Partner) | 0 | 23.97 | 0 | 0 | 0
22-23 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | -50 | 0
22-23 BEN Forecast - Total | 0 | 23.97 | 0 | -50 | 0
23-24 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
23-24 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
23-24 BEN Baseline - Economic (inc Private Partner) | 0 | 25.38 | 0 | 0 | 0
23-24 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | -50 | 0
23-24 BEN Baseline - Total | 0 | 25.38 | 0 | -50 | 0
23-24 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
23-24 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
23-24 BEN Forecast - Economic (inc Private Partner) | 0 | 25.38 | 0 | 0 | 0
23-24 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | -50 | 0
23-24 BEN Forecast - Total | 0 | 25.38 | 0 | -50 | 0
24-25 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
24-25 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
24-25 BEN Baseline - Economic (inc Private Partner) | 0 | 26.77 | 0 | 0 | 0
24-25 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | -50 | 0
24-25 BEN Baseline - Total | 0 | 26.77 | 0 | -50 | 0
24-25 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
24-25 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
24-25 BEN Forecast - Economic (inc Private Partner) | 0 | 26.77 | 0 | 0 | 0
24-25 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | -50 | 0
24-25 BEN Forecast - Total | 0 | 26.77 | 0 | -50 | 0
25-26 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
25-26 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
25-26 BEN Baseline - Economic (inc Private Partner) | 0 | 28.11 | 0 | 0 | 0
25-26 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | -50 | 0
25-26 BEN Baseline - Total | 0 | 28.11 | 0 | -50 | 0
25-26 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
25-26 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
25-26 BEN Forecast - Economic (inc Private Partner) | 3967 | 28.11 | 0 | 0 | 0
25-26 BEN Forecast - Disbenefit UK Economic | -1.36 | 0 | 0 | -50 | 0
25-26 BEN Forecast - Total | 3965.64 | 28.11 | 0 | -50 | 0
26-27 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
26-27 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
26-27 BEN Baseline - Economic (inc Private Partner) | 0 | 29.41 | 0 | 0 | 0
26-27 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
26-27 BEN Baseline - Total | 0 | 29.41 | 0 | 0 | 0
26-27 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
26-27 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
26-27 BEN Forecast - Economic (inc Private Partner) | 3967 | 29.41 | 0 | 0 | 0
26-27 BEN Forecast - Disbenefit UK Economic | -1.38 | 0 | 0 | 0 | 0
26-27 BEN Forecast - Total | 3965.62 | 29.41 | 0 | 0 | 0
27-28 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
27-28 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
27-28 BEN Baseline - Economic (inc Private Partner) | 0 | 30.67 | 0 | 0 | 0
27-28 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
27-28 BEN Baseline - Total | 0 | 30.67 | 0 | 0 | 0
27-28 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
27-28 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
27-28 BEN Forecast - Economic (inc Private Partner) | 3967 | 30.67 | 0 | 0 | 0
27-28 BEN Forecast - Disbenefit UK Economic | -1.4 | 0 | 0 | 0 | 0
27-28 BEN Forecast - Total | 3965.6 | 30.67 | 0 | 0 | 0
28-29 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
28-29 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
28-29 BEN Baseline - Economic (inc Private Partner) | 0 | 31.89 | 0 | 0 | 0
28-29 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
28-29 BEN Baseline - Total | 0 | 31.89 | 0 | 0 | 0
28-29 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
28-29 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
28-29 BEN Forecast - Economic (inc Private Partner) | 3967 | 31.89 | 0 | 0 | 0
28-29 BEN Forecast - Disbenefit UK Economic | -1.42 | 0 | 0 | 0 | 0
28-29 BEN Forecast - Total | 3965.58 | 31.89 | 0 | 0 | 0
29-30 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
29-30 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
29-30 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
29-30 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
29-30 BEN Baseline -Total | 0 | 0 | 0 | 0 | 0
29-30 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
29-30 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
29-30 BEN Forecast - Economic (inc Private Partner) | 3967 | 0 | 0 | 0 | 0
29-30 BEN Forecast - Disbenefit UK Economic | -1.44 | 0 | 0 | 0 | 0
29-30 BEN Forecast - Total | 3965.56 | 0 | 0 | 0 | 0
30-31 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
30-31 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
30-31 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
30-31 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
30-31 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
30-31 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
30-31 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
30-31 BEN Forecast - Economic (inc Private Partner) | 3967 | 0 | 0 | 0 | 0
30-31 BEN Forecast - Disbenefit UK Economic | -1.58 | 0 | 0 | 0 | 0
30-31 BEN Forecast - Total | 3965.42 | 0 | 0 | 0 | 0
31-32 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
31-32 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
31-32 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
31-32 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
31-32 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
31-32 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
31-32 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
31-32 BEN Forecast - Economic (inc Private Partner) | 3967 | 0 | 0 | 0 | 0
31-32 BEN Forecast - Disbenefit UK Economic | -1.71 | 0 | 0 | 0 | 0
31-32 BEN Forecast - Total | 3965.29 | 0 | 0 | 0 | 0
32-33 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
32-33 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
32-33 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
32-33 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
32-33 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
32-33 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
32-33 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
32-33 BEN Forecast - Economic (inc Private Partner) | 3967 | 0 | 0 | 0 | 0
32-33 BEN Forecast - Disbenefit UK Economic | -1.85 | 0 | 0 | 0 | 0
32-33 BEN Forecast - Total | 3965.15 | 0 | 0 | 0 | 0
33-34 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
33-34 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
33-34 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
33-34 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
33-34 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
33-34 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
33-34 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
33-34 BEN Forecast - Economic (inc Private Partner) | 3967 | 0 | 0 | 0 | 0
33-34 BEN Forecast - Disbenefit UK Economic | -1.98 | 0 | 0 | 0 | 0
33-34 BEN Forecast - Total | 3965.02 | 0 | 0 | 0 | 0
34-35 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
34-35 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
34-35 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
34-35 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
34-35 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
34-35 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
34-35 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
34-35 BEN Forecast - Economic (inc Private Partner) | 3967 | 0 | 0 | 0 | 0
34-35 BEN Forecast - Disbenefit UK Economic | -2.11 | 0 | 0 | 0 | 0
34-35 BEN Forecast - Total | 3964.89 | 0 | 0 | 0 | 0
35-36 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
35-36 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
35-36 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
35-36 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
35-36 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
35-36 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
35-36 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
35-36 BEN Forecast - Economic (inc Private Partner) | 3967 | 0 | 0 | 0 | 0
35-36 BEN Forecast - Disbenefit UK Economic | -2.11 | 0 | 0 | 0 | 0
35-36 BEN Forecast - Total | 3964.89 | 0 | 0 | 0 | 0
36-37 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
36-37 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
36-37 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
36-37 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
36-37 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
36-37 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
36-37 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
36-37 BEN Forecast - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
36-37 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
36-37 BEN Forecast - Total | 0 | 0 | 0 | 0 | 0
37-38 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
37-38 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
37-38 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
37-38 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
37-38 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
37-38 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
37-38 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
37-38 BEN Forecast - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
37-38 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
37-38 BEN Forecast - Total | 0 | 0 | 0 | 0 | 0
38-39 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
38-39 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
38-39 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
38-39 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
38-39 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
38-39 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
38-39 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
38-39 BEN Forecast - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
38-39 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
38-39 BEN Forecast - Total | 0 | 0 | 0 | 0 | 0
39-40 BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
39-40 BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
39-40 BEN Baseline - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
39-40 BEN Baseline - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
39-40 BEN Baseline - Total | 0 | 0 | 0 | 0 | 0
39-40 BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
39-40 BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
39-40 BEN Forecast - Economic (inc Private Partner) | 0 | 0 | 0 | 0 | 0
39-40 BEN Forecast - Disbenefit UK Economic | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder BEN Baseline - Economic (inc Private Partner) | 0 | 2158.08 | 3919 | 4512 | 0
Unprofiled Remainder BEN Baseline - Disbenefit UK Economic | 0 | 0 | -425 | 0 | 0
Unprofiled Remainder BEN - Total | 0 | 2158.08 | 3494 | 4512 | 0
Unprofiled Remainder BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
Unprofiled Remainder BEN Forecast - Economic (inc Private Partner) | 0 | 2158.08 | 3919 | 4512 | 0
Unprofiled Remainder BEN Forecast - Disbenefit UK Economic | 0 | 0 | -425 | 0 | 0
Unprofiled Remainder BEN Forecast - Total Monetised Benefits | 0 | 2158.08 | 3494 | 4512 | 0
Total BEN Baseline - Gov. Cashable | 0 | 0 | 0 | 0 | 0
Total BEN Baseline - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
Total BEN Baseline - Economic (inc Private Partner) | 0 | 2397.79 | 3919 | 4512 | 0
Total BEN Baseline - Disbenefit UK Economic | 0 | 0 | -425 | -200 | 0
Total BEN Baseline - Total Monetised Benefits | 0 | 2397.79 | 3494 | 4312 | 0
Total BEN Forecast - Gov. Cashable | 0 | 0 | 0 | 0 | 0
Total BEN Forecast - Gov. Non-Cashable | 0 | 0 | 0 | 0 | 0
Total BEN Forecast - Economic (inc Private Partner) | 43637 | 2397.79 | 3919 | 4512 | 0
Total BEN Forecast - Disbenefit UK Economic | -18.34 | 0 | -425 | -200 | 0
Total BEN Forecast - Total Monetised Benefits | 43618.66 | 2397.79 | 3494 | 4312 | 0
Year BEN spend stops | 2036 | 2079/2080 | 2063/2064 | 2085/2086 | No Monetised Benefits
No Deductions - Net Benefits Provided stored | No | Yes | No | Yes | No
No deductions - Calc Net BEN | No | Yes | No | Yes | No
16-17 Forecast one off new costs
16-17 RDEL Actual recurring new costs |  |  | 0 | 0 | 0
16-17 RDEL Actual recurring old costs |  |  | 0 | 0 | 0
16-17 RDEL Actual Total |  | 0 | 4.09 | 0 | 11.36
16-17 CDEL Forecast one off new costs
16-17 CDEL Actual recurring new costs
16-17 CDEL Actual recurring old costs
16-17 CDEL Actual Total |  | 0 | 0 | 0 | 0
16-17 Actual Non-Gov
17-18 RDEL Forecast one off new costs |  |  | 12 | 0 | 46.72
17-18 RDEL Forecast recurring new costs |  |  |  | 0 | 0
17-18 RDEL Forecast recurring old costs |  |  | 0 | 0 | 0
17-18 RDEL Forecast Total |  | 0 | 12 | 0 | 46.72
17-18 CDEL Forecast one off new costs |  | 379.5 | 174 | 49.9 | 0
17-18 CDEL Forecast recurring new costs |  | 0 |  | 0 | 0
17-18 CDEL Forecast recurring old costs |  | 0 | 0 | 0 | 0
17-18 CDEL Forecast one off new costs |  | 379.5 | 174 | 49.9 | 0
17-18 Forecast Non-Gov |  |  | 96 |  | 174.7
18-19 RDEL Forecast one off new costs |  |  | 37.88 | 0 | 36.22
18-19 RDEL Forecast recurring new costs |  |  |  | 0 | 0
18-19 RDEL Forecast recurring old costs |  |  | 0 | 0 | 0
18-19 RDEL Forecast Non Gov costs |  | 0 | 0 | 0 | 0
18-19 RDEL Forecast Total |  | 0 | 37.88 | 0 | 36.22
18-19 RDEL Forecast Income |  | 0 | 0 | 0 | 0
18-19 CDEL Forecast one off new costs |  | 470 | 25 | 61.9 | 0
18-19 CDEL Forecast recurring new costs |  | 0 |  | 0 | 0
18-19 CDEL Forecast recurring old costs |  | 0 | 0 | 0 | 0
18-19 Forecast Non-Gov |  |  | 96 |  | 71.1
18-19 CDEL Forecast Total WLC |  | 447.8 | 110.25 | 78.4 | 99.9
18-19 Forecast - Income both Revenue and Capital |  |  |  |  | 0
19-20 RDEL Forecast one off new costs | 0 |  | 34.49 | 0 | 33.42
19-20 RDEL Forecast recurring new costs | 0 |  |  | 0 | 0
19-20 RDEL Forecast recurring old costs | 0 |  | 0 | 0 | 0
19-20 RDEL Forecast Non Gov costs | 0 | 0 | 0 | 0 | 0
19-20 RDEL Forecast Total | 0 | 0 | 34.49 | 0 | 33.42
19-20 RDEL Forecast Income | 0 | 0 | 0 | 0 | 0
19-20 CDEL Forecast one off new costs | 0 | 243.9 | 0 | 64.3 | 0
19-20 CDEL Forecast recurring new costs | 0 | 0 | 0 | 0 | 0
19-20 CDEL Forecast recurring old costs | 0 | 0 | 0 | 0 | 0
19-20 Forecast Non-Gov | 0 |  |  | 0 | 30.7
19-20 CDEL Forecast Total WLC | 0 | 320.9 | 0 | 165 | 11.7
19-20 Forecast - Income both Revenue and Capital | 0 |  |  |  | 0
DfT Group | Red | Blue | Red | Green | Blue
Project stage | Outline Business Case
SRO Finance confidence | Amber | Amber/Green | Amber/Red | Red | Green
GMPP - IPA ID Number